## SHZT 24-25 - 1st correction
Annex 5.1 - NETWORK STATEMENT 2024/2025 Network schedule of track closures planned within timetable 2024/2025 - FIRST CORRECTION
No. | IDDE code | Line No. | Line name | Principal | Identification of the station, route or line section, on wich the works will be performed | Track No. | Km from | Km to | Type of work performed | No. of days of track, route, section closure | No. of hours of closure per day | Total No. of closure hours | Speed limit km/h - on adjacted track | Speed limit km/h - after works finish | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 | [12 empty] | The way of traffic control description | Proposed deadlines from | Proposed deadlines to | KPK projects
[15 empty] | XII | I | II | III | IV | V | VI | VII | VIII | IX | X | XI | XII
1 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IZ Częstochowa | st. Częstochowa Towarowa | 7-13 | 231.8 | 233.073 | facilities, railroad surface, network, RTC, power supply | 184 | 24 | 4416 | 50 |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31 | traffic on active track at the station | 2025-03-01 | 2025-08-31 | 1.204
2 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | st. Będzin | 1,2,4 | 305.1 | 306.15 | upgrade | 129 | 24 | 3096 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 22 | traffic on active track at the station | 2024-10-30 | 2025-04-22
3 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | st. Będzin | 3,3a,5,5a,5b,7 | 305.1 | 306.15 | technology commissioning activities | 129 | 4 | 516 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 22 | traffic interruption | 2024-10-30 | 2025-04-22
4 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | st. Będzin | 2,4,6 | 305.1 | 306.15 | upgrade | 30 | 24 | 720 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 8; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 22 | traffic on active track at the station | 2025-04-23 | 2025-05-22
5 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | st. Będzin | 1,3,3a,5,5a,5b,7 | 305.1 | 306.15 | technology commissioning activities | 30 | 4 | 120 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 8; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 22 | traffic interruption | 2025-04-23 | 2025-05-22
6 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | st. Będzin | 4,6 | 305.1 | 306.15 | upgrade | 43 | 24 | 1032 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 7; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 5 | traffic on active track at the station | 2025-06-07 | 2025-08-05
7 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | st. Będzin | 1,2,3,5,7 | 305.1 | 306.15 | technology commissioning activities | 43 | 4 | 172 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 7; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 5 | traffic interruption | 2025-06-07 | 2025-08-05
8 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | Będzin - Sosnowiec Główny | 1,2 | 306.15 | 308.5 | upgrade | 129 | 24 | 3096 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 22 | traffic interruption Travel on track 1(3) LK 659 | 2024-10-30 | 2025-04-22
9 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | Będzin - Sosnowiec Główny | 2 | 306.15 | 308.5 | upgrade | 45 | 24 | 1080 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 8; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 6 | single-track two-way traffic on the active track | 2025-04-23 | 2025-06-06
10 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | Będzin - Sosnowiec Główny | 1 | 306.15 | 308.5 | technology commissioning activities | 45 | 4 | 180 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 8; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 6 | single-track two-way traffic on the active track | 2025-04-23 | 2025-06-06
11 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | Będzin - Sosnowiec Główny | 1,2 | 306.15 | 308.5 | technology commissioning activities | 190 | 4 | 760 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 24; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 13 | traffic interruption | 2025-07-06 | 2026-02-11
12 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | st. Sosnowiec Główny | 2 | 308.4 | 309.8 | upgrade | 14 | 24 | 336 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 8; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 6 | traffic on active track at the station | 2025-05-23 | 2025-06-06
13 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | st. Sosnowiec Główny | 2 | 308.4 | 309.8 | technology commissioning activities | 159 | 4 | 636 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 22 | traffic interruption | 2024-10-30 | 2025-05-22
14 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | st. Sosnowiec Główny | 1,3,5,7,9,11,13 | 308.4 | 309.8 | technology commissioning activities | 174 | 4 | 636 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 6 | traffic interruption | 2024-10-30 | 2025-06-06
15 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | st. Sosnowiec Główny | 1,2,3,5,7,9, 11,13 | 308.4 | 309.8 | upgrade | 140 | 24 | 3360 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 24; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 24 | traffic on active track at the station | 2025-06-07 | 2025-10-24
16 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | st. Sosnowiec Główny | 1,2,3,5,7,9,11,13 | 308.4 | 309.8 | upgrade | 50 | 24 | 1200 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 7; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-10-25 | 2026-07-11
17 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | Sosnowiec Główny - Katowice Zawodzie | 1,2 | 310.9 | 312.2 | technology commissioning activities | 129 | 4 | 516 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 22 | traffic interruption | 2024-10-30 | 2025-04-22
18 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | Sosnowiec Główny - Katowice Zawodzie | 1,2 | 310.9 | 312.2 | technology commissioning activities | 60 | 4 | 240 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 24; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 5 | traffic interruption | 2025-06-07 | 2025-08-05
19 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | Sosnowiec Główny - Katowice Zawodzie | 2 | 310.9 | 312.2 | upgrade | 80 | 24 | 1920 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 26; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 24 | single-track two-way traffic on the active track | 2025-08-06 | 2025-10-24
20 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | Sosnowiec Główny - Katowice Zawodzie | 1 | 310.9 | 312.2 | technology commissioning activities | 80 | 4 | 320 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 26; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 24 | traffic interruption | 2025-08-06 | 2025-10-24
21 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | Sosnowiec Główny - Katowice Zawodzie | 1,2 | 310.9 | 312.2 | upgrade | 49 | 24 | 1176 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 6; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption Travel on track 6 LK 660 | 2025-10-25 | 2026-07-11
22 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | st. Katowice | 1 | 317.023 | 318.686 | upgrade | 167 | 24 | 4008 | 40 | 120 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 30 | traffic on active track at the station | 2024-12-16 | 2025-05-30
23 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | st. Katowice | 2 | 317.023 | 318.686 | upgrade | 142 | 24 | 3048 | 40 | 120 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 20 | traffic on active track at the station | 2025-05-02 | 2025-09-20
24 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | st. Katowice | 4 | 317.023 | 318.686 | upgrade | 113 | 24 | 2712 | 40 | 120 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 23 | traffic on active track at the station | 2025-06-03 | 2025-09-23
25 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | st. Katowice | 6 | 317.023 | 318.686 | upgrade | 183 | 24 | 4392 | 40 | 120 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 2 | traffic on active track at the station | 2025-06-03 | 2025-12-02
26 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | st. Katowice | 13,13a | 317.023 | 318.686 | upgrade | 11 | 24 | 264 | 40 | 120 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 11 | traffic on active track at the station | 2025-12-03 | 2026-01-30
27 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | st. Katowice | 15a | 317.023 | 318.686 | upgrade | 11 | 24 | 264 | 40 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 11 | traffic on active track at the station | 2025-12-03 | 2026-06-29
28 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | st. Katowice | 17 | 317.023 | 318.686 | upgrade | 11 | 24 | 264 | 40 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 11 | traffic on active track at the station | 2025-12-03 | 2026-06-29
29 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | st. Katowice | 8 | 317.023 | 318.686 | upgrade | 11 | 24 | 264 | 40 | 60 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 11 | traffic on active track at the station | 2025-12-03 | 2026-03-31
30 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | Warszawa Zachodnia - Warszawa Centralna | 1, 2 | -2.62 | -0.3 | Upgrade of railway lines and railway stations | 184 | 24 | 4416 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 18; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-06-13 | 2027-06-13 | 1.093
31 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | st. Warszawa Centralna | 1, 2, 3, 4, 5, 6, 7, 8 | -0.3 | 0.2 | Upgrade of railway lines and railway stations | 184 | 24 | 4416 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 18; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-06-13 | 2027-06-13 | 1.093
32 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | Warszawa Centralna - Warszawa Wschodnia | 1, 2 | 0.2 | 3.69 | Upgrade of railway lines and railway stations | 184 | 24 | 4416 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 18; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-06-13 | 2027-06-13 | 1.093
33 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | st. Warszawa Wschodnia | 1, 1a, 3, 3a, 4, 4a, 4b, 4c, 51, 52, 53, 54, 6, 8, 10, 12, 1T, 2s, 5a, 5b, 40, 41, 44, 61, 63, 81 | 3.69 | 4.516 | Upgrade of railway lines and railway stations | 184 | 24 | 4416 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 18; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-06-13 | 2027-06-13 | 1.093
34 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | st. Warszawa Wschodnia | 74, 72, 70, 18, 16, 14 | 4.516 | 4.916 | Upgrade of railway lines and railway stations | 184 | 24 | 4416 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 18; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-06-13 | 2027-06-13 | 1.093
35 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | Warszawa Wschodnia - Warszawa Podskarbińska | 1M, 2M | 4.516 | 6.435 | Upgrade of railway lines and railway stations | 184 | 24 | 4416 | 20 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 18; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-06-13 | 2027-06-13 | 1.093
36 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | Warszawa Antoninów - Warszawa Rembertów | 1m | 9.4 | 9.6 | viaduct construction | 364 | 4 | 1456 | 50 | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | single-track two-way traffic on the active track | 2024-02-02 | 2026-02-01 | 1.066
37 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | Warszawa Rembertów | 2m | 11.673 | 11.823 | tunnel construction | 104 | 24 | 2496 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-09-01 | 2025-12-17 | 1.066
38 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | Warszawa Rembertów | 1m | 11.673 | 11.823 | tunnel construction | 78 | 24 | 1872 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 2 | traffic on active track at the station | 2024-09-02 | 2025-03-02 | 1.066
39 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | Warszawa Rembertów - Sulejówek Miłosna | 1 | 16.2 | 16.4 | tunnel construction | 17 | 24 | 408 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 17 | single-track two-way traffic on the active track | 2025-07-01 | 2025-07-17 | 1.066
40 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | Warszawa Rembertów - Sulejówek Miłosna | 1, 2 | 16.2 | 16.4 | tunnel construction | 306 | 4 | 1224 | 50 | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 16 |  |  | traffic interruption | 2024-06-03 | 2025-10-16 | 1.066
41 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/5 | Sokule - Biała Podlaska | 1,2 | 160.556 | 171.799 | upgrade | 364 | 4 | 1456 | no limit | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2023-10-11 | 2028-10-10 | 1.123
42 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/5 | st. Biała Podlaska | 1,2 | 171.799 | 174.121 | upgrade | 364 | 4 | 1456 | no limit | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic on active track at the station | 2023-10-11 | 2028-10-10 | 1.123
43 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/5 | Biała Podlaska - Chotyłów | 1,2 | 174.121 | 188.019 | upgrade | 364 | 4 | 1456 | no limit | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2023-10-11 | 2028-10-10 | 1.123
44 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/5 | Chotyłów - Małaszewicze | 1,2 | 190.33 | 198.49 | upgrade | 364 | 4 | 1456 | no limit | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2023-10-11 | 2028-10-10 | 1.123
45 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/5 | Magdalenka - Małaszewicze Południowe | 1,2 | 198.051 | 198.49 | upgrade | 364 | 4 | 1456 | no limit | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2023-10-11 | 2028-10-10 | 1.123
46 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/5 | st. Małaszewicze | 1,2 | 198.49 | 200.118 | upgrade | 364 | 4 | 1456 | no limit | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic on active track at the station | 2023-10-11 | 2028-10-10 | 1.123
47 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/5 | Małaszewicze - Terespol | 1,2 | 200.118 | 207.502 | upgrade | 364 | 4 | 1456 | no limit | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2023-10-11 | 2028-10-10 | 1.123
48 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/5 | st. Terespol | 1,2 | 207.502 | 210.3 | upgrade | 364 | 4 | 1456 | no limit | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic on active track at the station | 2023-10-11 | 2028-10-10 | 1.123
49 | 1 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR1/1 | Teresin | 1,3,5 | 41.73 | 41.75 | construction of a railway viaduct | 178 | 4 | 712 | 40 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 10 | traffic on active track at the station | 2024-12-15 | 2025-06-10 | 1.066
50 | 1 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR1/1 | Teresin | 2 | 41.73 | 41.75 | construction of a railway viaduct | 186 | 4 | 744 | 40 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 20; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-06-11 | 2025-12-13 | 1.066
51 | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Poznań Wchód - Swarzędz | 2 | 292.4 | 298.5 | renovation | 90 | 24 | 2160 | 50 | announcing trains using telephone communication | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 16; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-09-15 | 2026-01-04 | 1.117
52 | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7/3 | Poznań Górczyn - Palędzie | 1 | 310.895 | 317.025 | surface work | 19 | 24 | 456 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 2 | single-track two-way traffic on the active track | 2024-12-03 | 2025-01-02
53* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Nowy Tomyśl (głowica Rz od strony Pń) | 1,3 | 360.953 | 362.562 | surface work | 6 | 24 | 144 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 6 | traffic on active track at the station | 2025-11-17 | 2025-11-22
54* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Nowy Tomyśl (głowica Rz od strony Zbk) | 1,3 | 360.953 | 362.562 | surface work | 18 | 24 | 432 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 9; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 9 | traffic on active track at the station | 2025-11-22 | 2025-12-22
55* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Poznań Górczyn - Palędzie | 1 | 310.895 | 317.025 | surface work | 1 | 24 | 24 | 60 | no limit | [13 empty] | single-track two-way traffic on the active track | 2024-11-11 | 2024-12-11 | bar: Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII
56* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Poznań Górczyn - Palędzie | 1 | 310.895 | 317.025 | surface work | 21 | 24 | 504 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 21 | single-track two-way traffic on the active track | 2024-12-11 | 2024-12-31
57* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Poznań Górczyn - Palędzie | 2 | 310.895 | 317.025 | surface work | 31 | 24 | 744 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 22; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 9 | single-track two-way traffic on the active track | 2025-01-10 | 2025-02-09
58* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Poznań Górczyn - Palędzie | 2 | 310.895 | 317.025 | surface work | 21 | 24 | 504 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 20; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 1 | single-track two-way traffic on the active track | 2025-02-09 | 2025-03-01
59* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Palędzie | 1,3 | 317.025 | 318.565 | surface work | 21 | 24 | 504 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 21 | traffic on active track at the station | 2024-12-11 | 2024-12-31
60* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Palędzie | 1,3 | 317.025 | 318.565 | surface work | 11 | 24 | 264 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 1; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 10 | traffic on active track at the station | 2024-12-31 | 2025-01-10
61* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Palędzie (głowica RZ od strony Pń) | 2,4,6 | 317.025 | 318.565 | surface work | 21 | 24 | 504 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 20; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 1 | traffic on active track at the station | 2025-02-09 | 2025-03-01
62* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Palędzie (głowica RZ od strony Zbk) | 2,4,6 | 317.025 | 318.565 | surface work | 21 | 24 | 504 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 21 | traffic on active track at the station | 2025-03-01 | 2025-03-21
63* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Palędzie - Buk | 1 | 318.565 | 334.07 | surface work | 11 | 24 | 264 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 1; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 10 | single-track two-way traffic on the active track | 2024-12-31 | 2025-01-10
64* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Palędzie - Buk | 1 | 318.565 | 334.07 | surface work | 41 | 24 | 984 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 11; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | single-track two-way traffic on the active track | 2025-03-21 | 2025-04-30
65* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Palędzie - Buk | 1 | 318.565 | 334.07 | surface work | 11 | 24 | 264 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 1; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 10 | single-track two-way traffic on the active track | 2025-04-30 | 2025-05-10
66* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Palędzie - Buk | 2 | 318.565 | 334.07 | surface work | 21 | 24 | 504 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 21 | single-track two-way traffic on the active track | 2025-03-01 | 2025-03-21
67* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Palędzie - Buk | 2 | 318.565 | 334.07 | surface work | 41 | 24 | 984 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 15; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 26 | single-track two-way traffic on the active track | 2025-05-17 | 2025-06-26
68* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Palędzie - Buk | 2 | 318.565 | 334.07 | surface work | 8 | 24 | 192 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 5; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 3 | single-track two-way traffic on the active track | 2025-06-26 | 2025-07-03
69* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Buk (głowica Rz od strony Pń) | 1,3 | 334.07 | 335.553 | surface work | 11 | 24 | 264 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 1; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 10 | traffic on active track at the station | 2025-04-30 | 2025-05-10
70* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Buk (głowica Rz od strony Zbk) | 1,3 | 334.07 | 335.553 | surface work | 8 | 24 | 192 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 8 | traffic on active track at the station | 2025-05-10 | 2025-05-17
71* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Buk (głowica Rz od strony Pń) | 2,4,6 | 334.07 | 335.553 | surface work | 8 | 24 | 192 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 5; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 3 | traffic on active track at the station | 2025-06-26 | 2025-07-03
72* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Buk (głowica Rz od strony Zbk) | 2,4,6 | 334.07 | 335.553 | surface work | 8 | 24 | 192 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 8 | traffic on active track at the station | 2025-07-03 | 2025-07-10
73* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Buk - Opalenica | 1 | 335.553 | 343.044 | surface work | 8 | 24 | 192 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 8 | single-track two-way traffic on the active track | 2025-05-10 | 2025-05-17
74* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Buk - Opalenica | 1 | 335.553 | 343.044 | surface work | 26 | 24 | 624 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 22; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 4 | single-track two-way traffic on the active track | 2025-07-10 | 2025-08-04
75* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Buk - Opalenica | 1 | 335.553 | 343.044 | surface work | 16 | 24 | 384 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 16 | single-track two-way traffic on the active track | 2025-08-04 | 2025-08-19
76* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Buk - Opalenica | 2 | 335.553 | 343.044 | surface work | 8 | 24 | 192 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 8 | single-track two-way traffic on the active track | 2025-07-03 | 2025-07-10
77* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Buk - Opalenica | 2 | 335.553 | 343.044 | surface work | 21 | 24 | 504 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 21 | single-track two-way traffic on the active track | 2025-09-08 | 2025-09-28
78* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Buk - Opalenica | 2 | 335.553 | 343.044 | surface work | 16 | 24 | 384 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 3; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 13 | single-track two-way traffic on the active track | 2025-09-28 | 2025-10-13
79* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Opalenica (głowica Rz od strony Pń) | 1,3,5 | 343.044 | 344.601 | surface work | 16 | 24 | 384 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 16 | traffic on active track at the station | 2025-08-04 | 2025-08-19
80* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Opalenica (głowica Rz od strony Zbk) | 1,3,5 | 343.044 | 344.601 | surface work | 21 | 24 | 504 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 13; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 8 | traffic on active track at the station | 2025-08-19 | 2025-09-08
81* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Opalenica (głowica Rz od strony Pń) | 2,4,6 | 343.044 | 344.601 | surface work | 16 | 24 | 384 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 3; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 13 | traffic on active track at the station | 2025-09-28 | 2025-10-13
82* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Opalenica (głowica Rz od strony Zbk) | 2,4,6 | 343.044 | 344.601 | surface work | 16 | 24 | 384 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 16 | traffic on active track at the station | 2025-10-13 | 2025-10-28
83* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Opalenica - Nowy Tomyśl | 2 | 344.601 | 360.953 | surface work | 16 | 24 | 384 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 16 | single-track two-way traffic on the active track | 2025-10-13 | 2025-10-28
84* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Opalenica - Porażyn | 1 | 344.601 | 351.19 | surface work | 21 | 24 | 504 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 13; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 8 | single-track two-way traffic on the active track | 2025-08-19 | 2025-09-08
85* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Porażyn - Nowy Tomyśl | 1 | 351.19 | 360.953 | surface work | 21 | 24 | 504 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 4; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 17 | single-track two-way traffic on the active track | 2025-10-28 | 2025-11-17
86* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Porażyn - Nowy Tomyśl | 1 | 351.19 | 360.953 | surface work | 6 | 24 | 144 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 6 | single-track two-way traffic on the active track | 2025-11-17 | 2025-11-22
87* | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/7 | Nowy Tomyśl - Zbąszyń | 1 | 362.562 | 373.1 | surface work | 18 | 24 | 432 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 9; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 9 | single-track two-way traffic on the active track | 2025-11-22 | 2025-12-22
88 |  | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IZ Warszawa | Warszawa Włochy - Warszawa Gołąbki | 2 |  |  | upgrade of walkway at km 10.672 l.3 | 28 | 6 | 168 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28 | single-track two-way traffic on the active track | 2025-02-01 | 2025-02-28
89 |  | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IZ Warszawa | Warszawa Włochy - Warszawa Gołąbki | 1 |  |  | upgrade of walkway at km 10.672 l.3 alternating closure | 91 | 8 | 728 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 30 | single-track two-way traffic on the active track | 2025-03-01 | 2025-05-30
90 |  | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IZ Warszawa | Warszawa Włochy - Warszawa Gołąbki | 2 |  |  | upgrade of walkway at km 10.672 l.3 alternating closure | 91 | 8 | 728 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 30 | single-track two-way traffic on the active track | 2025-03-01 | 2025-05-30
91 |  | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IZ Warszawa | Warszawa Włochy - Warszawa Gołąbki | 1 |  |  | upgrade of walkway at km 10.672 l.3 alternating closure | 30 | 6 | 180 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 30 | single-track two-way traffic on the active track | 2025-08-01 | 2025-08-30
92 |  | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IZ Warszawa | Warszawa Włochy - Warszawa Gołąbki | 2 |  |  | upgrade of walkway at km 10.672 l.3 alternating closure | 30 | 6 | 180 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 30 | single-track two-way traffic on the active track | 2025-08-01 | 2025-08-30
93 |  | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IZ Warszawa | Warszawa Włochy - Warszawa Gołąbki | 1 |  |  | platform upgrade; viaduct renovation; major track repair; | 30 | 24 | 720 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 29; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 1 | single-track two-way traffic on the active track | 2025-06-02 | 2025-07-01
94 |  | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IZ Warszawa | Warszawa Włochy - Warszawa Gołąbki | 2 |  |  | platform upgrade; viaduct renovation; major track repair; | 30 | 24 | 720 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 30 | single-track two-way traffic on the active track | 2025-07-02 | 2025-07-31
95 |  | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IZ Warszawa | Warszawa Gołąbki - Bednary | 1 |  |  | renovation of culverts at km 46.202; 49.197 | 30 | 24 | 720 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 30 | single-track two-way traffic on the active track | 2025-05-01 | 2025-05-30
96 |  | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IZ Warszawa | Bednary - Warszawa Gołabki | 2 |  |  | renovation of culverts at km 46.202; 49.197 | 30 | 24 | 720 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30 | single-track two-way traffic on the active track | 2025-06-01 | 2025-06-30
97 |  | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IZ Warszawa | Barłogi - Koło | 1 |  |  | bridge upgrade 167.917 | 122 | 24 | 2928 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30 | single-track two-way traffic on the active track | 2025-03-01 | 2025-06-30
98 |  | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IZ Warszawa | Koło - Barłogi | 2 |  |  | bridge upgrade 167.917 | 122 | 24 | 2928 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 30 | single-track two-way traffic on the active track | 2025-07-01 | 2025-10-30
99 | 1 | 7 | WARSZAWA WSCHODNIA OSOBOWA - DOROHUSK | IRR1/3 | Warszawa Międzylesie - Warszawa Falenica | 2 | 15.127 | 19.51 | Upgrade | 273 | 24 | 6552 |  | 120 |  |  |  | 16 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | single-track two-way traffic on the active track | 2025-03-16 | 2026-03-14
100 | 1 | 7 | WARSZAWA WSCHODNIA OSOBOWA - DOROHUSK | IRR1/3 | Warszawa Międzylesie - Otwock | 1 | 15.127 | 26.05 | Upgrade | 273 | 4 | 1092 |  | 120 |  |  |  | 16 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2025-03-16 | 2026-03-14
101 | 1 | 7 | WARSZAWA WSCHODNIA OSOBOWA - DOROHUSK | IRR1/3 | st. Falenica | 3,3a,4,5,9 | 20.04 | 21.825 | Upgrade | 91 | 24 | 2184 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 15 | traffic on active track at the station | 2024-09-25 | 2025-03-15
102 | 1 | 7 | WARSZAWA WSCHODNIA OSOBOWA - DOROHUSK | IRR1/3 | st. Falenica | 2, 2c | 20.04 | 21.825 | Upgrade | 273 | 24 | 6552 | [5 empty] | 16 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic on active track at the station | 2025-03-16 | 2026-03-14
103 | 1 | 7 | WARSZAWA WSCHODNIA OSOBOWA - DOROHUSK | IRR1/3 | Warszawa Falenica - Otwock | 2 | 21.99 | 26.05 | Upgrade | 273 | 24 | 6552 |  | 120 |  |  |  | 16 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | single-track two-way traffic on the active track | 2025-03-16 | 2026-03-14
104 | 1 | 7 | WARSZAWA WSCHODNIA OSOBOWA - DOROHUSK | IRR1/1 | Otwock - Celestynów | 1 | 28.872 | 36.731 | Disassembly and assembly of the contact line for the purpose of facility construction, removal of RTC collisions | 178 | 4 | 712 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 10 | single-track two-way traffic on the active track | 2024-12-15 | 2025-06-10 | 1.066
105 | 1 | 7 | WARSZAWA WSCHODNIA OSOBOWA - DOROHUSK | IRR1/1 | Otwock - Celestynów | 2 | 28.872 | 36.731 | Disassembly and assembly of the contact line for the purpose of facility construction, removal of RTC collisions | 186 | 4 | 744 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 20; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-06-11 | 2025-12-13 | 1.066
106 | 1 | 7 | WARSZAWA WSCHODNIA OSOBOWA - DOROHUSK | IRR1/1 | Celestynów | 1 | 36.731 | 40.7 | Disassembly and assembly of the contact line for the purpose of facility construction, removal of RTC collisions | 178 | 4 | 712 | 40 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 10 | traffic on active track at the station | 2024-12-15 | 2025-06-10 | 1.066
107 | 1 | 7 | WARSZAWA WSCHODNIA OSOBOWA - DOROHUSK | IRR1/1 | Celestynów | 2 | 36.731 | 40.7 | Disassembly and assembly of the contact line for the purpose of facility construction, removal of RTC collisions | 186 | 4 | 744 | 40 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 20; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-06-11 | 2025-12-13 | 1.066
108 | 1 | 7 | WARSZAWA WSCHODNIA OSOBOWA - DOROHUSK | IRR1/1 | Celestynów- Pilawa | 2 | 40.7 | 52.829 | Disassembly and assembly of the contact line for the purpose of facility construction, removal of RTC collisions | 186 | 4 | 744 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 20; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-06-11 | 2025-12-13 | 1.066
109 | 2 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IRR1/2 | Lesiów - Radom Wschodni | 1 | 97 | 101.4 | Reconstruction of the contact line, drainage and other colliding infrastructure, construction of a platform in the intertrack space between tracks No. 1 and 2 of line No. 8 at km 101.000 – 101.400 | 14 | 6 | 84 | 30 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 14 | traffic interruption | 2023-07-06 | 2024-12-28 | 4.022
110 | 2 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IRR1/2 | Lesiów - Radom Wschodni | 2 | 97 | 101.4 | Reconstruction of the contact line, drainage and other colliding infrastructure, construction of a platform in the intertrack space between tracks No. 1 and 2 of line No. 8 at km 101.000 – 101.400 | 14 | 6 | 84 | 30 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 14 | traffic interruption | 2023-07-06 | 2024-12-28 | 4.022
111 | 3 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IZ Kraków | Słomniki | 1.3 | 290.7 | 291.125 | Contact line upgrade | 22 | 24 | 528 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 22 | traffic on active track at the station | 2025-06-05 | 2025-06-26
112 | 3 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IZ Kraków | Słomniki | 2.4 | 290.7 | 291.125 | Contact line upgrade | 21 | 24 | 504 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 16; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 5 | traffic on active track at the station | 2025-08-16 | 2025-09-05
113 | 3 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IZ Kraków | Słomniki - Niedźwiedź | 1 | 291.125 | 295 | Contact line upgrade | 72 | 24 | 1728 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 26; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 15 | single-track two-way traffic on the active track | 2025-06-05 | 2025-08-15
114 | 3 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IZ Kraków | Słomniki - Niedźwiedź | 2 | 291.125 | 295 | Contact line upgrade | 79 | 24 | 1896 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 2; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 16 | single-track two-way traffic on the active track | 2025-08-16 | 2025-11-16
115 | 3 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IZ Kraków | Niedźwiedź | 1,3,5,7 | 295 | 295.44 | Contact line upgrade | 19 | 24 | 456 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 4; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 15 | traffic on active track at the station | 2025-07-28 | 2025-08-15
116 | 3 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IZ Kraków | Niedźwiedź | 2 | 295 | 296.2 | Contact line upgrade | 19 | 24 | 456 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 19 | traffic on active track at the station | 2025-10-13 | 2025-10-31
117 | 1 | 9 | WARSZAWA WSCHODNIA OSOBOWA - GDAŃSK GŁÓWNY | IRR1/11 | st. Warszawa Wschodnia | 2, 2a, 2b | 3.69 | 4.516 | Upgrade of railway lines and railway stations | 184 | 24 | 4416 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 18; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-06-13 | 2027-06-13 | 1.093
118 | 1 | 9 | WARSZAWA WSCHODNIA OSOBOWA - GDAŃSK GŁÓWNY | IRR1/11 | Warszawa Wschodnia - Warszawa Praga | 1WS, 2WS | 4.407 | 5.12 | Upgrade of railway lines and railway stations | 184 | 24 | 4416 | 20 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 18; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-06-13 | 2027-06-13 | 1.093
119 | 1 | 11 | SKIERNIEWICE - ŁOWICZ GŁÓWNY | IZ Łódź | Skierniewice - Bełchów | 1 | 2.23 | 10.132 | Track works, engineering structure works, contact line, RTC, telecommunications | 201 | 24 | 4824 | 50 | no limit |  | 3 | 28 | 31 | 30 | 31 | 30 | 31 | 17 |  |  |  |  | single-track two-way traffic on the active track | 2025-01-29 | 2025-08-17
120 | 1 | 11 | SKIERNIEWICE - ŁOWICZ GŁÓWNY | IZ Łódź | Skierniewice - Bełchów | 2 | 2.23 | 10.132 | Track works, engineering structure works, contact line, RTC, telecommunications | 118 | 24 | 2832 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 14; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-08-18 | 2026-03-05
121 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | st. Puszcza Mariańska | 2,4,6,8 | 12.1 | 15.325 | upgrade | 178 | 24 | 4272 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 6; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 19 | traffic on active track at the station | 2025-02-23 | 2025-08-19
122 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | st. Puszcza Mariańska | 1 | 12.1 | 15.325 | upgrade | 178 | 4 | 712 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 6; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 19 | traffic interruption | 2025-02-23 | 2025-08-19
123 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Puszcza Mariańska - Mszczonów | 2 | 15.325 | 25.61 | upgrade | 178 | 24 | 4272 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 6; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 19 | single-track two-way traffic on the active track | 2025-02-23 | 2025-08-19
124 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Puszcza Mariańska - Mszczonów | 1 | 15.325 | 25.61 | upgrade | 178 | 4 | 712 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 6; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 19 | traffic interruption | 2025-02-23 | 2025-08-19
125 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Marków- Mszczonów | 2 | 24.682 | 25.61 | upgrade | 116 | 4 | 464 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 12; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-08-20 | 2026-01-18
126 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Marków- Mszczonów | 1 | 24.682 | 25.61 | upgrade | 116 | 24 | 2784 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 12; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-08-20 | 2026-01-18
127 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | st. Mszczonów | 3 | 25.61 | 29.97 | Track 3 axial offsetting to enable foundation of contact line gantries | 46 | 24 | 1104 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 24; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 22 | traffic on active track at the station | 2025-01-08 | 2025-02-22
128 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | st. Mszczonów | 1,2 | 25.61 | 29.97 | Track 3 axial offsetting to enable foundation of contact line gantries | 46 | 4 | 184 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 24; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 22 | traffic interruption | 2025-01-08 | 2025-02-22
129 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | st. Mszczonów | 1,3 | 25.61 | 29.97 | upgrade | 116 | 24 | 2784 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 12; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-08-20 | 2026-01-18
130 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | st. Mszczonów | 2 | 25.61 | 29.97 | upgrade | 116 | 4 | 464 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 12; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-08-20 | 2026-01-18
131 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Mszczonów - Tarczyn | 2 | 29.97 | 46.41 | Installation of new Rz43 | 15 | 24 | 360 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 15 | single-track two-way traffic on the active track | 2025-01-15 | 2025-01-29
132 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Mszczonów - Tarczyn | 1 | 29.97 | 46.41 | Installation of new Rz43 | 15 | 4 | 60 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 15 | traffic interruption | 2025-01-15 | 2025-01-29
133 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Mszczonów - Tarczyn | 1 | 29.97 | 46.41 | Installation of new Rz43 | 16 | 24 | 384 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 2; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 14 | single-track two-way traffic on the active track | 2025-01-30 | 2025-02-14
134 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Mszczonów - Tarczyn | 2 | 29.97 | 46.41 | Installation of new Rz43 | 16 | 4 | 64 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 2; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 14 | traffic interruption | 2025-01-30 | 2025-02-14
135 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Mszczonów - Tarczyn | 1 | 29.97 | 46.41 | upgrade | 116 | 24 | 2784 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 12; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-08-20 | 2026-01-18
136 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Mszczonów - Tarczyn | 2 | 29.97 | 46.41 | upgrade | 116 | 4 | 464 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 12; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-08-20 | 2026-01-18
137 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | st. Tarczyn | 6,8,10 | 46.41 | 48.655 | track demolition for contact line branch | 46 | 24 | 1104 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 24; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 22 | traffic on active track at the station | 2025-01-08 | 2025-02-22
138 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | st. Tarczyn | 1,2,3,4 | 46.41 | 48.655 | track demolition for contact line branch | 46 | 4 | 184 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 24; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 22 | traffic interruption | 2025-01-08 | 2025-02-22
139 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Czachówek Zachodni - Czachówek Wschodni | 2 | 64.52 | 66.439 | upgrade | 116 | 4 | 464 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 12; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-08-20 | 2026-01-18
140 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Czachówek Zachodni - Czachówek Wschodni | 2 | 64.52 | 66.439 | upgrade | 103 | 24 | 2472 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 8; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 4 | single-track two-way traffic on the active track | 2025-03-24 | 2025-07-04
141 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Czachówek Zachodni - Czachówek Wschodni | 1 | 64.52 | 66.439 | upgrade | 103 | 4 | 412 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 8; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 4 | traffic interruption | 2025-03-24 | 2025-07-04
142 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Czachówek Zachodni - Czachówek Wschodni | 1 | 64.52 | 66.439 | upgrade | 116 | 24 | 2784 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 12; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-08-20 | 2026-01-18
143 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | st. Czachówek Wschodni | 3,4 | 66.005 | 69.74 | track demolition for contact line branch | 46 | 24 | 1104 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 24; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 22 | traffic on active track at the station | 2025-01-08 | 2025-02-22
144 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | st. Czachówek Wschodni | 1,2 | 66.005 | 69.74 | track demolition for contact line branch | 46 | 4 | 184 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 24; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 22 | traffic interruption | 2025-01-08 | 2025-02-22
145 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Czachówek Wschodni - Góra Kalwaria | 2 | 67.94 | 71.985 | upgrade | 178 | 24 | 4272 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 6; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 19 | single-track two-way traffic on the active track | 2025-02-23 | 2025-08-19
146 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Czachówek Wschodni - Góra Kalwaria | 1 | 67.94 | 71.985 | upgrade | 178 | 4 | 712 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 6; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 19 | traffic interruption | 2025-02-23 | 2025-08-19
147 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Czachówek Wschodni - Góra Kalwaria | 2 | 67.94 | 71.985 | upgrade | 116 | 4 | 464 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 12; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-08-20 | 2026-01-18
148 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Czachówek Wschodni - Góra Kalwaria | 1 | 67.94 | 71.985 | upgrade | 116 | 24 | 2784 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 12; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-08-20 | 2026-01-18
149 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | st. Góra Kalwaria | 2,4 | 71.985 | 73.836 | upgrade | 178 | 24 | 4272 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 6; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 19 | traffic on active track at the station | 2025-02-23 | 2025-08-19
150 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | st. Góra Kalwaria | 1 | 71.985 | 73.836 | upgrade | 178 | 4 | 712 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 6; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 19 | traffic on active track at the station | 2025-02-23 | 2025-08-19
151 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | st. Osieck | 1 | 88.446 | 90.66 | disassembly of existing Rz27 and installation of new Rz on track 2 | 16 | 4 | 64 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 7; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 9 | traffic on active track at the station | 2025-02-22 | 2025-03-09
152 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | st. Osieck | 2 | 88.446 | 90.66 | disassembly of existing Rz27 and installation of new Rz on track 2 | 16 | 24 | 384 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 7; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 9 | traffic on active track at the station | 2025-02-22 | 2025-03-09
153 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Osieck - Jaźwiny | 2 | 90.66 | 96.196 | disassembly of existing Rz27 and installation of new Rz on track 2 | 16 | 24 | 384 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 7; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 9 | single-track two-way traffic on the active track | 2025-02-22 | 2025-03-09
154 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Osieck - Jaźwiny | 1 | 90.66 | 96.196 | disassembly of existing Rz27 and installation of new Rz on track 2 | 16 | 4 | 64 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 7; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 9 | traffic interruption | 2025-02-22 | 2025-03-09
155 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Osieck - Jaźwiny | 1 | 90.66 | 96.196 | upgrade | 116 | 24 | 2784 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 12; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-08-20 | 2026-01-18
156 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Osieck - Jaźwiny | 2 | 90.66 | 96.196 | upgrade | 116 | 4 | 464 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 12; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-08-20 | 2026-01-18
157 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Jaźwiny- Pilawa | 1 | 96.196 | 101.163 | upgrade | 15 | 24 | 360 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 15 | single-track two-way traffic on the active track | 2025-03-10 | 2025-03-24
158 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Jaźwiny- Pilawa | 2 | 96.196 | 101.163 | upgrade | 15 | 4 | 60 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 15 | traffic interruption | 2025-03-10 | 2025-03-24
159 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Jaźwiny- Pilawa | 1 | 96.196 | 101.163 | upgrade | 116 | 24 | 2784 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 12; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-08-20 | 2026-01-18
160 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Jaźwiny- Pilawa | 2 | 96.196 | 101.163 | upgrade | 116 | 4 | 464 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 12; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-08-20 | 2026-01-18
161 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Jedlanka- Łuków | 2 | 131.719 | 161.16 | upgrade | 223 | 24 | 5352 |  | no limit |  | 23 | 28 | 31 | 30 | 31 | 30 | 31 | 19 |  |  |  |  | single-track two-way traffic on the active track | 2025-01-09 | 2025-08-19
162 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Jedlanka- Łuków | 1 | 131.719 | 161.16 | upgrade | 223 | 4 | 892 |  | no limit |  | 23 | 28 | 31 | 30 | 31 | 30 | 31 | 19 |  |  |  |  | traffic interruption | 2025-01-09 | 2025-08-19
163 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Stoczek Łukowski - Jedlanka | 1 | 131.719 | 161.16 | upgrade | 116 | 24 | 2784 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 12; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-08-20 | 2026-01-18
164 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Stoczek Łukowski - Jedlanka | 2 | 131.719 | 161.16 | upgrade | 116 | 4 | 464 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 12; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-08-20 | 2026-01-18
165 | 7 | 14 | ŁÓDŹ KALISKA - TUPLICE | IZ Ostrów Wlkp. | Ostrów Wielkopolski - Ostrów Wielkopolski Zachodni | 1 | 137.348 | 138.1 | Track surface replacement on 60 E1 | 46 | 24 | 1104 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 15; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31 | single-track two-way traffic on the active track | 2025-06-16 | 2025-07-31
166 | 7 | 14 | ŁÓDŹ KALISKA - TUPLICE | IZ Ostrów Wlkp. | Leszno | 4.6 | 236.21 | 236.21 | End-to-end repair of rail and road crossing | 21 | 24 | 504 | 50 |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 21 | traffic on active track at the station | 2025-05-01 | 2025-05-21
167 | 7 | 14 | ŁÓDŹ KALISKA - TUPLICE | IZ Ostrów Wlkp. | Leszno | 8,10 | 236.21 | 236.21 | End-to-end repair of rail and road crossing | 39 | 24 | 936 | 50 |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 10; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 29 | traffic on active track at the station | 2025-05-22 | 2025-06-29
168 | 6 | 14 | ŁÓDŹ KALISKA - TUPLICE | IZ Wrocław | Głogów - Kłobuczyn | 1 | 283.601 | 294.501 | Viaduct renovation | 75 | 24 | 1800 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 16; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28 | traffic interruption | 2024-12-15 | 2025-02-28
169 | 5 | 18 | KUTNO - PIŁA GŁÓWNA | IZ Bydgoszcz | Toruń Główny - Cierpice (+1) | 1 | 118.8 | 118.900 | installation of switch No. 2 | 12 | 24 | 288 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 12 | Track No. 2, operational platform edges on tracks No. 2 and 4, crossing possible | 2025-05-05 | 2025-05-16
170 | 5 | 18 | KUTNO - PIŁA GŁÓWNA | IZ Bydgoszcz | Toruń Główny TrB - Cierpice (+2,4,6) | 2 | 118.8 | 118.900 | installation of switch No. 1 | 12 | 24 | 288 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 12 | Track No. 1, active 1 platform edge at track No. 1, no crossing possible | 2025-05-19 | 2025-05-30
171 | 5 | 18 | KUTNO - PIŁA GŁÓWNA | IZ Bydgoszcz | Cierpice | 4,6 | 119.203 | 120.093 | track No. 6 upgrade removal of switch No. 8 and 108 (track location installation) | 31 | 24 | 744 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30 | Tracks No. 1, 2, | 2025-06-01 | 2025-06-30
172 |  | 19 | WARSZAWA GŁÓWNA TOWAROWA - JÓZEFINÓW | IZ Warszawa | p.o. Warszawa Gołąbki WGT - Józefinów | 1 |  |  | upgrade of walkway at km 10.672 l.3 | 28 | 6 | 168 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28 | single-track two-way traffic on the active track | 2025-02-01 | 2025-02-28
173 |  | 19 | WARSZAWA GŁÓWNA TOWAROWA - JÓZEFINÓW | IZ Warszawa | p.o. Warszawa Gołąbki WGT - Józefinów | 2 |  |  | upgrade of walkway at km 10.672 l.3 | 28 | 6 | 168 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28 | single-track two-way traffic on the active track | 2025-02-01 | 2025-02-28
174 |  | 19 | WARSZAWA GŁÓWNA TOWAROWA - JÓZEFINÓW | IZ Warszawa | p.o. Warszawa Gołąbki WGT - Józefinów | 1 |  |  | upgrade of walkway at km 10.672 l.3 alternating closure | 91 | 8 | 728 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 30 | single-track two-way traffic on the active track | 2025-03-01 | 2025-05-30
175 |  | 19 | WARSZAWA GŁÓWNA TOWAROWA - JÓZEFINÓW | IZ Warszawa | p.o. Warszawa Gołąbki WGT - Józefinów | 2 |  |  | upgrade of walkway at km 10.672 l.3 alternating closure | 91 | 8 | 728 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 30 | single-track two-way traffic on the active track | 2025-03-01 | 2025-05-30
176 |  | 19 | WARSZAWA GŁÓWNA TOWAROWA - JÓZEFINÓW | IZ Warszawa | p.o. Warszawa Gołąbki WGT - Józefinów | 1 |  |  | upgrade of walkway at km 10.672 l.3 alternating closure | 15 | 6 | 90 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 15 | single-track two-way traffic on the active track | 2025-08-01 | 2025-08-30
177 |  | 19 | WARSZAWA GŁÓWNA TOWAROWA - JÓZEFINÓW | IZ Warszawa | p.o. Warszawa Gołąbki WGT - Józefinów | 2 |  |  | upgrade of walkway at km 10.672 l.3 alternating closure | 15 | 6 | 90 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 15 | single-track two-way traffic on the active track | 2025-08-01 | 2025-08-30
178 | 2 | 25 | ŁÓDŹ KALISKA - DĘBICA | IRR3/1 | Sandomierz - Sobów | 1 | 242.327 | 248.502 | end-to-end upgrade | 7 | 24 | 168 | - | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 7 | traffic interruption – single-track line | 2024-06-09 | 2024-12-21
179 | 2 | 25 | ŁÓDŹ KALISKA - DĘBICA | IRR3/1 | st. Chmielów | 3-15 | 260 | 261 | Track surface replacement, reconstruction of platforms at passenger stations, reconstruction of engineering structures, non-contact line electrical and telecommunications works and associated works | 8 | 24 | 192 | - | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 8 | traffic on active track at the station | 2025-12-05 | 2026-03-05
180 | 2 | 25 | ŁÓDŹ KALISKA - DĘBICA | IRR3/1 | Chmielów - Padew | 1 | 260 | 275.3 | Track surface replacement, reconstruction of platforms at passenger stations, reconstruction of engineering structures, non-contact line electrical and telecommunications works and associated works | 181 | 24 | 4344 | - | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 24; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 4 | traffic interruption – single-track line | 2025-06-07 | 2025-12-04
181 | 2 | 26 | ŁUKÓW - RADOM GŁÓWNY | IRR1/2 | st. Radom Wschodni | 101 | 115.8 | 116.59 | Contact line reconstruction, construction of road viaduct over railway tracks | 14 | 6 | 84 | 30 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 14 | traffic on active track at the station | 2023-07-06 | 2024-12-28 | 4.022
182 | 2 | 26 | ŁUKÓW - RADOM GŁÓWNY | IRR1/2 | st. Radom Wschodni | 102 | 115.8 | 116.59 | Contact line reconstruction, construction of road viaduct over railway tracks | 14 | 6 | 84 | 30 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 14 | traffic on active track at the station | 2023-07-06 | 2024-12-28 | 4.022
183 | 2 | 30 | ŁUKÓW - LUBLIN PÓŁNOCNY | IZ Lublin | Radzyń Podlaski - Bezwola | 1 | 23.771 | 34.512 | Horizontal and vertical mechanical adjustment of track position | 7 | 8 | 56 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 7 | traffic interruption – single-track line | 2024-03-15 | 2024-03-21
184 | 2 | 30 | ŁUKÓW - LUBLIN PÓŁNOCNY | IZ Lublin | Bezwola - Parczew | 1 | 35.52 | 52.34 | Horizontal and vertical mechanical adjustment of track position | 13 | 8 | 104 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 10; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 3 | traffic interruption – single-track line | 2024-03-22 | 2024-04-03
185 | 2 | 30 | ŁUKÓW - LUBLIN PÓŁNOCNY | IZ Lublin | Parczew - Brzeżnica Bychawska | 1 | 53.76 | 67.496 | Horizontal and vertical mechanical adjustment of track position | 9 | 8 | 72 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 9 | traffic interruption – single-track line | 2024-04-04 | 2024-04-12
186 |  | 30 | ŁUKÓW - LUBLIN PÓŁNOCNY | IZ Lublin | Brzeżnica Bychawska - Lubartów | 1 | 68.397 | 82.427 | Horizontal and vertical mechanical adjustment of track position | 9 | 8 | 72 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 9 | traffic interruption – single-track line | 2024-04-15 | 2024-04-23
187 | 2 | 30 | ŁUKÓW - LUBLIN PÓŁNOCNY | IZ Lublin | Lubartów - Bystrzyca koło Lublina | 1 | 83.873 | 93.46 | Horizontal and vertical mechanical adjustment of track position | 7 | 8 | 56 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 7 | traffic interruption – single-track line | 2024-04-24 | 2024-04-30
188 | 2 | 30 | ŁUKÓW - LUBLIN PÓŁNOCNY | IZ Lublin | Bystrzyca koło Lublina - Zadębie | 1 | 95.188 | 106.235 | Horizontal and vertical mechanical adjustment of track position | 8 | 8 | 64 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 8 | traffic interruption – single-track line | 2024-05-01 | 2024-05-08
189 | 2 | 30 | ŁUKÓW - LUBLIN PÓŁNOCNY | IZ Lublin | Zadębie - Lublin Północny | 1 | 106.277 | 107.723 | Horizontal and vertical mechanical adjustment of track position | 1 | 8 | 8 | traffic interruption | no limit | [13 empty] | traffic interruption – single-track line | 2024-05-09 | 2024-05-09 | bar: Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V
190 | 5 | 33 | KUTNO - BRODNICA | IZ Bydgoszcz | Sierpc - Brodnica Rypin | 1 | 117.6 | 118 | track No. 1 upgrade, | 76 | 24 | 1824 | 0 km/h | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 15 | Suspension of train traffic Possibility of LPO Szczutowo, LPO Kretki service; LPO Rypin with service from Sierpc | 2025-09-01 | 2025-11-15
191 | 5 | 33 | KUTNO - BRODNICA | IZ Bydgoszcz | Sierpc - Brodnica Rypin | 1 1, 2 | 116.435 | tor 1 do km 117,500; nr 2 do km 116,600 | upgrade of tracks No. 1, 2, 12, 14, switches No. 1, 2, 4, 11, 12, 13, 14, 103 demolition of platform 2 and construction of a new one | 52 | 24 | 1248 | 0 km/h | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 15; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 6 | Suspension of train traffic Possibility of LPO Szczutowo, LPO Kretki service; LPO Rypin - excluded from service | 2025-04-16 | 2025-06-05
192 | 5 | 33 | KUTNO - BRODNICA | IZ Bydgoszcz | Rypin | 3,5,7 | 116.47 | 117.596 | upgrade of tracks No. 3 and 5, replacement of switches No. 3 and 10 | 40 | 24 | 960 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 10; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 30 | Tracks No. 1, 2, Rypin station | 2025-07-21 | 2025-08-30
193 | 5 | 33 | KUTNO - BRODNICA | IZ Bydgoszcz | Rypin | 4 | 116.88 | 117.38 | construction of track No. 4 | 30 | 24 | 720 | 0 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | Other tracks operational in station | 2025-04-01 | 2025-04-30
194 | 5 | 33 | KUTNO - BRODNICA | IZ Bydgoszcz | Rypin | 6 | 116.88 | 117.02 | track No. 6 upgrade, switches No. 101, 103 | 60 | 24 | 1440 | 0 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 30 | LPO Rypin excluded from service | 2025-06-01 | 2025-07-30
195 | 5 | 33 | KUTNO - BRODNICA | IZ Bydgoszcz | Rypin | 14 | 117.633 | 118 | track No. 14 upgrade | 60 | 24 | 1440 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 30 | LPO Rypin excluded from service | 2025-06-01 | 2025-07-30
196 | 5 | 33 | KUTNO - BRODNICA | IZ Bydgoszcz | Sierpc - Brodnica | 1 | 128.424 | 129.217 | replacement of switch No.8 installation of switch No. 3 | 10 | 24 | 240 | 0 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 10 | suspension of traffic LPO Kretki excluded from service | 2025-05-12 | 2025-05-21
197 | 5 | 33 | KUTNO - BRODNICA | IZ Bydgoszcz | Kretki | 3 | 128.424 | 129.217 | track No. 3 upgrade | 25 | 24 | 600 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 25 | No restrictions | 2025-08-04 | 2025-08-28
198 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Białystok - Białystok Starosielce | 1 | 3.591 | 4.555 | upgrade works | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-03 | 2027-12-30
199 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Białystok Starosielce - Knyszyn | 1 | 4.555 | 28.437 | upgrade works | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-03 | 2027-12-30
200 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Knyszyn - Mońki | 1 | 28.437 | 43.872 | upgrade works | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-03 | 2027-12-30
201 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Mońki - Osowiec | 1 | 43.872 | 57.232 | upgrade works | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-03 | 2027-12-30
202 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Osowiec - Grajewo | 1 | 57.232 | 82.477 | upgrade works | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-03 | 2027-12-30
203 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Grajewo - Ełk | 1 | 82.477 | 103.236 | upgrade works | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-03 | 2027-12-30
204 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Giżycko - Sterławki Wielkie | 1 | 152.85 | 164.615 | Track works, engineering structure works, contact line, RTC, telecommunications | 364 | 24 | 8736 | not applicable | 160 | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption – single-track line | 2023-04-05 | 2026-03-04 | 1.203
205 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | st. Sterławki Wielkie | 1, 2, 3, 5 | 164.615 | 166.65 | Track works, engineering structure works, contact line, RTC, telecommunications | 364 | 24 | 8736 | not applicable | 160 | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2023-11-12 | 2026-03-04 | 1.203
206 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Sterławki Wielkie - Kętrzyn | 1 | 166.65 | 178.7 | Track works, engineering structure works, contact line, RTC, telecommunications | 364 | 24 | 8736 | not applicable | 160 | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption – single-track line | 2023-11-12 | 2026-03-04 | 1.203
207 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | st. Kętrzyn | 1, 2, 6, 8, 18, 31, 3, 5, 7, 10, 11, 12, 13, 14, 15, 16, 20, 24, 24a, 25, 26, 29, 33 | 178.7 | 181 | Track works, engineering structure works, contact line, RTC, telecommunications | 364 | 24 | 8736 | not applicable | 160 | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2023-11-12 | 2026-03-04 | 1.203
208 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Kętrzyn - Tołkiny | 1 | 181 | 191.95 | Track works, engineering structure works, contact line, RTC, telecommunications | 364 | 24 | 8736 | not applicable | 160 | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption – single-track line | 2023-11-12 | 2026-03-04 | 1.203
209 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | st. Tołkiny | 1, 3, 4 | 191.95 | 193.8 | Track works, engineering structure works, contact line, RTC, telecommunications | 364 | 24 | 8736 | not applicable | 160 | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2023-11-12 | 2026-03-04 | 1.203
210 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Tołkiny - Korsze | 1 | 193.8 | 200.1 | Track works, engineering structure works, contact line, RTC, telecommunications | 364 | 24 | 8736 | not applicable | 160 | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption – single-track line | 2023-11-12 | 2026-03-04 | 1.203
211 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | st. Korsze | 1 | 200.1 | 202.826 | Track works, engineering structure works, contact line, RTC, telecommunications | 364 | 24 | 8736 | not applicable | 160 | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic on active track at the station | 2023-11-12 | 2026-03-04 | 1.203
212 | 1 | 45 | WARSZAWA WSCHODNIA OSOBOWA - WARSZAWA GROCHÓW T1G,2G | IRR1/11 | Warszawa Wschodnia - Warszawa Grochów | 1G, 2G | 0.862 | 1.496 | Upgrade of railway lines and railway stations | 184 | 24 | 4416 | 20 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 18; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-06-13 | 2027-06-13 | 1.093
213 | 1 | 60 | KOBYLANY - TERESPOL (SZ) | IRR1/16 | st. Terespol | 1S | 205.126 | 205.2 | Turnout 665 construction | 8 | 24 | 192 | 50 | 60 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 8 | traffic on active track at the station | 2025-10-08 | 2025-10-15
214 | 1 | 60 | KOBYLANY - TERESPOL (SZ) | IRR1/16 | Kobylany-Terespol | 1S | 205.2 | 208.9 | Track upgrade | 31 | 24 | 744 | 50 | 60 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 16; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 15 | traffic interruption – single-track line | 2025-10-16 | 2025-11-15
215 | 1 | 60 | KOBYLANY - TERESPOL (SZ) | IRR1/16 | st. Terespol | 1,3,3a,3b | 206.5 | 208.894 | Track adjustment | 7 | 24 | 168 | 50 | 60 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 7 | traffic on active track at the station | 2025-10-17 | 2025-10-23
216 | 1 | 60 | KOBYLANY - TERESPOL (SZ) | IRR1/16 | st. Terespol | 154 | 208.1 | 208.5 | Track upgrade | 30 | 24 | 720 | 50 | 60 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 5; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 25 | traffic on active track at the station | 2025-03-27 | 2025-04-25
217 | 1 | 60 | KOBYLANY - TERESPOL (SZ) | IRR1/16 | st. Terespol | 102S | 208.5 | 208.9 | Integration of track 102S into track 154 | 7 | 24 | 168 | 50 | 60 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 7 | traffic on active track at the station | 2025-10-01 | 2025-10-07
218 | 3 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR3/8 | Jaroszowiec Olkuski - Olkusz | 1 | 35.898 | 43.6 | Olkusz station reconstruction | 262 | 24 | 6288 | 40km/h x 1000m | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 2 |  |  |  | single-track two-way traffic on the active track | 2024-12-15 | 2025-09-02
219 | 3 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR3/8 | Jaroszowiec Olkuski - Olkusz | 2 | 35.898 | 43.6 | service interruption | 262 | 4 | 1572 | 0 | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 2 |  |  |  | traffic interruption | 2024-12-15 | 2025-09-02
220 | 3 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR3/8 | Olkusz | 1, 3 | 43.6 | 46.8 | Olkusz station reconstruction | 262 | 24 | 6288 | 40km/h at a lenght 2000m | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 2 |  |  |  | traffic on active track at the station | 2024-12-15 | 2025-09-02
221 | 3 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR3/8 | Olkusz | 2, 4, 6 | 43.6 | 46.8 | service interruption | 262 | 4 | 1572 | 0 | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 2 |  |  |  | traffic interruption | 2024-12-15 | 2025-09-02
222 | 3 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR3/8 | Olkusz - Bukowno | 1 | 46.8 | 51.825 | Olkusz station reconstruction | 262 | 24 | 6288 | no limit | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 2 |  |  |  | single-track two-way traffic on the active track | 2024-12-15 | 2025-09-02
223 | 3 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR3/8 | Olkusz - Bukowno | 2 | 46.8 | 51.825 | service interruption | 262 | 4 | 1572 | 0 | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 2 |  |  |  | traffic interruption | 2024-12-15 | 2025-09-02
224 | 4 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR4/4 | Sosnowiec Południowy - Sosnowiec Główny | 1 | 83.35 | 83.7 | upgrade | 45 | 24 | 1080 | not applicable | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 8; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 6 | traffic interruption | 2025-04-23 | 2025-06-06
225 | 4 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR4/4 | st. Sosnowiec Główny | 4,6,8,10 | 83.7 | 84.95 | upgrade | 98 | 24 | 2352 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 22 | traffic on active track at the station | 2024-10-30 | 2025-04-22
226 | 4 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR4/4 | st. Sosnowiec Główny | 4 | 83.7 | 84.95 | upgrade | 154 | 24 | 3696 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 3 | traffic on active track at the station | 2025-06-07 | 2025-11-03
227 | 4 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR4/4 | st. Sosnowiec Główny | 4 | 83.7 | 84.95 | upgrade | 9 | 24 | 216 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 6; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 3 | traffic on active track at the station | 2025-10-25 | 2025-11-03
228 | 4 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR4/4 | st. Sosnowiec Główny | 6 | 83.7 | 84.95 | technology commissioning activities | 9 | 4 | 36 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 6; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 3 | traffic interruption | 2025-10-25 | 2025-11-03
229 | 4 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR4/4 | st. Sosnowiec Główny | 4 | 83.7 | 84.95 | technology commissioning activities | 40 | 4 | 160 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 27; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-11-04 | 2026-07-11
230 | 2 | 64 | KOZŁÓW - KONIECPOL | IRR3/1 | Sprowa - Kozłów | 1 | 1.2 | 1.6 | Upgrade of the line/reconstruction of the track system and other infrastructure components | 87 | 24 | 2088 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 11 | single-track two-way traffic on the active track | 2024-11-09 | 2025-03-11
231 | 2 | 64 | KOZŁÓW - KONIECPOL | IRR3/1 | Sprowa - Kozłów | 2 | 1.2 | 1.6 | Upgrade of the line/reconstruction of the track system and other infrastructure components | 87 | 4 | 348 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 11 | traffic interruption | 2024-11-09 | 2025-03-11
232 | 2 | 68 | LUBLIN GŁÓWNY - PRZEWORSK | IZ Lublin | Lublin Zemborzyce - Niedrzwica | 1 | 9.287 | 19.519 | Horizontal and vertical mechanical adjustment of track position | 7 | 6 | 42 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 7 | traffic interruption – single-track line | 2024-09-12 | 2024-09-18
233 | 2 | 68 | LUBLIN GŁÓWNY - PRZEWORSK | IZ Lublin | Niedrzwica - Wilkołaz | 1 | 20.984 | 35.092 | Horizontal and vertical mechanical adjustment of track position | 12 | 6 | 72 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 12 | traffic interruption – single-track line | 2024-09-19 | 2024-09-30
234 | 2 | 68 | LUBLIN GŁÓWNY - PRZEWORSK | IZ Lublin | Wilokołaz - Kraśnik | 1 | 36.529 | 43.379 | Horizontal and vertical mechanical adjustment of track position | 4 | 6 | 24 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 4 | traffic interruption – single-track line | 2024-10-01 | 2024-10-04
235 | 2 | 68 | LUBLIN GŁÓWNY - PRZEWORSK | IZ Lublin | Kraśnik - Szastarka | 1 | 44.905 | 54.495 | Horizontal and vertical mechanical adjustment of track position | 5 | 6 | 30 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 5 | traffic interruption – single-track line | 2024-10-07 | 2024-10-11
236 | 2 | 68 | LUBLIN GŁÓWNY - PRZEWORSK | IZ Lublin | Szastarka - Rzeczyca | 1 | 55.876 | 65.744 | Horizontal and vertical mechanical adjustment of track position | 5 | 6 | 30 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 5 | traffic interruption – single-track line | 2024-10-14 | 2024-10-18
237 | 2 | 68 | LUBLIN GŁÓWNY - PRZEWORSK | IZ Lublin | Rzeczyca - Zaklików | 1 | 67.175 | 75.222 | Horizontal and vertical mechanical adjustment of track position | 4 | 6 | 24 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 4 | traffic interruption – single-track line | 2024-10-21 | 2024-10-24
238 | 2 | 70 | WŁOSZCZOWICE - CHMIELÓW | IRR3/1 | Chmielów - Strzegomek | 1 | 0 | 0.9 | Track surface replacement, reconstruction of platforms at passenger stations, reconstruction of engineering structures, non-contact line electrical and telecommunications works and associated works | 9 | 24 | 216 | - | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 9 | traffic interruption – single-track line | 2025-12-05 | 2026-03-05
239 | 2 | 74 | SOBÓW - STALOWA WOLA ROZWADÓW | IRR3/1 | Grębów - Zbydniów - Stalowa Wola Rozwadów Towarowy | 1 | 7.389 | 22.181 | end-to-end upgrade | 31 | 24 | 744 | - | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 26; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 5 | single-track two-way traffic on the active track | 2025-08-06 | 2025-09-05
240 | 2 | 74 | SOBÓW - STALOWA WOLA ROZWADÓW | IRR3/1 | Grębów - Stalowa Wola Rozwadów Towarowy | 2 | 7.389 | 22.181 | service interruption | 31 | 4 | 124 | - | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 26; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 5 | traffic interruption | 2025-08-06 | 2025-09-05
241 | 2 | 74 | SOBÓW - STALOWA WOLA ROZWADÓW | IRR3/1 | st. Grębów | 2 | 14 | 15.5 | end-to-end upgrade | 99 | 24 | 2376 | - | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 25; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-09-06 | 2026-03-05
242 | 2 | 74 | SOBÓW - STALOWA WOLA ROZWADÓW | IRR3/1 | st. Grębów | 1 | 14 | 15.5 | service interruption | 99 | 4 | 396 | - | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 25; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-09-06 | 2026-03-05
243 | 2 | 74 | SOBÓW - STALOWA WOLA ROZWADÓW | IRR3/1 | Zbydniów - Stalowa Wola Rozwadów Towarowy | 1 | 14 | 21.9 | Track surface replacement, reconstruction of platforms at passenger stations, reconstruction of engineering structures, non-contact line electrical and telecommunications works and associated works | 99 | 24 | 2376 | - | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 25; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-09-06 | 2026-03-05
244 | 2 | 74 | SOBÓW - STALOWA WOLA ROZWADÓW | IRR3/1 | Zbydniów - Stalowa Wola Rozwadów Towarowy | 2 | 14 | 21.9 | Track surface replacement, reconstruction of platforms at passenger stations, reconstruction of engineering structures, non-contact line electrical and telecommunications works and associated works | 99 | 4 | 396 | - | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 25; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-09-06 | 2026-03-05
245 | 2 | 74 | SOBÓW - STALOWA WOLA ROZWADÓW | IRR3/1 | Grębów - Zbydniów | 2 | 14.466 | 7.389 | end-to-end upgrade | 22 | 24 | 528 | - | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 5 | single-track two-way traffic on the active track | 2024-06-09 | 2025-01-05
246 | 2 | 74 | SOBÓW - STALOWA WOLA ROZWADÓW | IRR3/1 | Grębów - Zbydniów | 1 | 14.466 | 7.389 | service interruption | 22 | 4 | 88 | - | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 5 | traffic interruption | 2024-06-09 | 2025-01-05
247 | 2 | 74 | SOBÓW - STALOWA WOLA ROZWADÓW | IRR3/1 | Grębów - Zbydniów | 1 | 14.466 | 7.389 | end-to-end upgrade | 212 | 24 | 5088 | - | no limit |  | 26 | 28 | 31 | 30 | 31 | 30 | 31 | 5 |  |  |  |  | single-track two-way traffic on the active track | 2025-01-06 | 2025-08-05
248 | 2 | 74 | SOBÓW - STALOWA WOLA ROZWADÓW | IRR3/1 | Zbydniów - Grębów | 2 | 14.466 | 7.389 | service interruption | 212 | 4 | 848 | - | no limit |  | 26 | 28 | 31 | 30 | 31 | 30 | 31 | 5 |  |  |  |  | traffic interruption | 2025-01-06 | 2025-08-05
249 | 2 | 74 | SOBÓW - STALOWA WOLA ROZWADÓW | IRR3/1 | st. Stalowa Wola Rozwadów Towarowy | 2 | 21.9 | 23 | Track surface replacement, reconstruction of platforms at passenger stations, reconstruction of engineering structures, non-contact line electrical and telecommunications works and associated works | 151 | 24 | 3624 | - | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 23; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 5 | traffic on active track at the station | 2025-04-08 | 2025-09-05
250 | 2 | 74 | SOBÓW - STALOWA WOLA ROZWADÓW | IRR3/1 | st. Stalowa Wola Rozwadów Towarowy | 1 | 21.9 | 23 | Track surface replacement, reconstruction of platforms at passenger stations, reconstruction of engineering structures, non-contact line electrical and telecommunications works and associated works | 151 | 4 | 604 | - | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 23; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 5 | traffic interruption | 2025-04-08 | 2025-09-05
251 | 4 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR4/4 | Zabrzeg - Bronów | 1,2 | 53.1 | 58.5 | upgrade | 128 | 24 | 3072 | 60 | 160 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 21 | traffic interruption travel on lines 150 and 693 | 2024-10-20 | 2025-04-21
252 | 4 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR4/4 | Zabrzeg - Bronów | 2 | 53.1 | 58.5 | upgrade | 236 | 24 | 5664 | 60 | 160 |  |  |  |  | 9 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | single-track two-way traffic on the active track | 2025-04-22 | 2026-02-19
253 | 4 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR4/4 | Bronów - Chybie | 1,2 | 58.5 | 60.2 | upgrade | 128 | 24 | 3072 | 60 | 160 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 21 | traffic interruption travel on line 150 | 2024-10-20 | 2025-04-21
254 | 4 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR4/4 | st. Chybie | 2,4,6, 1 (od rozj. 15 do rozj. 55) | 60.2 | 62 | upgrade | 128 | 24 | 3072 | 60 | 160 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 21 | traffic on active track at the station | 2024-10-20 | 2025-04-21
255 | 4 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR4/4 | st. Chybie | 2,4,6, 1 (od RZ15 do RZ55) | 60.2 | 62 | upgrade | 236 | 24 | 5664 | 60 | 160 |  |  |  |  | 9 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic on active track at the station | 2025-04-22 | 2026-02-19
256 | 4 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR4/4 | Chybie - Pruchna | 2 | 62 | 69 | upgrade | 236 | 24 | 5664 | 60 | 160 |  |  |  |  | 9 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | single-track two-way traffic on the active track | 2025-04-22 | 2026-02-19
257 | 4 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR4/4 | Pruchna Zebrzydowice | 2 | 69 | 76 | upgrade | 236 | 24 | 5664 | 60 | 120 |  |  |  |  | 9 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | single-track two-way traffic on the active track | 2025-04-22 | 2026-02-19
258 | 4 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR4/4 | st. Pruchna | 1,3,4,6 | 69.1 | 70.2 | upgrade | 128 | 24 | 3072 | 60 | 160 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 21 | traffic on active track at the station | 2024-10-20 | 2025-04-21
259 | 4 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR4/4 | st. Zebrzydowice | 1-17, 6-8, 100-109, 301-303, 503 | 76 | 77.8 | upgrade | 128 | 24 | 3072 | 60 | 160 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 21 | traffic on active track at the station | 2024-10-20 | 2025-04-21
260 | 4 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR4/4 | st. Zebrzydowice | 1-25; 6-8; 100-109 | 76 | 77.8 | upgrade | 236 | 24 | 5664 | 60 | 160 |  |  |  |  | 9 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic on active track at the station | 2025-04-22 | 2026-02-19
261 | 4 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR4/4 | Zebrzydowice - granica państwa | 1 | 77.8 | 80.66 | upgrade | 128 | 24 | 3072 | 60 | 160 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 21 | single-track two-way traffic on the active track | 2024-10-20 | 2025-04-21
262 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Tarnów Filia - Kłokowa | 1 | 4 | 5.596 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
263 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | mij. Kłokowa | 1.3 | 5.596 | 6.802 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
264 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Kłokowa - Łowczówek Pleśna | 1 | 6.802 | 9.785 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
265 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | st. Łowczówek Pleśna | 1.3 | 9.785 | 11.28 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
266 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Łowczówek Pleśna - Łowczów | 1 | 11.28 | 15.483 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
267 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | mij. Łowczów | 1.3 | 15.483 | 16.939 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
268 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Łowczów - Tuchów | 1 | 16.939 | 20.25 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
269 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | st. Tuchów | 1,3,5 | 20.25 | 21.703 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
270 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Tuchów - Siedliska | 1 | 21.703 | 25.398 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
271 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | mij. Siedliska | 1.3 | 25.398 | 26.667 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
272 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Siedliska - Gromnik | 1 | 26.667 | 31.319 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
273 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | st. Gromnik | 1,2,3 | 31.319 | 32.694 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
274 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Gromnik - Bogoniowice Ciężkowice | 1 | 32.694 | 35.307 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
275 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | st. Bogoniowice Ciężkowice | 1,2,3 | 35.307 | 36.856 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
276 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Bogoniowice Ciężkowice - Zborowice | 1 | 36.856 | 39.572 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
277 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | mij. Zborowice | 1.2 | 39.572 | 40.971 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
278 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Zborowice - Bobowa | 1 | 40.971 | 46.488 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
279 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | st. Bobowa | 1,2,3 | 46.488 | 48.284 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
280 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Bobowa - Wilczyska | 1 | 48.284 | 53.086 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
281 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | mij. Wilczyska | 1.3 | 53.086 | 54.426 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
282 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Wilczyska - Stróże | 1 | 54.426 | 55.395 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
283 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Kamionka Wielka - Nowy Sącz | 1 | 81.33 | 86.731 | major track repair | 92 | 24 | 2208 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31 | single-track two-way traffic on the active track | 2025-03-01 | 2025-05-31
284 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Kamionka Wielka - Nowy Sącz | 2 | 81.33 | 86.731 | major track repair | 92 | 24 | 2208 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31 | single-track two-way traffic on the active track | 2025-06-01 | 2025-08-31
285 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Nowy Sącz Biegonice - Stary Sącz | 1 | 92.986 | 94.657 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
286 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | st. Stary Sącz | 1,2,4 | 94.657 | 96.353 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
287 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Stary Sącz - Rytro | 1 | 96.353 | 104.069 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
288 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | st. Rytro | 1.2 | 104.069 | 105.636 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
289 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Rytro - Piwniczna | 1 | 105.636 | 112.773 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
290 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | st. Piwniczna | 1,2,3 | 112.773 | 114.331 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
291 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Piwniczna - Wierchomla | 1 | 114.331 | 117.886 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
292 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | mij. Wierchomla | 1.3 | 117.886 | 118.889 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
293 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Wierchomla - Żegiestów | 1 | 118.889 | 125.499 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
294 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | st. Żegiestów | 1,3,5 | 125.499 | 126.737 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
295 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Żegiestów - Andrzejówka | 1 | 126.737 | 130.807 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
296 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | mij. Andrzejówka | 1.3 | 130.807 | 132.401 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
297 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Andrzejówka - Muszyna | 1 | 132.401 | 137.88 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
298 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Muszyna - Leluchów (GP) | 1 | 137.88 | 146.374 | major track repair | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
299 | 3 | 97 | SKAWINA - ŻYWIEC | IRR3/2 | Sucha Beskidzka - Żywiec | 1 | 46.239 | 81.392 | Line upgrade | 364 | 24 | 8736 | 0 | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption – single-track line | 2024-07-01 | 2026-02-27 | 1.208
300 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/8 | Chabówka - Rabka Zaryte | 1 | 0.576 | 5.142 | line upgrade | 83 | 24 | 1992 | not applicable | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 7 | traffic interruption – single-track line | 2023-06-11 | 2025-03-07 | 1.201
301 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/8 | Rabka Zaryte | 1,3 | 5.142 | 5.841 | line upgrade | 83 | 24 | 1992 | not applicable | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 7 | traffic interruption | 2023-06-11 | 2025-03-07 | 1.201
302 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/8 | Rabka Zaryte - Mszana Dolna | 1 | 5.841 | 14.393 | line upgrade | 266 | 24 | 6384 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 6 |  |  |  | traffic interruption – single-track line | 2023-06-11 | 2025-09-06 | 1.201
303 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/8 | Mszana Dolna | 1,3 | 14.393 | 15.091 | line upgrade | 266 | 24 | 6384 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 6 |  |  |  | traffic interruption | 2023-12-10 | 2025-09-06 | 1.201
304 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/8 | Mszana Dolna - Tymbark | 1 | 15.091 | 36.35 | line upgrade | 266 | 24 | 6384 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 6 |  |  |  | traffic interruption – single-track line | 2023-12-10 | 2025-09-06 | 1.201
305 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/8 | Tymbark - Limanowa | 1 | 37.352 | 46.768 | line upgrade | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption – single-track line | 2024-06-10 | 2026-05-29 | 1.201
306 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/8 | Limanowa | 1,2,3,3a,4 | 46.768 | 47.569 | line upgrade | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-06-10 | 2026-05-29 | 1.201
307 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/8 | Limanowa - Marcinkowice | 1 | 47.569 | 66.969 | line upgrade | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption – single-track line | 2023-09-03 | 2026-06-06 | 1.201
308 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/8 | Marcinkowice | 1, 2, 3, 3a, 4 | 66.969 | 67.81 | line upgrade | 195 | 24 | 4680 | not applicable | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 27 | traffic interruption | 2023-09-03 | 2025-06-27 | 1.201
309 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/8 | Marcinkowice - Nowy Sącz | 1 | 67.81 | 76.652 | line upgrade | 195 | 24 | 4680 | not applicable | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 27 | traffic interruption – single-track line | 2023-09-03 | 2025-06-27 | 1.201
310 | 3 | 105 | MUSZYNA - KRYNICA-ZDRÓJ | IZ Nowy Sącz | Muszyna - Powroźnik | 1 | 0.544 | 3.86 | reconstruction of Powroźnik station | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
311 | 3 | 105 | MUSZYNA - KRYNICA-ZDRÓJ | IZ Nowy Sącz | st. Powroźnik | 1,2,3,4,6,8 | 3.86 | 6.012 | reconstruction of Powroźnik station | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
312 | 3 | 105 | MUSZYNA - KRYNICA-ZDRÓJ | IZ Nowy Sącz | Powroźnik - Krynica Zdrój | 1 | 6.012 | 9.656 | reconstruction of Powroźnik station | 103 | 24 | 2472 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11 | traffic interruption – single-track line | 2025-03-01 | 2025-06-11
313 | 3 | 108 | STRÓŻE - KROŚCIENKO | IRR3/8 | st. Jasło | 1,3,5,7,9,11 | 44.95 | 47 | upgrade | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-12 | 2026-06-30
314 | 3 | 108 | STRÓŻE - KROŚCIENKO | IRR3/8 | Jasło - Tarnowiec | 1 | 47 | 52.85 | upgrade | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-12 | 2026-06-30
315 | 3 | 108 | STRÓŻE - KROŚCIENKO | IRR3/8 | st. Tarnowiec | 1,2,3, 2a | 52.85 | 54.75 | upgrade | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-12 | 2026-06-30
316 | 3 | 108 | STRÓŻE - KROŚCIENKO | IRR3/8 | Tarnowiec - Jedlicze | 1 | 54.75 | 59.35 | upgrade | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-12 | 2026-06-30
317 | 3 | 108 | STRÓŻE - KROŚCIENKO | IRR3/8 | st. Jedlicze | 1,2,3,4,5,100,102 | 59.35 | 61.25 | upgrade | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-12 | 2026-06-30
318 | 3 | 108 | STRÓŻE - KROŚCIENKO | IRR3/8 | Jedlicze - Krosno | 1 | 61.25 | 67 | upgrade | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-12 | 2026-06-30
319 | 3 | 108 | STRÓŻE - KROŚCIENKO | IRR3/8 | st. Krosno | 1,2a,2,3a,5,7,7a,9,9a | 67 | 69.7 | upgrade | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-12 | 2026-06-30
320 | 3 | 108 | STRÓŻE - KROŚCIENKO | IRR3/8 | Krosno - Targowiska | 1 | 69.7 | 72.1 | upgrade | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-12 | 2026-06-30
321 | 3 | 108 | STRÓŻE - KROŚCIENKO | IRR3/8 | Krosno - Targowiska | 1 | 72.1 | 74.9 | upgrade | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-12 | 2026-06-30
322 | 3 | 108 | STRÓŻE - KROŚCIENKO | IRR3/8 | st. Targowiska | 1,2,3,4,5,6,100 | 74.9 | 76.8 | upgrade | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-12 | 2026-06-30
323 | 3 | 108 | STRÓŻE - KROŚCIENKO | IRR3/8 | Targowiska - Wróblik Szlachecki | 1 | 76.8 | 80.3 | upgrade | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-12 | 2026-06-30
324 | 3 | 108 | STRÓŻE - KROŚCIENKO | IRR3/8 | st. Wróblik Szlachecki | 1,2,3,5 | 80.3 | 82.8 | upgrade | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-12 | 2026-06-30
325 | 3 | 108 | STRÓŻE - KROŚCIENKO | IRR3/8 | Wróblik Szlachecki - Zarszyn | 1 | 82.8 | 91.5 | upgrade | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-12 | 2026-06-30
326 | 3 | 108 | STRÓŻE - KROŚCIENKO | IRR3/8 | st. Zarszyn | 1,2,3,5 | 91.5 | 93.55 | upgrade | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-12 | 2026-06-30
327 | 3 | 108 | STRÓŻE - KROŚCIENKO | IRR3/8 | st. Nowosielce | 1,3,5a | 96.3 | 99.435 | upgrade | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-12 | 2026-06-30
328 | 3 | 108 | STRÓŻE - KROŚCIENKO | IRR3/8 | Nowosielce - Sanok | 1 | 99.435 | 107 | upgrade | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-12 | 2026-06-30
329 | 3 | 108 | STRÓŻE - KROŚCIENKO | IRR3/8 | st. Sanok | 1,2, 2A,3,5,7,9, 9A, 11, 11A, 11B,11C, 21A, 22,23,401,411 | 107 | 109.05 | upgrade | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-12 | 2026-06-30
330 | 3 | 108 | STRÓŻE - KROŚCIENKO | IRR3/8 | Sanok - Nowy Zagórz | 1 | 109.05 | 112.7 | upgrade | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-12 | 2026-06-30
331 | 3 | 108 | STRÓŻE - KROŚCIENKO | IRR3/8 | st. Nowy Zagórz | 1,2,3,4,5,7,8 | 112.7 | 114.95 | upgrade | 364 | 24 | 8736 | not applicable | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-12 | 2026-06-30
332 | 4 | 128 | RADZIONKÓW - NAKŁO ŚLĄSKIE T4 | IRR4/5 | Radzionków - Nakło Śląskie tor T4 | 1 (4) | 27.405 | 29.279 | Closing the tangent line | 67 | 24 | 1608 | 50 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 24; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption – single-track line | 2024-11-12 | 2026-06-30
333 | 4 | 128 | RADZIONKÓW - NAKŁO ŚLĄSKIE T4 | IRR4/5 | Radzionków - Nakło | 1 (4) | 28.13 | 30.143 | Closing the tangent line | 137 | 24 | 3288 | 50 | 50 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | traffic interruption – single-track line | 2024-11-12 | 2026-06-30 | 1.095
334 | 4 | 130 | TARNOWSKIE GÓRY TGD - KALETY T4 | IRR4/5 | Tarnowskie Góry TGD - Kalety tor T4 | 1 (4) | 37.321 | 47.933 | Closing the tangent line | 67 | 24 | 1608 | 50 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 24; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption – single-track line | 2024-11-12 | 2026-06-30
335 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | st. Chorzów Batory | 8, 10, 12, 14, 14a | 5.9 | 5.9 | surface replacement, construction of engineering structures, replacement of contact line | 137 | 4 | 548 | 40 | 40 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | traffic on active track at the station | 2024-11-12 | 2026-06-30 | 1.095
336 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | st. Chorzów Stary | 7,9,11,13,15,17 | 11.68 | 13.1 | surface replacement, construction of engineering structures, replacement of contact line | 137 | 24 | 3288 | 50 | 50 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | traffic on active track at the station | 2024-11-12 | 2025-04-30 | 1.095
337 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | Chorzów Stary - Bytom | 1 | 13 | 16.75 | surface replacement, construction of engineering structures, replacement of contact line | 137 | 24 | 3288 | 50 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | single-track two-way traffic on the active track | 2024-06-01 | 2025-04-30 | 1.095
338 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | Chorzów Stary - Bytom | 2 | 13.1 | 17 | surface replacement, construction of engineering structures, replacement of contact line | 137 | 4 | 548 | 50 | 50 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | traffic interruption | 2024-06-01 | 2025-04-30 | 1.095
339 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | Bytom | 4a, 8a; 10,10a 12,12a, 14, 16, 18, 20, 22, 24, 26, 28,30,32,34,36,38,40,42 | 16.85 | 18.55 | surface replacement, construction of engineering structures, replacement of contact line | 137 | 24 | 3288 | 40 | 40 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | traffic on active track at the station | 2024-05-01 | 2025-04-30 | 1.095
340 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | Bytom - Bytom Karb | 2 | 18.5 | 19.9 | surface replacement, construction of engineering structures, replacement of contact line | 137 | 24 | 3288 | 50 | 50 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | traffic on active track at the station | 2024-06-01 | 2025-04-30 | 1.095
341 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | Bytom - Bytom Karb | 1 | 18.5 | 20.15 | delivery of materials on active track | 137 | 4 | 548 | 50 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | traffic interruption | 2024-06-01 | 2025-04-30 | 1.095
342 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | st. Bytom Karb | 1 | 19.9 | 21.2 | surface replacement, construction of engineering structures, replacement of contact line | 137 | 4 | 548 | 50 | 50 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | traffic interruption | 2024-06-01 | 2025-04-30 | 1.095
343 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | st. Bytom Karb | 2,4,6 | 20.15 | 21.1 | surface replacement, construction of engineering structures, replacement of contact line | 137 | 24 | 3288 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | traffic on active track at the station | 2024-06-01 | 2025-04-30 | 1.095
344 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | Bytom Północny - Radzionków | 1 | 21.04 | 26.8 | delivery of materials on active track | 137 | 4 | 548 | 50 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | traffic interruption | 2024-06-01 | 2025-04-30 | 1.095
345 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | Bytom Północny - Radzionków | 2 | 21.04 | 26.8 | surface replacement, construction of engineering structures, replacement of contact line | 137 | 24 | 3288 | 50 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | single-track two-way traffic on the active track | 2024-06-01 | 2025-04-30 | 1.095
346 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | Bytom Karb - Bytom Północny | 2 | 21.1 | 26.8 | surface replacement, construction of engineering structures, replacement of contact line | 137 | 24 | 3288 | 50 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | single-track two-way traffic on the active track | 2024-06-01 | 2025-04-30 | 1.095
347 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | Bytom Karb - Bytom Północny | 1 | 21.1 | 26.8 | delivery of materials on active track | 137 | 4 | 548 | 50 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | traffic interruption | 2024-06-01 | 2025-04-30 | 1.095
348 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | st. Radzionków | 2,4,6,8 | 26.8 | 27.95 | transport of materials on the active track | 137 | 24 | 3288 | 40 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | traffic on active track at the station | 2024-06-01 | 2025-04-30 | 1.095
349 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | st. Radzionków | 1 | 26.8 | 27.95 | surface replacement, construction of engineering structures, replacement of contact line | 137 | 4 | 548 | 40 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | traffic interruption | 2024-06-01 | 2025-04-30 | 1.095
350 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | Radzionków - Nakło Śląskie | 2 | 27.95 | 29.5 | surface replacement, construction of engineering structures, replacement of contact line | 137 | 24 | 3288 | 50 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | single-track two-way traffic on the active track | 2024-06-01 | 2025-04-30 | 1.095
351 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | Radzionków - Nakło Śląskie | 1 | 28.13 | 30.143 | surface replacement, construction of engineering structures, replacement of contact line | 137 | 4 | 548 | 50 | 50 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | traffic interruption | 2024-03-11 | 2025-04-30 | 1.095
352 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | st. Nakło Śląskie | 1 | 29.279 | 30.143 | surface replacement, construction of engineering structures, replacement of contact line | 148 | 24 | 3552 | 50 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 11 | traffic on active track at the station | 2024-12-12 | 2025-05-11
353 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | st. Nakło Śląskie | 2 | 29.279 | 30.143 | process transport | 148 | 4 | 592 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 11 | traffic on active track at the station | 2024-12-12 | 2025-05-11
354 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | st. Nakło Śląskie | 2 | 29.279 | 30.143 | surface replacement, construction of engineering structures, replacement of contact line | 151 | 24 | 3624 | 50 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 21; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 8 | traffic on active track at the station | 2025-05-11 | 2025-10-08
355 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | st. Nakło Śląskie | 1 | 29.279 | 30.143 | process transport | 151 | 4 | 604 | 0 km/h | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 21; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 8 | traffic interruption | 2025-05-11 | 2025-10-08
356 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | Nakło Śląskie - Tarnowskie Góry | 1 | 30.143 | 33.098 | surface replacement, construction of engineering structures, replacement of contact line | 67 | 24 | 1608 | 50 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 24; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-10-08 | 2026-02-25
357 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | TGE - Kalety | 1 | 39.558 | 46.93 | surface replacement, construction of engineering structures, replacement of contact line | 148 | 24 | 3552 | 50 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 11 | single-track two-way traffic on the active track | 2024-12-12 | 2025-05-11
358 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | TGE - Kalety | 2 | 39.558 | 46.93 | process transport | 148 | 4 | 592 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 11 | traffic interruption | 2024-12-12 | 2025-05-11
359 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | TGE - Kalety | 2 | 39.558 | 46.93 | surface replacement, construction of engineering structures, replacement of contact line | 151 | 24 | 3624 | 50 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 21; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 8 | single-track two-way traffic on the active track | 2025-05-11 | 2025-10-08
360 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | TGE - Kalety | 1 | 39.558 | 46.93 | process transport | 151 | 4 | 604 | 0 km/h | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 21; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 8 | traffic interruption | 2025-05-11 | 2025-10-08
361 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | st. Kalety | 1 | 46.93 | 47.966 | surface replacement, construction of engineering structures, replacement of contact line | 67 | 24 | 1608 | 50 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 24; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-10-08 | 2026-03-07
362 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | st. Kalety | 2 | 46.93 | 47.966 | process transport | 67 | 4 | 268 | 0 km/h | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 24; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-10-08 | 2026-03-07
363 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | st. Boronów | 1 | 58.721 | 59.678 | surface replacement, construction of engineering structures, replacement of contact line | 148 | 24 | 3552 | 50 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 11 | traffic on active track at the station | 2024-12-12 | 2025-05-11
364 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | st. Boronów | 2 | 58.721 | 59.678 | process transport | 148 | 4 | 592 | 0 km/h | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 11 | traffic interruption | 2024-12-12 | 2025-05-11
365 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | st. Boronów | 2 | 58.721 | 59.678 | surface replacement, construction of engineering structures, replacement of contact line | 151 | 24 | 3624 | 50 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 21; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 8 | traffic on active track at the station | 2025-05-11 | 2025-10-08
366 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | st. Boronów | 1 | 58.721 | 59.678 | process transport | 151 | 4 | 604 | 0 km/h | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 21; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 8 | traffic interruption | 2025-05-11 | 2025-10-08
367 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | Boronów - Kalina | 1 | 59.678 | 66.8 | surface replacement, construction of engineering structures, replacement of contact line | 67 | 24 | 1608 | 50 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 24; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-10-08 | 2026-03-07
368 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | Boronów - Kalina | 2 | 59.678 | 66.8 | process transport | 67 | 4 | 268 | 0 km/h | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 24; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-10-08 | 2026-03-07
369 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Szadek - Otok | 2 | 180.4 | 190.3 | end-to-end surface replacement | 175 | 24 | 4200 | 50 | 20 km/h first train, then no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 9; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-06-22 | 2026-01-09
370 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | st. Poddębice | 2,4 | 201.8 | 203.9 | end-to-end surface replacement | 141 | 24 | 3384 | 40 | 40 km/h up to 30 days, then no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 9; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 9 | traffic on active track at the station | 2025-06-22 | 2025-11-09
371 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | st. Poddębice | 1,3 | 201.8 | 203.9 | end-to-end surface replacement | 34 | 24 | 816 | 40 | 40 km/h up to 30 days, then no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 21; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-11-10 | 2026-04-11
372 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Poddębice - Kłudna | 2 | 203.9 | 211.7 | end-to-end surface replacement | 141 | 24 | 3384 | 50 | 20 km/h first train, then no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 9; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 9 | single-track two-way traffic on the active track | 2025-06-22 | 2025-11-09
373 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Poddębice - Kłudna | 1 | 203.9 | 211.7 | end-to-end surface replacement | 34 | 24 | 816 | 50 | 20 km/h first train, then no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 21; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-11-10 | 2026-04-11
374 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | st. Kraski | 1,3 | 220.2 | 222.3 | end-to-end surface replacement | 141 | 24 | 3384 | 40 | 40 km/h up to 30 days, then no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 9; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 9 | traffic on active track at the station | 2025-06-22 | 2025-11-09
375 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | st. Kraski | 2,4 | 220.2 | 222.3 | end-to-end surface replacement | 34 | 24 | 816 | 40 | 40 km/h up to 30 days, then no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 21; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-11-10 | 2026-04-11
376 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Kraski - Dąbie nad Nerem | 1 | 222.3 | 228.6 | end-to-end surface replacement | 141 | 24 | 3384 | 50 | 20 km/h first train, then no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 9; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 9 | single-track two-way traffic on the active track | 2025-06-22 | 2025-11-09
377 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Kraski - Dąbie nad Nerem | 2 | 222.3 | 228.6 | end-to-end surface replacement | 34 | 24 | 816 | 50 | 20 km/h first train, then no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 21; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-11-10 | 2026-04-11
378 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | st. Nowa Wieś Wielka | 15 | 345.2 | 345.9 | Reconstruction of the track system | 136 | 24 | 3264 | 50 | 50 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 1; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-07-31 | 2025-12-17
379 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Brzoza Bydgoska (+2, 4) - Trzciniec | 2,4 | 353.6 | 362.35 | end-to-end surface replacement, reconstruction in other areas | 105 | 24 | 2520 | 60 | 60 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 1; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-08-31 | 2026-01-12
380 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/7 | Kotomierz - Maksymilianowo | 2 | 380.2 | 388.614 | end-to-end upgrade | 89 | 24 | 2136 | 50 | 120 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 19; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 9 | single-track two-way traffic on the active track | 2025-07-12 | 2025-10-09
381 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/7 | Kotomierz - Maksymilianowo | 1 | 380.414 | 388.849 | installation of Rz301 | 15 | 24 | 360 | 50 | 120 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 15 | single-track two-way traffic on the active track | 2025-04-13 | 2025-04-27
382 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/7 | Maksymilianowo - Kotomierz | 1 | 380.414 | 388.849 | end-to-end upgrade | 65 | 24 | 1560 | 50 | 120 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 22; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-10-10 | 2026-02-06
383 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/7 | Kotomierz - Maksymilianowo | 2 | 380.48 | 388.614 | installation of Rz302 | 15 | 24 | 360 | 50 | 120 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 3; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 12 | single-track two-way traffic on the active track | 2025-03-29 | 2025-04-12
384 | 4 | 132 | BYTOM - WROCŁAW GŁÓWNY | IRR4/5 | st. Gliwice Łabędy | 105 | 1 | 1 | Reconstruction of track systems including contact line and traffic control | 40 | 24 | 960 | 50 |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 27; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-11-04 | 2026-04-02
385 | 4 | 132 | BYTOM - WROCŁAW GŁÓWNY | IRR4/5 | Bytom - Bytom Bobrek | 2 | 18.35 | 18.92 | Closing the tangent line | 107 | 24 | 2568 | 50 | 50 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31 | single-track two-way traffic on the active track | 2024-07-01 | 2025-03-31 | 1.095
386 | 4 | 132 | BYTOM - WROCŁAW GŁÓWNY | IRR4/5 | Bytom - Bytom Bobrek | 1 | 18.35 | 18.92 | delivery of materials on active track | 107 | 4 | 428 | 50 | 50 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31 | traffic interruption | 2024-07-01 | 2025-03-31 | 1.095
387 | 6 | 132 | BYTOM - WROCŁAW GŁÓWNY | IZ Wrocław | Oława – Święta Katarzyna | 1 | 155.12 | 169.301 | platform construction, Oława Zachodnia passenger stop | 30 | 24 | 720 | 50 km/h at a lenght 300m | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 23; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 7 | single-track two-way traffic on the active track | 2025-03-09 | 2025-04-07
388 | 6 | 132 | BYTOM - WROCŁAW GŁÓWNY | IZ Wrocław | st. Wrocław Główny | 10, 11 | 180.747 | 181.047 | repair of an engineering facility and accompanying works | 7 | 12 | 84 | 20 km/h at a lenght 200m | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 7 | traffic on active track at the station | 2025-06-11 | 2025-06-18
389 | 6 | 132 | BYTOM - WROCŁAW GŁÓWNY | IZ Wrocław | st. Wrocław Główny | 11, 12 | 180.747 | 181.047 | repair of an engineering facility and accompanying works | 7 | 12 | 84 | 20 km/h at a lenght 200m | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 7 | traffic on active track at the station | 2025-06-18 | 2025-06-25
390 | 6 | 132 | BYTOM - WROCŁAW GŁÓWNY | IZ Wrocław | st. Wrocław Główny | 12 | 180.747 | 181.047 | repair of an engineering facility and accompanying works | 21 | 24 | 504 | 20 km/h at a lenght 200m | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 6; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 15 | traffic on active track at the station | 2025-06-25 | 2025-07-15
391 | 6 | 132 | BYTOM - WROCŁAW GŁÓWNY | IZ Wrocław | st. Wrocław Główny | 11 | 180.747 | 181.047 | repair of an engineering facility and accompanying works | 21 | 24 | 504 | 20 km/h at a lenght 200m | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 16; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 5 | traffic on active track at the station | 2025-07-15 | 2025-08-05
392 | 6 | 132 | BYTOM - WROCŁAW GŁÓWNY | IZ Wrocław | st. Wrocław Główny | 11, 12 | 180.747 | 181.047 | repair of an engineering facility and accompanying works | 7 | 24 | 168 | 20 km/h at a lenght 200m | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 7 | traffic on active track at the station | 2025-08-05 | 2025-08-12
393 | 6 | 132 | BYTOM - WROCŁAW GŁÓWNY | IZ Wrocław | st. Wrocław Główny | 10 | 180.747 | 181.047 | repair of an engineering facility and accompanying works | 21 | 24 | 504 | 20 km/h at a lenght 200m | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 19; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 2 | traffic on active track at the station | 2025-08-12 | 2025-09-02
394 | 6 | 132 | BYTOM - WROCŁAW GŁÓWNY | IZ Wrocław | st. Wrocław Główny | 10, 11 | 180.747 | 181.047 | repair of an engineering facility and accompanying works | 7 | 24 | 168 | 20 km/h at a lenght 200m | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 7 | traffic on active track at the station | 2025-09-02 | 2025-09-09
395 | 4 | 135 | GLIWICE ŁABĘDY - PYSKOWICE | IRR4/5 | st. Gliwice Łabędy | 31 | -0.283 | 0.06 | Reconstruction of track systems including contact line and traffic control | 92 | 24 | 2208 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 16 | traffic on active track at the station | 2024-10-17 | 2025-03-16
396 | 4 | 135 | GLIWICE ŁABĘDY - PYSKOWICE | IRR4/5 | st. Gliwice Łabędy | 21 | -0.283 | 0.058 | Reconstruction of track systems. Platform edge construction. | 34 | 24 | 816 | 50 |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 16; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 18 | traffic on active track at the station | 2025-03-16 | 2025-04-18
397 | 4 | 135 | GLIWICE ŁABĘDY - PYSKOWICE | IRR4/5 | st. Gliwice Łabędy | 11, 27, 27a ,29 | -0.283 | 0.058 | Reconstruction of track systems. Platform edge construction. | 201 | 24 | 4824 | 50 |  |  |  |  | 4 | 30 | 31 | 30 | 31 | 31 | 30 | 14 |  |  | traffic on active track at the station | 2025-03-28 | 2025-10-14
398 | 4 | 135 | GLIWICE ŁABĘDY - PYSKOWICE | IRR4/5 | st. Gliwice Łabędy | 31 | -0.283 | 0.06 | Reconstruction of track systems including contact line and traffic control | 40 | 24 | 960 | 50 |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 27; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-11-04 | 2026-04-02
399 | 4 | 135 | GLIWICE ŁABĘDY - PYSKOWICE | IRR4/5 | Gliwice Łabędy - Pyskowice | 1 | -0.209 | 5.727 | Reconstruction of track systems. Platform edge construction. | 201 | 24 | 4824 | 50 |  |  |  |  | 4 | 30 | 31 | 30 | 31 | 31 | 30 | 14 |  |  | traffic on active track at the station | 2025-03-28 | 2025-10-14
400 | 4 | 137 | KATOWICE - LEGNICA | IRR4/4 | st. Katowice | UR88 (stary) - UR 166(nowy) | 0.381 | 2.251 | upgrade | 113 | 24 | 2712 | 60 | 120 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 29; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 23 | traffic on active track at the station | 2025-03-03 | 2025-06-23
401 | 4 | 137 | KATOWICE - LEGNICA | IRR4/5 | Szobiszowice - Gliwice Łabędy | 1 | 28.732 | 32.661 | Reconstruction of track systems including contact line and traffic control, demolition and construction of engineering structures. | 40 | 24 | 960 | 50 |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 27; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-11-04 | 2026-04-02
402 | 4 | 137 | KATOWICE - LEGNICA | IRR4/5 | Szobiszowice - Gliwice Łabędy | 2 | 28.817 | 32.856 | Reconstruction of track systems including contact line and traffic control. Platform edge construction. Demolition and construction of engineering structures. | 92 | 24 | 2208 | 50 |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 16 | single-track two-way traffic on the active track | 2024-10-17 | 2025-03-16
403 | 4 | 137 | KATOWICE - LEGNICA | IRR4/5 | Gliwice Łabędy | 3 | 31.606 | 32.879 | Reconstruction of track systems including contact line and traffic control | 40 | 24 | 960 | 50 |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 27; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-11-04 | 2026-04-02
404 | 6 | 137 | KATOWICE - LEGNICA | IZ OPOLE | Prudnik - Nowy Świętów | 2 | 115 | 118.9 | End-to-end surface replacement | 183 | 24 | 4392 | 50 km/h 3900m | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30 | single-track two-way traffic on the active track | 2025-04-01 | 2025-09-30
405 | 6 | 137 | KATOWICE - LEGNICA | IZ OPOLE | Goświnowice - Otmuchów | 1 | 151.5 | 152.7 | End-to-end surface replacement | 92 | 24 | 2208 | 50 km/h 1200m | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31 | single-track two-way traffic on the active track | 2025-08-01 | 2025-11-30
406 | 6 | 137 | KATOWICE - LEGNICA | IZ OPOLE | Ząbkowice Śląskie - Piława Górna | 1 | 189.85 | 190.2 | Surface and sleeper major repairs | 57 | 24 | 1368 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 27; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30 | traffic interruption – single-track line | 2025-05-05 | 2025-06-30
407 | 6 | 137 | KATOWICE - LEGNICA | IZ Opole | Dzierżoniów Śląski - Mościsko Dzierżoniowskie | 1 | 215.1 | 215.3 | bridge reconstruction at km 215.176 | 5 | 24 | 120 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 5 | traffic interruption – single-track line | 2025-07-01 | 2025-07-05
408 | 6 | 137 | KATOWICE - LEGNICA | IZ Opole | Dzierżoniów Śląski - Mościsko Dzierżoniowskie | 1 | 215.1 | 215.3 | bridge reconstruction at km 215.176 | 5 | 24 | 120 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 5 | traffic interruption – single-track line | 2025-10-27 | 2025-10-31
409 | 4 | 138 | OŚWIĘCIM - KATOWICE | IRR4/4 | st. Katowice Zawodzie | 4,6,8,10 | 29.1 | 30.8 | upgrade | 2 | 4 | 8 | 40 | 40 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 2 | traffic interruption | 2024-10-15 | 2024-12-16
410 | 4 | 138 | OŚWIĘCIM - KATOWICE | IRR4/4 | Katowice Zawodzie - Katowice | 1.2 | 30.8 | 31.617 | upgrade | 48 | 24 | 1152 | 40 | 120 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31 | traffic interruption travel on lines 1 and 659 | 2024-09-16 | 2025-01-31
411 | 4 | 138 | OŚWIĘCIM - KATOWICE | IRR4/4 | st. Katowice | 527 | 31.617 | 33.286 | upgrade | 76 | 24 | 1824 | 40 | 120 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28 | traffic on active track at the station | 2024-10-04 | 2025-02-28
412 | 4 | 138 | OŚWIĘCIM - KATOWICE | IRR4/4 | st. Katowice | 505 | 31.617 | 33.286 | upgrade | 107 | 24 | 2568 | 40 | 120 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31 | traffic on active track at the station | 2024-09-16 | 2025-03-31
413 | 4 | 138 | OŚWIĘCIM - KATOWICE | IRR4/4 | st. Katowice | 11,12,14,16,18,20/22,26,28 | 32.2 | 32.45 | upgrade | 183 | 24 | 4392 | 60 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 29; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 1 | traffic on active track at the station | 2025-03-03 | 2025-09-01
414 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | Brynów - Katowice Ligota | 1 | 3.629 | 5.329 | upgrade | 104 | 24 | 2496 | 60 | 120 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-09-01 | 2026-04-02
415 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | st. Katowice Ligota | 2 | 5.329 | 7.739 | upgrade | 257 | 24 | 6168 | 40 | 100 | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 28 |  |  |  |  | traffic on active track at the station | 2024-10-15 | 2025-08-28
416 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | st. Katowice Ligota | 1,3 | 5.329 | 7.739 | upgrade | 258 | 24 | 6192 | 40 | 100 |  |  |  | 1 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic on active track at the station | 2025-03-31 | 2026-03-31
417 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | Tychy - Kobiór | 2 | 19 | 25.578 | upgrade | 212 | 24 | 5088 | 90 | [6 empty] | 16 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | single-track two-way traffic on the active track | 2025-05-16 | 2026-02-16
418 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | Tychy - Kobiór | 1 | 19 | 25.578 | technology commissioning activities | 212 | 6 | 1272 | 90 | [6 empty] | 16 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2025-05-16 | 2026-02-16
419 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | st. Kobiór | 6, 6a, 8, 8a, 16, 18 | 25.578 | 25.989 | upgrade | 364 | 24 | 8736 | not applicable |  | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic on active track at the station | 2023-10-16 | 2026-02-15
420 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | Kobiór - Pszczyna | 1 | 25.9 | 35.7 | upgrade | 152 | 24 | 3648 | 20/50/90 | 90 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 15 | single-track two-way traffic on the active track | 2024-08-10 | 2025-05-15
421 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | Kobiór - Pszczyna | 2 | 25.9 | 35.7 | technology commissioning activities | 152 | 6 | 912 | not applicable |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 15 | traffic interruption | 2024-08-10 | 2025-05-15
422 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | st. Pszczyna | 4a, 6. 8, 8a, 10, 10a, 12, 14, 20, 22, | 35.593 | 36.687 | upgrade | 244 | 24 | 5856 | not applicable |  | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 15 |  |  |  |  | traffic on active track at the station | 2023-10-16 | 2025-08-15
423 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | st. Pszczyna | 1 | 35.593 | 36.687 | technology commissioning activities | 244 | 6 | 1464 | not applicable |  | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 15 |  |  |  |  | traffic interruption | 2023-10-16 | 2025-08-15
424 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | st. Pszczyna | 2,4 | 35.593 | 36.687 | upgrade | 244 | 24 | 5856 | not applicable |  | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 15 |  |  |  |  | traffic on active track at the station | 2024-03-12 | 2025-08-15
425 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | st. Pszczyna | 1 | 35.593 | 36.687 | upgrade | 120 | 24 | 2880 | not applicable |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 16; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-08-15 | 2026-05-15
426 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | st. Pszczyna | 5, 5a, 5b, 7, 7a, 9, 9a, | 35.593 | 36.687 | upgrade | 364 | 24 | 8736 | not applicable |  | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic on active track at the station | 2023-10-16 | 2026-02-15
427 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | st. Pszczyna | 2,4,6 | 35.593 | 36.687 | technology commissioning activities | 316 | 6 | 1896 | not applicable |  |  |  | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2025-02-01 | 2026-02-15
428 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | Pszczyna - Most Wisła | 2 | 36.6 | 40.5 | upgrade | 153 | 24 | 3672 | 20/50/90 |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 16 | single-track two-way traffic on the active track | 2024-08-24 | 2025-05-16
429 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | Pszczyna - Most Wisła | 1 | 36.6 | 40.5 | technology commissioning activities | 153 | 6 | 918 | not applicable |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 16 | traffic interruption | 2024-08-24 | 2025-05-16
430 | 4 | 140 | KATOWICE LIGOTA - NĘDZA | IRR4/4 | Katowice Ligota - Mikołów Jamna | 1 | 0.659 | 1.521 | upgrade | 58 | 24 | 1392 | 60 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 30 | traffic interruption – single-track line | 2025-09-03 | 2025-10-30
431 | 4 | 141 | KATOWICE LIGOTA - GLIWICE | IRR4/4 | st. Katowice Ligota | 4 | -0.57 | 0.757 | upgrade | 257 | 24 | 6168 | 40 | 100 | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 28 |  |  |  |  | traffic on active track at the station | 2024-10-15 | 2025-08-28
432 | 4 | 141 | KATOWICE LIGOTA - GLIWICE | IRR4/4 | st. Katowice Ligota | 6,8 | -0.57 | 0.757 | upgrade | 257 | 24 | 6168 | 40 | 40 | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 28 |  |  |  |  | traffic on active track at the station | 2024-09-16 | 2025-08-28
433 | 4 | 141 | KATOWICE LIGOTA - GLIWICE | IRR4/4 | st. Katowice Ligota | 14,16,18,20,22 | -0.57 | 0.757 | upgrade | 257 | 24 | 6168 | 40 | 60 | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 28 |  |  |  |  | traffic on active track at the station | 2024-04-15 | 2025-08-28
434 | 4 | 141 | KATOWICE LIGOTA - GLIWICE | IRR4/4 | st. Katowice Ligota | 10 | -0.57 | 0.757 | upgrade | 107 | 24 | 2568 | 40 | 40 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31 | traffic on active track at the station | 2024-09-16 | 2025-03-31
435 | 4 | 141 | KATOWICE LIGOTA - GLIWICE | IRR4/4 | st. Katowice Ligota | 12 | -0.57 | 0.757 | upgrade | 107 | 24 | 2568 | 40 | 40 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31 | traffic on active track at the station | 2024-04-15 | 2025-03-31
436 | 4 | 141 | KATOWICE LIGOTA - GLIWICE | IRR4/4 | st. Katowice Ligota | 5 | -0.57 | 0.757 | upgrade | 102 | 24 | 2448 | 40 | 60 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-09-03 | 2026-03-30
437 | 4 | 141 | KATOWICE LIGOTA - GLIWICE | IRR4/4 | Katowice Ligota - Panewnik | 1 | -0.57 | 1.573 | upgrade | 258 | 24 | 6192 | 60 | 60 | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 29 |  |  |  |  | single-track two-way traffic on the active track | 2024-10-15 | 2025-08-29
438 | 4 | 141 | KATOWICE LIGOTA - GLIWICE | IRR4/4 | Katowice Ligota - Panewnik | 1, 2 | -0.57 | 1.573 | upgrade | 106 | 24 | 2544 | 60 | 60 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 2; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-08-30 | 2027-02-28
439 | 4 | 148 | PSZCZYNA - RYBNIK | IRR4/4 | st. Pszczyna | 3 | -0.632 | 0 | technology commissioning activities | 244 | 6 | 1464 | not applicable |  | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 15 |  |  |  |  | traffic interruption | 2023-10-23 | 2025-08-15
440 | 4 | 148 | PSZCZYNA - RYBNIK | IRR4/4 | st. Pszczyna | 3 | -0.632 | 0 | upgrade | 120 | 24 | 2880 | not applicable |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 16; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-08-15 | 2026-05-15
441 | 4 | 148 | PSZCZYNA - RYBNIK | IRR4/4 | Pszczyna - Radostowice | 1 | 0 | 7.621 | upgrade | 364 | 24 | 8736 | not applicable |  | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-08-10 | 2025-02-16
442 | 4 | 148 | PSZCZYNA - RYBNIK | IRR4/4 | Radostowice - Suszec | 1 | 7.621 | 14.77 | upgrade | 226 | 24 | 5424 | not applicable | no limit | [5 empty] | 30 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption – single-track line | 2025-05-02 | 2026-04-30 | 1.219
443 | 4 | 148 | PSZCZYNA - RYBNIK | IRR4/4 | Suszec - Suszec Rudziczka | 1 | 14.77 | 18.096 | upgrade | 226 | 24 | 5424 | not applicable | no limit | [5 empty] | 30 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption – single-track line | 2025-05-02 | 2026-04-30 | 1.219
444 | 4 | 148 | PSZCZYNA - RYBNIK | IRR4/4 | Suszec Rudziczka - Kleszczów | 1 | 18.096 | 20.565 | upgrade | 226 | 24 | 5424 | not applicable | no limit | [5 empty] | 30 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption – single-track line | 2025-05-02 | 2026-04-30 | 1.219
445 | 4 | 148 | PSZCZYNA - RYBNIK | IRR4/4 | Kleszczów - Żory | 1 | 20.565 | 22.631 | upgrade | 226 | 24 | 5424 | not applicable | no limit | [5 empty] | 30 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption – single-track line | 2025-05-02 | 2026-04-30 | 1.219
446 | 4 | 157 | PAWŁOWICE ŚLĄSKIE - SKOCZÓW | IRR4/4 | Chybie - Bieniowiec | 1 | 11.9 | 12.45 | upgrade | 236 | 24 | 5664 | not applicable | 80 |  |  |  |  | 9 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2025-04-22 | 2026-02-19
447 | 4 | 161 | KATOWICE SZOPIENICE PÓŁNOCNE - CHORZÓW STARY | IRR4/5 | Chorzów Stary - Siemianowice | 1 | 11.55 | 11.77 | Closing the tangent line | 137 | 24 | 3288 | 50 | 50 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | single-track two-way traffic on the active track | 2024-10-01 | 2025-04-30 | 1.095
448 | 4 | 161 | KATOWICE SZOPIENICE PÓŁNOCNE - CHORZÓW STARY | IRR4/5 | Chorzów Stary - Siemianowice | 2 | 11.55 | 11.77 | delivery of materials on active track | 137 | 4 | 548 | 50 | 50 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | traffic interruption | 2024-10-01 | 2025-04-30 | 1.095
449 | 4 | 165 | BYTOM BOBREK - BYTOM KARB | IRR4/5 | Bytom Karb - Bytom Bobrek | 2 | 1.185 | 1.285 | Closing the tangent line | 137 | 24 | 3288 | 50 | 50 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | single-track two-way traffic on the active track | 2024-08-31 | 2025-04-30 | 1.095
450 | 4 | 165 | BYTOM BOBREK - BYTOM KARB | IRR4/5 | Bytom Karb - Bytom Bobrek | 1 | 1.185 | 1.285 | delivery of materials on active track | 137 | 4 | 548 | 50 | 50 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | traffic interruption | 2024-08-31 | 2025-04-30 | 1.095
451 | 4 | 168 | GLIWICE - GLIWICE ŁABĘDY | IRR4/5 | Szobiszowice - Gliwice Łabędy | 2 (4) | 1.476 | 4.579 | Reconstruction of track systems including contact line and traffic control, demolition and construction of engineering structures. | 40 | 24 | 960 | 50 |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 27; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-11-04 | 2026-04-02
452 | 4 | 168 | GLIWICE - GLIWICE ŁABĘDY | IRR4/5 | st. Gliwice Łabędy | 7.9 | 4.58 | 5.7 | Reconstruction of track systems including contact line and traffic control | 40 | 24 | 960 | 50 |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 27; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-11-04 | 2026-04-02
453 | 4 | 168 | GLIWICE - GLIWICE ŁABĘDY | IRR4/5 | st. Gliwice Łabędy | 9 | 4.58 | 5.7 | Reconstruction of track systems including contact line and traffic control | 40 | 24 | 960 | 50 |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 27; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-11-04 | 2026-04-02
454 | 4 | 168 | GLIWICE - GLIWICE ŁABĘDY | IRR4/5 | Szobiszowice - Gliwice Łabędy | 1 (3) | 4.674 | 5.333 | Reconstruction of track systems including contact line and traffic control. Platform edge construction. Demolition and construction of engineering structures. | 92 | 24 | 2208 | 50 |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 16 | single-track two-way traffic on the active track | 2024-10-17 | 2025-03-16
455 | 4 | 168 | GLIWICE - GLIWICE ŁABĘDY | IRR4/5 | st. Gliwice Łabędy | 9 | 4.674 | 5.333 | Reconstruction of track systems including contact line and traffic control | 92 | 24 | 2208 | 50 |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 16 | traffic on active track at the station | 2024-10-17 | 2025-03-16
456 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/9 | Bydgoszcz Emilianowo | 1, 3, 5, 7, 9, 11 | 0.7 | 10.25 | end-to-end surface replacement, reconstruction in other areas | 137 | 24 | 3288 | 50 | 50 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | traffic on active track at the station | 2024-06-01 | 2025-04-30
457 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/9 | Bydgoszcz Emilianowo - Nowa Wieś Wielka | 2 | 0.7 | 8.7 | Track adjustment, end-to-end surface replacement, reconstruction in other areas | 136 | 24 | 3264 | 60 | 60 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 1; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-07-31 | 2025-12-27
458 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/9 | Bydgoszcz Emilianowo | 2,4,6 | 0.7 | 10.15 | end-to-end surface replacement, reconstruction in other areas | 136 | 24 | 3264 | 50 | 50 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 1; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-07-31 | 2025-12-27
459 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/9 | Bydgoszcz Emilianowo - Bydgoszcz Wschód | 2 | 10.15 | 20.6 | Replacement of switches, adjustment | 137 | 24 | 3288 | 60 | 60 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | single-track two-way traffic on the active track | 2024-06-01 | 2025-04-30
460 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Maksymilianowo - Bydgoszcz Leśna | 2 | 24.03 | 33.63 | end-to-end upgrade | 137 | 4 | 548 | 50 | 120 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | single-track two-way traffic on the active track | 2024-06-01 | 2025-04-30
461 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Maksymilianowo - Serock (+1,3) - Wierzchucin | 1 | 34.128 | 72.34 | end-to-end upgrade | 269 | 24 | 6456 | 50 | 120 |  |  |  | 12 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2025-03-20 | 2025-12-24
462 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Wierzchucin - Lipowa Tucholska (+1,3,5,7) | 1 | 72.34 | 94.73 | end-to-end upgrade | 177 | 24 | 4248 | not applicable | 120 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-06-20 | 2026-02-14
463 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Łąg Południowy - Bąk (+1,3) | 1 | 105.2 | 117.53 | end-to-end upgrade | 364 | 24 | 8736 | not applicable | 120 | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-11-29 | 2026-03-23
464 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | st. Kościerzyna | 3, 5, 7, 9, 11, 13, 15, 17, 19 | 136.105 | 138.068 | Reconstruction of the track system | 139 | 24 | 3336 | 50 | 50 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 2 | traffic on active track at the station | 2024-12-02 | 2025-05-02
465 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | st. Kościerzyna | 15, 17, 19 | 136.105 | 138.068 | Reconstruction of the track system | 258 | 24 | 6192 | 50 | 60 |  |  |  | 1 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic on active track at the station | 2025-03-31 | 2026-09-29
466 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Kościerzyna - Gołubie Kaszubskie | 1 | 138.068 | 148.344 | End-to-end route reconstruction | 364 | 24 | 8736 | not applicable | 60 | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-01-31 | 2026-11-01
467 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | st. Gołubie Kaszubskie | 1, 2, 4 | 148.344 | 149.701 | Reconstruction of the track system | 364 | 24 | 8736 | not applicable | 60 | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-01-31 | 2026-11-01
468 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Gołubie Kaszubskie - Somonino | 1 | 149.701 | 161.73 | End-to-end route reconstruction | 364 | 24 | 8736 | not applicable | 60 | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-01-31 | 2026-11-01
469 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | st. Somonino | 1 | 161.73 | 162.5 | Reconstruction of the track system | 229 | 24 | 5496 | 50 | 50 | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | [5 empty] | traffic on active track at the station | 2024-01-31 | 2025-07-31
470 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | st. Somonino | 10, 12 | 161.73 | 163.363 | Reconstruction of the track system | 229 | 24 | 5496 | 50 | 50 | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | [5 empty] | traffic on active track at the station | 2024-01-31 | 2025-07-31
471 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | st. Somonino | 1, 2, 3, 10, 12 | 161.73 | 163.363 | Reconstruction of the track system | 135 | 24 | 3240 | 50 | 50 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-08-01 | 2026-05-02
472 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Somonino - Glincz | 1 | 163.333 | 174.476 | line upgrade, construction of the second track | 322 | 24 | 7728 | not applicable | 60 |  | 6 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption – single-track line | 2025-01-26 | 2027-03-16
473 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Glincz - Żukowo Wschodnie | 1 | 174.476 | 178.4 | line upgrade, construction of the second track | 322 | 24 | 7728 | not applicable | 60 |  | 6 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption – single-track line | 2025-01-26 | 2026-02-25
474 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | st. Żukowo Wschodnie | 1,2,6 | 178.4 | 179.706 | line upgrade, construction of the second track | 322 | 24 | 7728 | not applicable | 60 |  | 6 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2025-01-26 | 2026-02-25
475 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Żukowo Wschodnie - Gdańsk Osowa | 1 | 179.706 | 184.518 | line upgrade, construction of the second track | 322 | 24 | 7728 | not applicable | 60 |  | 6 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption – single-track line | 2025-01-26 | 2026-02-25
476 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | st. Gdańsk Osowa | 2a, 2R na linii 248 PKM | 184.59 | 186.44 | station reconstruction, track adjustments in plane and profile | 42 | 24 | 1008 | not applicable | 60 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 25 | traffic on active track at the station | 2024-11-26 | 2025-01-25
477 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | st. Gdańsk Osowa | 2a, tor 3R na linii 253 PKM (km 1,356-1,421) | 184.59 | 186.44 | construction of the new track | 322 | 24 | 7728 | not applicable | 60 |  | 6 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic on active track at the station | 2025-01-26 | 2026-02-25
478 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | st. Gdańsk Osowa | 2b, 2c, 2d, 2e | 186.44 | 188.36 | station reconstruction | 42 | 24 | 1008 | 50 | 60 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 25 | traffic on active track at the station | 2024-06-27 | 2025-01-25
479 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | st. Gdańsk Osowa | 1a, 1b, 1c, tor 1R na linii 248 PKM (km 17,985-18,050) | 186.44 | 190.054 | construction of the new track | 183 | 24 | 4392 | 50 | 60 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 6; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 27 | traffic on active track at the station | 2025-01-26 | 2025-07-27
480 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | st. Gdańsk Osowa | 2, 2d, 2e, 2f, 4 | 188 | 190.054 | construction of the new track | 243 | 24 | 5832 | 50 | 50 |  | 6 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 25 |  |  |  | traffic on active track at the station | 2025-01-26 | 2025-09-25
481 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | st. Gdańsk Osowa | 1, 1e, 1f | 188.25 | 190.054 | station reconstruction | 60 | 24 | 1440 | 50 | 60 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 5; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 24 | traffic on active track at the station | 2025-09-26 | 2025-11-24
482 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | st. Gdańsk Osowa | 1 | 189.38 | 189.9 | station reconstruction | 15 | 24 | 360 | 50 | 60 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 15 | traffic on active track at the station | 2025-01-11 | 2025-01-25
483 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | st. Gdańsk Osowa | 1f | 189.45 | 189.9 | station reconstruction | 42 | 24 | 1008 | 50 | 60 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 25 | traffic on active track at the station | 2024-06-27 | 2025-01-25
484 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Gdańsk Osowa - Gdynia Wielki Kack | 2 | 190 | 193.3 | construction of new track No. 4, track No. 2 upgrade | 167 | 24 | 4008 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 1; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-06-30 | 2026-05-01
485 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Gdańsk Osowa - Gdynia Wielki Kack | 2 | 190.054 | 193.9 | construction of new track, track No. 2 upgrade | 243 | 24 | 5832 | not applicable | 60 |  | 6 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 25 |  |  |  | single-track two-way traffic on the active track | 2025-01-26 | 2025-09-25
486 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Gdańsk Osowa - Gdynia Wielki Kack | 1 | 190.054 | 193.858 | construction of new track, track No. 1 upgrade | 60 | 24 | 1440 | not applicable | 60 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 5; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 24 | single-track two-way traffic on the active track | 2025-09-26 | 2025-11-24
487 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | st. Gdynia Wielki Kack | 1 | 193.6 | 195.1 | construction of new track No. 3 and switches 1, 4, 27 | 167 | 24 | 4008 | not applicable | 60 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 1; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-06-30 | 2026-05-01
488 | 5 | 202 | GDAŃSK GŁÓWNY - STARGARD | IRR2/1 | Luzino - Strzebielino Morskie | 1 | 55.3 | 59.1 | upgrade of tracks and engineering structures | 147 | 24 | 3528 | not applicable | 50 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 16; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 8 | traffic interruption – single-track line | 2025-06-15 | 2025-11-08
489 | 5 | 202 | GDAŃSK GŁÓWNY - STARGARD | IRR2/1 | Bożepole Wielkie - Godętowo | 1 | 63.7 | 70.4 | upgrade of tracks and engineering structures | 35 | 24 | 840 | not applicable | 50 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 22; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption – single-track line | 2025-11-09 | 2026-03-07
490 | 8 | 202 | GDAŃSK GŁÓWNY - STARGARD | IRR2/1 | Słupsk - Reblino | 1 | 131.173 | 139.582 | upgrade of tracks and engineering structures | 104 | 24 | 2496 | not applicable | 60 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption – single-track line | 2025-09-01 | 2026-05-31
491 | 5 | 203 | TCZEW - KOSTRZYN | IRR2/7 | Swarożyn (+2) - Tczew Suchostrzygi | 2 | 3.8 | 13.65 | end-to-end upgrade | 151 | 24 | 3624 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 15; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 13 | single-track two-way traffic on the active track | 2025-06-16 | 2025-11-13
492 | 5 | 203 | TCZEW - KOSTRZYN | IRR2/7 | Tczew Suchostrzygi - Swarożyn | 1 | 3.8 | 12.4 | end-to-end upgrade | 18 | 24 | 432 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 5; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-11-26 | 2026-04-04
493 | 5 | 203 | TCZEW - KOSTRZYN | IRR2/7 | Tczew Suchostrzygi - Swarożyn | 2 | 3.8 | 12.4 | end-to-end upgrade | 18 | 4 | 72 | not applicable | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 5; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-11-26 | 2026-04-04
494 | 5 | 203 | TCZEW - KOSTRZYN | IRR2/7 | Swarożyn - Starogard Gdański | 2 | 16.9 | 17.6 | axial offsetting of the existing track | 8 | 24 | 192 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 8 | single-track two-way traffic on the active track | 2025-11-19 | 2025-11-26
495 | 5 | 203 | TCZEW - KOSTRZYN | IRR2/7 | Starogard Gdański - Zblewo | 2 | 24.5 | 38.76 | end-to-end upgrade | 25 | 24 | 600 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 12; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-11-19 | 2026-04-04
496 | 5 | 203 | TCZEW - KOSTRZYN | IRR2/7 | Starogard Gdański - Zblewo | 1 | 24.5 | 38.76 | end-to-end upgrade | 25 | 4 | 100 | not applicable | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 12; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-11-19 | 2026-04-04
497 | 5 | 203 | TCZEW - KOSTRZYN | IRR2/7 | Czersk - Czarna Woda | 2 | 55.4 | 66.2 | end-to-end upgrade | 25 | 24 | 600 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 12; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-11-19 | 2026-04-04
498 | 5 | 203 | TCZEW - KOSTRZYN | IRR2/7 | Czarna Woda - Czersk | 1 | 55.4 | 66.2 | end-to-end upgrade | 25 | 4 | 100 | not applicable | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 12; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-11-19 | 2026-04-04
499 | 5 | 209 | KOWALEWO POMORSKIE - BYDGOSZCZ WSCHÓD | IZ Bydgoszcz | Kowalewo Pomorskie (4,6,8,10) - Chełmża | 1 | 50.55 | 50.9 | track No. 1 upgrade, replacement of switch No. 1 | 15 | 24 | 360 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 15 | LK 209 traffic suspended | 2025-04-01 | 2025-04-15
500 | 5 | 209 | KOWALEWO POMORSKIE - BYDGOSZCZ WSCHÓD | IZ Bydgoszcz | Kowalewo Pomorskie | 4,6 | 50.562 | 51.52 | track No. 6 upgrade replacement of switch No. 12 | 30 | 24 | 720 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | Other tracks operational in station, platform edges on tracks No. 1, 2, 3 | 2025-04-01 | 2025-04-30
501 | 5 | 211 | CHOJNICE - KOŚCIERZYNA | IRR2/7 | Lipusz - Kościerzyna | 1 | 51.99 | 68.66 | End-to-end route reconstruction | 182 | 24 | 4368 | not applicable | 40 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 19; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 10 | traffic interruption | 2025-04-12 | 2025-10-10
502 | 7 | 272 | KLUCZBORK - POZNAŃ GŁÓWNY | IZ Ostrów Wlkp. | Ostrów Wielkopolski | 402 | 84.145 | 84.255 | Ongoing sleeper replacement | 14 | 24 | 336 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 14 | traffic on active track at the station | 2025-04-01 | 2025-04-14
503 | 7 | 272 | KLUCZBORK - POZNAŃ GŁÓWNY | IZ Ostrów Wlkp. | Ostrów Wielkopolski | 2 | 85.73 | 86.694 | Ongoing sleeper replacement | 31 | 24 | 744 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 16; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 15 | traffic on active track at the station | 2025-04-15 | 2025-05-15
504 | 7 | 272 | KLUCZBORK - POZNAŃ GŁÓWNY | IRR5/7 | Krzesiny - Poznań Starołęka | 2 | 192.8 | 195.3 | renovation | 154 | 24 | 3696 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 14 | single-track two-way traffic on the active track | 2025-04-14 | 2025-09-14 | 1.117
505 | 7 | 272 | KLUCZBORK - POZNAŃ GŁÓWNY | IRR5/7 | Krzesiny - Poznań Starołęka | 1 | 192.8 | 196.9 | renovation | 90 | 24 | 2160 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 16; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-09-15 | 2026-01-04 | 1.117
506 | 7 | 272 | KLUCZBORK - POZNAŃ GŁÓWNY | IRR5/7 | Poznań Starołęka PSK 2 - Poznań Główny | 2 | 197.26 | 199.8 | renovation | 7 | 24 | 168 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 7 | single-track two-way traffic on the active track | 2025-04-07 | 2025-04-13 | 1.117
507 | 6 | 273 | WROCŁAW GŁÓWNY - SZCZECIN GŁÓWNY | IZ Wrocław | Chełmek Wołowski - Rudna Gwizdanów | 1 | 66.11 | 76.988 | sleeper reinforcement with accompanying works | 60 | 24 | 1440 | 50 km/h at a lenght 1500m | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 2 | single-track two-way traffic on the active track | 2025-08-04 | 2025-10-02
508 | 6 | 273 | WROCŁAW GŁÓWNY - SZCZECIN GŁÓWNY | IZ Wrocław | Chełmek Wołowski - Rudna Gwizdanów | 2 | 66.11 | 76.988 | sleeper reinforcement with accompanying works | 70 | 24 | 1680 | 50 km/h at a lenght 1500m | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 29; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 11 | single-track two-way traffic on the active track | 2025-10-03 | 2025-12-11
509 | 6 | 275 | WROCŁAW MUCHOBÓR - GUBINEK | IZ Wrocław | Szczedrzykowice - Wielkie Piekary | 1 | 52.846 | 60.847 | platform construction, Kunice passenger stop | 20 | 24 | 480 | 50 km/h at a lenght 250m + 20 km/h at a lenght 30m | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 20 | single-track two-way traffic on the active track | 2025-03-09 | 2025-03-28
510 | 6 | 275 | WROCŁAW MUCHOBÓR - GUBINEK | IZ Wrocław | Szczedrzykowice - Wielkie Piekary | 2 | 52.846 | 60.847 | platform construction, Kunice passenger stop | 20 | 24 | 480 | 50 km/h at a lenght 250m + 20 km/h at a lenght 30m | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 3; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 17 | single-track two-way traffic on the active track | 2025-03-29 | 2025-04-17
511 | 6 | 276 | WROCŁAW GŁÓWNY - MIĘDZYLESIE | IZ OPOLE | Bardo Przyłęk - Kłodzko Główne | 2 | 82.9 | 88.95 | Slope securing and tree felling | 32 | 24 | 768 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 1 | single-track two-way traffic on the active track | 2025-07-01 | 2025-08-01
512 | 6 | 280 | OPOLE GROSZOWICE - OPOLE GŁÓWNE | IZ OPOLE | Opole Towarowa | 4W, 6W | 2.925 | 3.718 | Surface and sleeper major repairs | 53 | 24 | 1272 | 50 km/h 793m | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 22 | single-track two-way traffic on the active track | 2025-07-01 | 2025-08-22
513 | 7 | 281 | OLEŚNICA - CHOJNICE | IZ Ostrów Wielkopolski | Koźmin Wielkopolski - Krotoszyn | 1 | 63.959 | 78.352 | Line No. 281 upgrade | 269 | 24 | 6456 | [6 empty] | 24 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | traffic interruption – single-track line | 2025-04-07 | 2026-06-12 | 4.028.01
514 | 7 | 281 | OLEŚNICA - CHOJNICE | IZ Poznań | Września - Czerniejewo | 2 | 136.789 | 142.5 | End-to-end track surface replacement and associated works from km 136.789 to km 142.500 | 61 | 24 | 1464 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30 | single-track two-way traffic on the active track | 2025-08-01 | 2025-09-30
515 | 7 | 281 | OLEŚNICA - CHOJNICE | IZ Poznań | Września - Czerniejewo | 2 | 136.789 | 142.5 | speed limit after completion of works | 14 | 24 | 336 | no limit | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 14 | single-track two-way traffic on the active track | 2025-10-01 | 2025-10-14
516 | 7 | 281 | OLEŚNICA - CHOJNICE | IZ Poznań | Września - Czerniejewo | 2 | 138.9 | 138.91 | End-to-end track surface replacement, category C crossing at km 138.905 | 61 | 24 | 1464 | 20 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30 | single-track two-way traffic on the active track | 2025-08-01 | 2025-09-30
517 | 6 | 288 | NYSA - BRZEG | IZ OPOLE | Nysa - Brzeg | 1 | 20.495 | 22 | End-to-end surface replacement | 92 | 24 | 2208 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31 | traffic interruption – single-track line | 2025-06-01 | 2025-08-31
518* | 6 | 289 | LEGNICA - RUDNA GWIZDANÓW | IZ Wrocław | Legnica – Lubin | 1 | 0.802 | 21.225 | Replacement of suspension cable including drop wires | 7 | 4 | 28 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 7 | traffic interruption | 2025-01-10 | 2025-01-31
519* | 6 | 289 | LEGNICA - RUDNA GWIZDANÓW | IZ Wrocław | Legnica – Lubin | 1 | 0.802 | 21.225 | Replacement of suspension cable including drop wires | 6 | 24 | 144 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 6 | traffic interruption | 2025-01-10 | 2025-01-31
520* | 6 | 289 | LEGNICA - RUDNA GWIZDANÓW | IZ Wrocław | Legnica – Lubin | 1 | 0.802 | 21.225 | Replacement of suspension cable including drop wires | 8 | 4 | 32 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 8 | traffic interruption | 2025-02-01 | 2025-02-28
521* | 6 | 289 | LEGNICA - RUDNA GWIZDANÓW | IZ Wrocław | Legnica – Lubin | 1 | 0.802 | 21.225 | Replacement of suspension cable including drop wires | 8 | 24 | 192 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 8 | traffic interruption | 2025-02-01 | 2025-02-28
522* | 6 | 289 | LEGNICA - RUDNA GWIZDANÓW | IZ Wrocław | Legnica – Lubin | 1 | 0.802 | 21.225 | Replacement of suspension cable including drop wires | 7 | 4 | 28 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 7 | traffic interruption | 2025-03-01 | 2025-03-31
523* | 6 | 289 | LEGNICA - RUDNA GWIZDANÓW | IZ Wrocław | Legnica – Lubin | 1 | 0.802 | 21.225 | Replacement of suspension cable including drop wires | 8 | 24 | 192 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 8 | traffic interruption | 2025-03-01 | 2025-03-31
524* | 6 | 289 | LEGNICA - RUDNA GWIZDANÓW | IZ Wrocław | Legnica – Lubin | 1 | 0.802 | 21.225 | Replacement of suspension cable including drop wires | 2 | 4 | 8 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 2 | traffic interruption | 2025-04-04 | 2025-04-07
525* | 6 | 289 | LEGNICA - RUDNA GWIZDANÓW | IZ Wrocław | Legnica – Lubin | 1 | 0.802 | 21.225 | Replacement of suspension cable including drop wires | 2 | 24 | 48 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 2 | traffic interruption | 2025-04-04 | 2025-04-07
526 | 6 | 297 | NOWY ŚWIĘTÓW - GŁUCHOŁAZY ZDRÓJ | IZ OPOLE | Głuchołazy | 1 | 5.5 | 6.8 | Surface and sleeper major repairs | 68 | 24 | 1632 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 10 | traffic interruption – single-track line | 2025-08-04 | 2025-10-10
527 | 6 | 304 | BRZEG - MAŁUJOWICE | IZ OPOLE | Brzeg - Małujowice | 1 | 1.335 | 3.33 | End-to-end surface replacement | 92 | 24 | 2208 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31 | traffic interruption – single-track line | 2025-05-01 | 2025-07-31
528 | 6 | 333 | GŁUCHOŁAZY - POKRZYWNA | IZ OPOLE | Głuchołazy - granica państwa | 1 | 7 | 11.225 | End-to-end surface replacement and bridge renovation at km 8.643 | 91 | 24 | 2184 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30 | traffic interruption – single-track line | 2025-09-02 | 2025-11-30
529 | 6 | 343 | GŁUCHOŁAZY - GRANICA PAŃSTWA (MIKULOVICE) | IZ OPOLE | Głuchołazy - granica państwa | 1 | 1.18 | 5.586 | End-to-end surface replacement, renovation of facilities at km 1.568, 3.075 and 3.107, 5.184 | 91 | 24 | 2184 | traffic interruption | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30 | traffic interruption – single-track line | 2025-09-02 | 2025-11-30
530 | 7 | 352 | SWARZĘDZ - POZNAŃ STAROŁĘKA | IRR5/7 | Swarzędz - Poznań Franowo | 1 | 0.75 | 4.1 | renovation | 90 | 24 | 2160 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 16; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-09-15 | 2026-01-04 | 1.117
531 | 7 | 352 | SWARZĘDZ - POZNAŃ STAROŁĘKA | IRR5/7 | Swarzędz - Poznań Franowo | 2 | 0.75 | 4.05 | renovation | 7 | 4 | 28 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 7 | traffic interruption | 2025-09-15 | 2025-09-21 | 1.117
532 | 7 | 352 | SWARZĘDZ - POZNAŃ STAROŁĘKA | IRR5/7 | Poznań Franowo od ukresu rozjazdu nr 58 do ukresu skrzyżowania torów nr K10 | 2 | 4 | 4.1 | renovation | 137 | 24 | 3288 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30 | traffic on active track at the station | 2024-06-01 | 2025-04-30 | 1.117
533 | 7 | 352 | SWARZĘDZ - POZNAŃ STAROŁĘKA | IRR5/7 | Poznań Franowo od ukresu rozjazdu nr 78 do rozjazdu nr 58 | 2 | 4 | 5.35 | renovation | 107 | 24 | 2568 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 24; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 22 | traffic on active track at the station | 2025-04-07 | 2025-06-22 | 1.117
534 | 7 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Poznań | Trzemeszno - Wydartowo | 1 | 47.132 | 59.165 | relocation of the entrance system, switches No. 24, 30 and 33, renovation of the surface, the rail crossing, construction of a crossing under the tracks and renovation of the culvert. | 74 | 24 | 1776 | 50 | 100 km/h for 14 days | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 15; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28 | single-track two-way traffic on the active track | 2024-12-15 | 2025-02-28
535 | 7 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Poznań | Trzemeszno - Wydartowo | 1 | 59.98 | 61.2 | platform reconstruction, Trzemeszno station | 74 | 24 | 1776 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 15; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28 | single-track two-way traffic on the active track | 2024-12-15 | 2025-02-28
536 | 7 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Poznań | Trzemeszno - Wydartowo | 2 | 59.98 | 61.2 | closure to closed track No. 1 | 74 | 4 | 296 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 15; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28 | traffic interruption | 2022-12-15 | 2025-02-28
537 | 7 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Poznań | Trzemeszno | 1, 3 | 59.98 | 61.2 | platform reconstruction, Trzemeszno station | 74 | 24 | 1776 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 15; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28 | traffic on active track at the station | 2022-12-15 | 2025-02-28
538 | 7 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Poznań | Trzemeszno | 2, 4, 6 | 59.98 | 61.2 | closure to closed tracks No. 1, 3 | 74 | 4 | 296 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 15; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28 | traffic interruption | 2024-12-15 | 2025-02-28
539 | 7 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Poznań | Trzemeszno - Wydartowo | 1 | 60.545 | 60.554 | construction of a crossing under the tracks and culvert renovation - cat. A crossing | 74 | 24 | 1776 | 20 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 15; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28 | single-track two-way traffic on the active track | 2024-12-15 | 2025-02-28
540 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Mogilno | 3,5,7,57 | 73.25 | 73.35 | replacement of switch No. 16 | 16 | 24 | 384 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 7; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 10 | Other tracks operational in station, 2 platform edges on tracks No. 2 and 6, crossing option | 2025-06-24 | 2025-07-10
541 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Mogilno | 8 | 73.258 | 73.272 | track No. 8 upgrade replacement of switch No. 13 | 33 | 24 | 792 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 21; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 13 | Other tracks operational in station | 2025-07-11 | 2025-08-13
542 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Mogilno | 4,6,8,10,12 | 73.258 | 73.272 | track No. 8 upgrade replacement of switch No. 55 Cs 54/56; 55/57 | 13 | 24 | 312 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 13 | Other tracks operational in station, 3 platform edges | 2025-08-01 | 2025-08-13
543 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Mogilno | 9-17, 25 | 73.695 | 73.683 | replacement of switch No. 22 | 12 | 24 | 288 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 13 | Lack of capacity to operate the unloading facility | 2025-06-15 | 2025-06-27
544 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Mogilno | 9 | 73.705 | 74.139 | track No. 9 upgrade | 26 | 24 | 624 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 13; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 14 | Lack of capacity to operate the unloading facility | 2025-05-19 | 2025-06-14
545 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Mogilno | 68 | 74.334 | 74.506 | track No. 68 upgrade replacement of switch No. 57 | 20 | 24 | 480 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 21 | No restrictions track by the ramp | 2025-07-11 | 2025-07-31
546 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Mogilno - Kołodziejewo (+2,4) | 2 | 82.6 | 82.7 | installation of switch No. 21 | 12 | 24 | 288 | 100 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 12 | Track No. 1, active 1 platform edge at track No. 1, no crossing possible | 2025-06-02 | 2025-06-13
547 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Mogilno - Kołodziejewo (+1) | 1 | 82.65 | 82.75 | installation of switch No. 11 | 15 | 24 | 360 | 100 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 15 | Track No. 2, operational platform edges on tracks No. 2 and 4, crossing possible | 2025-06-16 | 2025-06-30
548 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Kołodziejewo - Janikowo | 2 | 84.1 | 84.3 | installation of switch No. 22 | 15 | 24 | 360 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 16 | Track No. 1 | 2025-05-05 | 2025-05-20
549 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Kołodziejewo (+1) - Janikowo | 1 | 84.1 | 84.3 | installation of switch No. 12 | 11 | 24 | 264 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 11 | Track No. 2, 2 operational platform edges on tracks No. 2 and 4, crossing possible | 2025-05-21 | 2025-05-31
550 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Janikowo | 4,6 | 89.621 | 90.565 | track No. 4 upgrade | 57 | 24 | 1368 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 18; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 9 | No entry for freight trains coming from Inowrocław on tracks No. 8 to 16. No entry of trains coming from Mogilno, trains using electric contact lines, on tracks No. 8 to 14. Difficulties with Ciech Janikowo Soda siding service | 2025-06-12 | 2025-08-09
551 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Janikowo | 4,6 | 89.665 | 90.565 | track No. 6 upgrade | 48 | 24 | 1152 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 18; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 30 | No entry for freight trains coming from Inowrocław on tracks No. 8 to 16. No entry of trains coming from Mogilno, trains using electric contact lines, on tracks No. 8 to 14. Difficulties with Ciech Janikowo Soda siding service | 2025-06-12 | 2025-07-31
552 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Janikowo | 4-18,28 | 89.752 | 90.505 | upgrade of tracks No. 10, 12, 14 replacement of switches No. 11, 12, 13, 14 | 46 | 24 | 1104 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 15 | No entry for freight trains coming from Inowrocław on tracks No. 8 to 16. No entry of trains coming from Mogilno, trains using electric contact lines, on tracks No. 8 to 14. Difficulties with Ciech Janikowo Soda siding service | 2025-08-01 | 2025-09-15
553 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Janikowo | 5 | 90.012 | 90.836 | upgrade of tracks No. 5 and 5a replacement of switch No. 21 | 41 | 24 | 984 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 26; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 15 | No restrictions track by the unloading area | 2025-05-05 | 2025-06-15
554 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Janikowo | 8-18,28 | 90.642 | 90.687 | replacement of switch No. 41 | 48 | 24 | 1152 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 18; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 30 | No entry for freight trains coming from Inowrocław on tracks No. 8 to 16. No entry of trains coming from Mogilno, trains using electric contact lines, on tracks No. 8 to 14. Difficulties with Ciech Janikowo Soda siding service | 2025-06-12 | 2025-07-30
555 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Papowo Toruńskie (2,4) - Toruń Wschodni | 2 | 144.96 | 145.055 | replacement of switch No. 1 | 10 | 24 | 240 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 10 | Track No. 2 Toruń Wschodni - Papowo Toruńskie + tracks No. 1, 3 Papowo Toruńskie station | 2025-05-22 | 2025-05-31
556 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Papowo Toruńskie | 2, 4 | 145.159 | 146.079 | upgrade of tracks No. 4, 14 replacement of Rz 27 | 10 | 24 | 240 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 10 | Other tracks operational in station, travel on tracks 1, 3, 5, 7, 9, operational platform edge on track No. 1, crossing possible | 2025-05-22 | 2025-05-31
557 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Papowo Toruńskie | 3,5,7,9 | 145.167 | 146.197 | track No. 3 upgrade | 30 | 24 | 720 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 16; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 14 | Other tracks operational in station, platform edges on tracks No. 1 and 2 | 2025-04-15 | 2025-05-14
558 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Papowo Toruńskie | 4 | 146.106 | 146.194 | track No. 4 upgrade | 20 | 24 | 480 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 20 | Other tracks operational in station, operational platform edges on tracks No. 1, 2, crossing option | 2025-06-01 | 2025-06-20
559 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Papowo Toruńskie (1-9) - Turzno (1) | 1 | 149.245 | 149.312 | track No. 3 upgrade, replacement of switches No. 31 and 101 | 7 | 24 | 168 | Track No 2 60 km/h | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 7 | 1 operational platform edge at track No. 2 at Papowo Toruńskie station, crossing possible. Turzno station - operational platform edge on track No. 2, no crossing possible | 2025-05-15 | 2025-05-21
560 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Turzno | 5 | 149.296 | 150.284 | track No. 5 upgrade | 20 | 24 | 480 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 20 | Travel on tracks No. 1, 2, 3, 4, operational platform edges on tracks No. 1 and 2 | 2025-05-01 | 2025-05-20
561 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Kowalewo Pomorskie (6-10) - Wąbrzeźno (+2) | 2 | 161.45 | 161.6 | track No. 6 upgrade installation of switch No. 61 | 15 | 24 | 360 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 15 | Track No. 1 At Kowalewo station - 3 operational platform edges, at Wąbrzeźno station - 1 operational platform edge, crossing possible | 2025-05-05 | 2025-05-19
562 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Kowalewo Pomorskie (+1,3) - Wąbrzeźno | 1 | 161.611 | 161.9 | track No. 1 upgrade, construction of switch No. 60 | 10 | 24 | 240 | 40 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 10 | Track No. 2, operational platform edges on tracks No. 2 and 6, crossing possible | 2025-06-01 | 2025-06-10
563 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Kowalewo Pomorskie | 44 | 161.654 | 161.904 | track No. 44 upgrade | 20 | 24 | 480 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 20 | without affecting train traffic | 2025-06-01 | 2025-06-20
564 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Kowalewo Pomorskie - Wąbrzeźno (+2) | 2 | 174.215 | 174.275 | track No. 2 upgrade, construction of switches No. 1, 4 | 10 | 24 | 240 | Track No 1 60 km/h | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 10 | Track No. 1, operational platform edge at track No. 1, crossing possible | 2025-08-01 | 2025-08-10
565 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Kowalewo Pomorskie (+1,3) - Wąbrzeźno (1,3,5) | 1 | 174.244 | 174.204 | track No. 1 upgrade, construction of switches No. 2, 3 | 20 | 24 | 480 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 20 | Track No. 2, Kowalewo Pomorskie station - 2 operational platform edges on tracks No. 2 and 4, crossing possible. | 2025-06-01 | 2025-06-20
566 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Kowalewo Pomorskie - Wąbrzeźno (+1) - Książki | 1 | 174.351 | 175.104 | track No. 3 upgrade, | 30 | 24 | 720 | 60 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30 | Track No. 2, 2 operational platform edges on tracks No. 2 and 4, crossing possible | 2025-06-01 | 2025-06-30
567 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Kowalewo Pomorskie (+1,3) - Wąbrzeźno (1,3,5) - Książki | 1 | 175.15 | 175.203 | Replacement of switch No. 25 Rkpd | 10 | 24 | 240 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 10 | Track No. 2, Kowalewo Pomorskie station - 2 operational platform edges on tracks No. 2 and 4, crossing possible. | 2025-06-01 | 2025-06-10
568 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Wąbrzeźno (2) - Ksiązki | 2 | 175.26 | 174.31 | track No. 2 upgrade, relocation of switch No. 23 and siding reconstruction ELWAR | 20 | 24 | 480 | Track No 1 60 km/h | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 20 | Track No. 1, operational platform edge at track No. 1, crossing possible | 2025-08-11 | 2025-08-31
569 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Książki - Jabłonowo Pomorskie (6-16) - Ostrowite | 2 | 193.35 | 194.661 | track No. 8 upgrade replacement of switches No. 13, 11 | 29 | 24 | 696 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 9; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 20 | Track No. 1, 4 operational platform edges, crossing possible | 2025-07-23 | 2025-08-20
570 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Książki - Jabłonowo Pomorskie (2-16) - Ostrowite | 2 | 193.35 | 194.661 | track No. 8 upgrade replacement of switch No. 61 Rkpd | 11 | 24 | 264 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 11 | Track No. 1, operational platform edge at track No. 1, no crossing possible | 2025-08-21 | 2025-08-31
571 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Książki - Jabłonowo Pomorskie (+1) | 1 | 193.391 | 149.481 | track No. 1 upgrade installation of switch No. 101 | 20 | 24 | 480 | 40 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 20 | Track No. 2, operational platform edges on tracks No. 2, 4, 6, 8, crossing possible | 2025-05-05 | 2025-05-25
572 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Jabłonowo Pomorskie | 1 | 193.391 | 149.481 | track No. 1 upgrade | 12 | 24 | 288 | 40 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 6; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 6 | No exit from tracks No. 2 and 4 in Ostrowite direction | 2025-05-26 | 2025-06-06
573 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Książki - Jabłonowo Pomorskie (2-16) - Ostrowite | 2 | 193.513 | 194.291 | track No. 2 upgrade installation of switch No. 102 | 15 | 24 | 360 | 40 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 15 | Track No. 1, operational platform edge at track No. 1, no crossing possible | 2025-06-07 | 2025-06-22
574 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Książki - Jabłonowo Pomorskie (2-4, 46,48) -Ostrowite | 2 | 193.513 | 194.291 | tracks No. 2 and 4 upgrade | 15 | 24 | 360 | 40 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 15 | Track No. 1, 3 operational platform edges, crossing possible | 2025-06-07 | 2025-06-22
575 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Książki - Jabłonowo Pomorskie (2-4,46,48) - Ostrowite | 2 | 193.513 | 194.291 | tracks No. 2 and 4 upgrade, replacement of switch No. 12 | 30 | 24 | 720 | 40 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 8; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 22 | Track No. 1, 3 operational platform edges, crossing possible | 2025-06-23 | 2025-07-22
576 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Książki - Jabłonowo Pomorskie (1,2-4,46,48) - Ostrowite | 2 | 193.555 | 194.467 | track No. 4 upgrade replacement of switches No. 46, 47 | 12 | 24 | 288 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 6; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 6 | Track No. 1, 4 operational platform edges, crossing possible | 2025-05-26 | 2025-06-06
577 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Jabłonowo Pomorskie -Ostrowite | 1 | 194.45 | 194.55 | installation of switch No. 69 | 15 | 24 | 360 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 15 | Track No. 2 Electric contact line - travel prohibited on tracks 1, 2, 4, | 2025-04-01 | 2025-04-15
578 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Jabłonowo Pomorskie (+2-16) - Ostrowite | 2 | 194.6 | 194.7 | installation of switch No. 70 | 15 | 24 | 360 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 15 | Track No. 1, active 1 platform edge at track No. 1, no crossing possible | 2025-04-16 | 2025-04-30
579 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IRRK2/10/4 | Samborowo | 2 | 249.653 | 249.653 | replacement of switches | 91 | 24 | 2184 | 20 | 120 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 1; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 29 | traffic on active track at the station | 2025-03-31 | 2025-06-29 | 1.223
580 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IRRK2/10/4 | Ostróda | 1 | 257.25 | 259.53 | construction work at the station | 101 | 24 | 2424 | 50 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 4; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 5 | traffic on active track at the station | 2025-06-27 | 2025-10-05 | 1.205
581 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IRRK2/10/4 | Ostróda | 1 | 257.859 | 259.53 | construction work at the station | 75 | 24 | 1800 | 50 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 27 | traffic on active track at the station | 2024-10-20 | 2025-02-27 | 1.205
582 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IRRK2/10/4 | Ostróda | 3 | 258.825 | 259.17 | construction work at the station | 181 | 24 | 4344 | 50 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 2; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 26 | traffic on active track at the station | 2025-02-27 | 2025-08-26 | 1.205
583 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IRRK2/10/4 | Biesal | 2 | 276.674 | 276.674 | replacement of switches | 91 | 24 | 2184 | 20 | 120 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 1; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 29 | traffic on active track at the station | 2025-03-31 | 2025-06-29 | 1.223
584 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ Bydgoszcz | Toruń Wschodni - Papowo Toruńskie (1,3,5,7,9) | 1 | 144,878 145,167 | 144,942 146,197 | replacement of switches No. 2, 3 track No. 3 upgrade | 14 | 24 | 984 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 14 | Track No. 2, 1 operational platform edge at track No. 2, crossing possible | 2025-04-01 | 2025-04-14
585 | 7 | 354 | POZNAŃ GŁÓWNY POD - PIŁA GŁÓWNA | IRR5/7 | Poznań PoD - Suchy Las | 1 | 0 | 6.1 | closure due to construction of a new connecting line | 35 | 24 | 840 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 19; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 16 | single-track two-way traffic on the active track | 2025-01-13 | 2025-02-16 | 1.117
586 | 7 | 354 | POZNAŃ GŁÓWNY POD - PIŁA GŁÓWNA | IRR5/7 | Poznań PoD - Suchy Las | 2 | 0 | 6.25 | closure due to construction of a new connecting line | 7 | 4 | 28 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 7 | traffic interruption | 2025-01-13 | 2025-01-19 | 1.117
587 | 7 | 354 | POZNAŃ GŁÓWNY POD - PIŁA GŁÓWNA | IRR5/7 | Poznań PoD - Suchy Las | 2 | 0 | 6.25 | closure due to construction of a new connecting line | 21 | 24 | 504 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 12; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 9 | single-track two-way traffic on the active track | 2025-02-17 | 2025-03-09 | 1.117
588 | 7 | 354 | POZNAŃ GŁÓWNY POD - PIŁA GŁÓWNA | IRR5/7 | Poznań PoD - Suchy Las - Złotniki | 1 | 0 | 8.6 | closure due to construction of a new connecting line | 8 | 24 | 192 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 8 | single-track two-way traffic on the active track | 2025-07-20 | 2025-07-27 | 1.117
589 | 7 | 357 | POWODOWO - LUBOŃ K. POZNANIA | IZ Poznań | Gronowo Nowotomyskie - Stęszew | 1 | 92.603 | 88.308 | Replacement of long rails with thermite welding | 21 | 8 | 168 | no limit | 100 km/h for 45 days | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 21 | traffic interruption – single-track line | 2025-07-10 | 2025-07-30
590 | 7 | 358 | ZBĄSZYNEK - GUBIN | IZ Zielona Góra | Czerwieńsk - Krosno Odrzańskie | 1 | 43.834 | 64.64 | end-to-end surface replacement | 300 | 24 | 7200 | no limit | no limit |  | 28 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 30 |  |  | traffic interruption – single-track line | 2025-01-03 | 2025-10-30 | task included in the KPO
591 | 7 | 358 | ZBĄSZYNEK - GUBIN | IZ Zielona Góra | Krosno Odrzańskie | 1, 2,6,8,3a, 2a, 5,7 | 64.64 | 67.045 | end-to-end surface replacement | 300 | 24 | 7200 | no limit | no limit |  | 28 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 30 |  |  | traffic interruption – single-track line | 2025-01-03 | 2025-10-30 | task included in the KPO
592 | 7 | 358 | ZBĄSZYNEK - GUBIN | IZ Zielona Góra | Krosno Odrzańskie - Wałowice | 1 | 67.045 | 86.855 | end-to-end surface replacement | 300 | 24 | 7200 | no limit | no limit |  | 28 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 30 |  |  | traffic interruption – single-track line | 2025-01-03 | 2025-10-30 | task included in the KPO
593 | 7 | 358 | ZBĄSZYNEK - GUBIN | IZ Zielona Góra | Wałowice | 1,2,4,2a, 2b | 86.855 | 88.391 | end-to-end surface replacement | 300 | 24 | 7200 | no limit | no limit |  | 28 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 30 |  |  | traffic interruption – single-track line | 2025-01-03 | 2025-10-30 | task included in the KPO
594 | 7 | 358 | ZBĄSZYNEK - GUBIN | IZ Zielona Góra | Wałowice - Gubin | 1 | 88.391 | 91.904 | end-to-end surface replacement | 300 | 24 | 7200 | no limit | no limit |  | 28 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 30 |  |  | traffic interruption – single-track line | 2025-01-03 | 2025-10-30 | task included in the KPO
595 | 7 | 358 | ZBĄSZYNEK - GUBIN | IZ Zielona Góra | Gubin | 1,2,5,2a, 16,16a | 91.904 | 93.145 | end-to-end surface replacement | 300 | 24 | 7200 | no limit | no limit |  | 28 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 30 |  |  | traffic interruption – single-track line | 2025-01-03 | 2025-10-30 | task included in the KPO
596 | 7 | 358 | ZBĄSZYNEK - GUBIN | IZ Zielona Góra | Gubin - Guben | 1 | 93.145 | 93.471 | end-to-end surface replacement | 300 | 24 | 7200 | no limit | no limit |  | 28 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 30 |  |  | traffic interruption – single-track line | 2025-01-03 | 2025-10-30 | task included in the KPO
597 | 7 | 359 | LESZNO - ZBĄSZYŃ | IZ Zielona Góra | Wolsztyn - Stefanowo | 1 | 46.939 | 62.144 | end-to-end surface replacement | 336 | 24 | 8064 | no limit | no limit |  | 21 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 12 | traffic interruption – single-track line | 2025-01-10 | 2025-12-12 | task included in the KPO
598 | 7 | 359 | LESZNO - ZBĄSZYŃ | IZ Zielona Góra | Stefanowo | 1.2 | 62.144 | 63.413 | end-to-end surface replacement | 336 | 24 | 8064 | no limit | no limit |  | 21 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 12 | traffic interruption – single-track line | 2025-01-10 | 2025-12-12 | task included in the KPO
599 | 7 | 359 | LESZNO - ZBĄSZYŃ | IZ Zielona Góra | Stefanowo - Zbąszyń | 1 | 63.413 | 67.772 | end-to-end surface replacement | 336 | 24 | 8064 | no limit | no limit |  | 21 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 12 | traffic interruption – single-track line | 2025-01-10 | 2025-12-12 | task included in the KPO
600 | 7 | 360 | JAROCIN - KĄKOLEWO | IRR5/13 | Gostyń | 1 | 35.963 | 37.09 | Revitalisation | 104 | 24 | 2496 | not applicable | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-09-01 | 2025-12-31 | 11
601 | 7 | 360 | JAROCIN - KĄKOLEWO | IRR5/13 | Gostyń | 3 | 36.288 | 36.898 | Revitalisation | 104 | 24 | 2496 | not applicable | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-09-01 | 2025-12-31 | 11
602 | 7 | 360 | JAROCIN - KĄKOLEWO | IRR5/13 | Gostyń | 2 | 36.82 | 37.03 | Revitalisation | 104 | 24 | 2496 | not applicable | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-09-01 | 2025-12-31 | 11
603 | 7 | 360 | JAROCIN - KĄKOLEWO | IRR5/13 | Gostyń - Kąkolewo | 1 | 36.85 | 58.396 | Revitalisation | 104 | 24 | 2496 | not applicable | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-09-01 | 2025-12-31 | 11
604 | 7 | 394 | POZNAŃ KRZESINY - KOBYLNICA | IRR5/7 | Poznań Franowo - Stary Młyn | 1 | 4.85 | 10.15 | renovation | 151 | 24 | 3624 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 14; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 14 | single-track two-way traffic on the active track | 2025-04-07 | 2025-09-14 | 1.117
605 | 7 | 394 | POZNAŃ KRZESINY - KOBYLNICA | IRR5/7 | Poznań Franowo - Stary Młyn - Zieliniec | 2 | 8.25 | 10.5 | renovation | 7 | 4 | 28 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 7 | traffic interruption | 2025-04-07 | 2025-04-13 | 1.117
606 | 7 | 394 | POZNAŃ KRZESINY - KOBYLNICA | IRR5/7 | Stary Młyn - Poznań Franowo | 1 | 8.35 | 10.2 | renovation | 90 | 24 | 2160 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 16; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-09-15 | 2026-01-04 | 1.117
607 | 7 | 394 | POZNAŃ KRZESINY - KOBYLNICA | IRR5/7 | podg. Stary Młyn | 1 | 10.15 | 10.65 | renovation | 28 | 24 | 672 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 14; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 14 | traffic on active track at the station | 2025-08-18 | 2025-09-14 | 1.117
608 | 7 | 394 | POZNAŃ KRZESINY - KOBYLNICA | IRR5/7 | Stary Młyn - Zieliniec | 1 | 10.65 | 12.05 | renovation | 161 | 24 | 3864 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 24; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 14 | single-track two-way traffic on the active track | 2025-04-07 | 2025-09-14 | 1.117
609 | 7 | 394 | POZNAŃ KRZESINY - KOBYLNICA | IRR5/7 | Zieliniec - Kobylnica | 1 | 12 | 15.7 | renovation | 36 | 24 | 864 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 4; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 1 | single-track two-way traffic on the active track | 2025-07-28 | 2025-09-01 | 1.117
610 | 7 | 395 | ZIELINIEC - KIEKRZ | IRR5/7 | st. Koziegłowy | 1, 3 | 3.35 | 4 | renovation | 29 | 24 | 696 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 16; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic on active track at the station | 2025-11-15 | 2026-01-17 | 1.117
611 | 7 | 395 | ZIELINIEC - KIEKRZ | IRR5/7 | szlak tymczasowy Koziegłowy - Naramowice | 1 | 4 | 7.4 | renovation | 29 | 24 | 696 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 16; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | single-track two-way traffic on the active track | 2025-11-15 | 2026-01-17 | 1.117
612 | 7 | 395 | ZIELINIEC - KIEKRZ | IRR5/7 | Koziegłowy - Poznań Piątkowo | 1 | 4.42 | 13.41 | installation of a temporary trapezoid track | 7 | 24 | 168 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 7 | single-track two-way traffic on the active track | 2025-03-10 | 2025-03-16 | 1.117
613 | 7 | 395 | ZIELINIEC - KIEKRZ | IRR5/7 | szlak tymczasowy Koziegłowy - Naramowice | 1, 2 | 4.43 | 7.5 | overpass renovation | 4 | 24 | 96 | no limit | 50 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 4 | traffic interruption | 2025-11-22 | 2025-11-25 | 1.117
614 | 7 | 395 | ZIELINIEC - KIEKRZ | IRR5/7 | Koziegłowy - Poznań Piątkowo | 2 | 4.5 | 13.3 | installation of a temporary trapezoid track | 7 | 24 | 168 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 7 | single-track two-way traffic on the active track | 2025-03-17 | 2025-03-23 | 1.117
615 | 7 | 395 | ZIELINIEC - KIEKRZ | IRR5/7 | szlak tymczasowy Naramowice - Poznań Piątkowo | 2 | 7.41 | 13.33 | renovation | 7 | 4 | 28 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 7 | traffic interruption | 2025-03-24 | 2025-03-30 | 1.117
616 | 7 | 395 | ZIELINIEC - KIEKRZ | IRR5/7 | szlak tymczasowy Naramowice - Poznań Piątkowo | 2 | 7.41 | 13.33 | renovation | 111 | 24 | 2664 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 4; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 15 | single-track two-way traffic on the active track | 2025-07-28 | 2025-11-15 | 1.117
617 | 7 | 395 | ZIELINIEC - KIEKRZ | IRR5/7 | szlak tymczasowy Naramowice - Poznań Piątkowo | 2,4,6 | 7.54 | 13.41 | renovation | 126 | 24 | 3024 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 8; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 27 | single-track two-way traffic on the active track | 2025-03-24 | 2025-07-27 | 1.117
618 | 7 | 395 | ZIELINIEC - KIEKRZ | IRR5/7 | szlak tymczasowy Naramowice - Poznań Piątkowo | 1 | 7.54 | 13.41 | renovation | 7 | 4 | 28 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 4; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 3 | traffic interruption | 2025-07-28 | 2025-08-03 | 1.117
619 | 7 | 395 | ZIELINIEC - KIEKRZ | IRR5/7 | st. Poznań Piątkowo | 2,4,6,8,10 | 13.1 | 14.45 | renovation | 29 | 24 | 696 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 12 | traffic on active track at the station | 2024-12-09 | 2025-01-12 | 1.117
620 | 7 | 395 | ZIELINIEC - KIEKRZ | IRR5/7 | st. Poznań Piątkowo | 1, 3, 5 | 13.39 | 14.67 | closure due to construction of a new connecting line | 35 | 24 | 840 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 8; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 27 | traffic on active track at the station | 2025-06-23 | 2025-07-27 | 1.117
621 | 7 | 395 | ZIELINIEC - KIEKRZ | IRR5/7 | Poznań Piątkowo - Kiekrz | 2 | 14.45 | 19.65 | renovation | 29 | 24 | 696 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 12 | single-track two-way traffic on the active track | 2024-12-09 | 2025-01-12 | 1.117
622 | 7 | 395 | ZIELINIEC - KIEKRZ | IRR5/7 | Poznań Piątkowo - Kiekrz | 1 | 14.47 | 19.73 | renovation | 56 | 24 | 1344 | 50 | announcing trains using telephone communication | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 19; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 9 | single-track two-way traffic on the active track | 2025-01-13 | 2025-03-09 | 1.117
623 | 1 | 448 | WARSZAWA ZACHODNIA - WARSZAWA REMBERTÓW | IRR1/11 | Warszawa Zachodnia - Warszawa Wschodnia | 3, 4 | -2.38 | 3.69 | Upgrade of railway lines and railway stations | 104 | 4 | 416 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-09-01 | 2027-06-13 | 1.093
624 | 1 | 448 | WARSZAWA ZACHODNIA - WARSZAWA REMBERTÓW | IRR1/11 | Warszawa Zachodnia - Warszawa Wschodnia | 3, 4 | -2.38 | 3.69 | Upgrade of railway lines and railway stations | 65 | 24 | 1560 |  | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 3; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31 | traffic interruption | 2025-06-28 | 2025-08-31 | 1.093
625 | 1 | 448 | WARSZAWA ZACHODNIA - WARSZAWA REMBERTÓW | IRR1/11 | Warszawa Podskarbińska - Warszawa Rembertów | 3m | 9.4 | 9.6 | viaduct construction | 364 | 4 | 1456 | 50 | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | single-track two-way traffic on the active track | 2024-02-02 | 2026-02-01 | 1.066
626 | 1 | 448 | WARSZAWA ZACHODNIA - WARSZAWA REMBERTÓW | IRR1/11 | Warszawa Rembertów | 3m, 4m | 11.673 | 11.823 | tunnel construction | 180 | 24 | 4320 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 27; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31 | traffic on active track at the station | 2025-03-03 | 2025-08-31 | 1.066
627 | 1 | 507 | WARSZAWA GŁÓWNA TOWAROWA - WARSZAWA GOŁĄBKI | IZ Warszawa | Warszawa Główna Towarowa - Warszawa Gołlabki | 3 |  |  | upgrade of walkway at km 10.672 l.3 | 28 | 6 | 168 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28 | single-track two-way traffic on the active track | 2025-02-01 | 2025-02-28
628 | 1 | 507 | WARSZAWA GŁÓWNA TOWAROWA - WARSZAWA GOŁĄBKI | IZ Warszawa | Warszawa Główna Towarowa - Warszawa Gołlabki | 4 |  |  | upgrade of walkway at km 10.672 l.3 | 28 | 6 | 168 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28 | single-track two-way traffic on the active track | 2025-02-01 | 2025-02-28
629 | 1 | 507 | WARSZAWA GŁÓWNA TOWAROWA - WARSZAWA GOŁĄBKI | IZ Warszawa | Warszawa Główna Towarowa - Warszawa Gołlabki | 3 |  |  | upgrade of walkway at km 10.672 l.3 alternating closure | 91 | 8 | 728 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 30 | single-track two-way traffic on the active track | 2025-03-01 | 2025-05-30
630 | 1 | 507 | WARSZAWA GŁÓWNA TOWAROWA - WARSZAWA GOŁĄBKI | IZ Warszawa | Warszawa Główna Towarowa - Warszawa Gołlabki | 4 |  |  | upgrade of walkway at km 10.672 l.3 alternating closure | 91 | 8 | 728 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 30 | single-track two-way traffic on the active track | 2025-03-01 | 2025-05-30
631 | 1 | 507 | WARSZAWA GŁÓWNA TOWAROWA - WARSZAWA GOŁĄBKI | IZ Warszawa | Warszawa Główna Towarowa - Warszawa Gołlabki | 3 |  |  | upgrade of walkway at km 10.672 l.3 alternating closure | 15 | 6 | 90 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 15 | single-track two-way traffic on the active track | 2025-08-01 | 2025-08-30
632 | 1 | 507 | WARSZAWA GŁÓWNA TOWAROWA - WARSZAWA GOŁĄBKI | IZ Warszawa | Warszawa Główna Towarowa - Warszawa Gołlabki | 4 |  |  | upgrade of walkway at km 10.672 l.3 alternating closure | 15 | 6 | 90 |  |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 15 | single-track two-way traffic on the active track | 2025-08-01 | 2025-08-30
633 | 1 | 546 | WARSZAWA WSCHODNIA TOWAROWA - WARSZAWA REMBERTÓW T6M | IRR1/11 | Warszawa Wschodnia Towarowa - Warszawa Rembertów | 6m | 9.4 | 9.6 | viaduct construction | 364 | 4 | 1456 | 50 | no limit | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption | 2024-02-02 | 2026-02-01 | 1.066
634 | 2 | 565 | CHARZEWICE - STALOWA WOLA ROZWADÓW TOWAROWY | IRR3/1 | Charzewice - Stalowa Wola Rozwadów Towarowy | 1 | 0.001 | 0.167 | Track surface replacement, reconstruction of platforms at passenger stations, reconstruction of engineering structures, non-contact line electrical and telecommunications works and associated works | 151 | 24 | 3624 | - | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 23; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 5 | traffic interruption – single-track line | 2025-04-08 | 2025-09-05
635 | 4 | 656 | KATOWICE - BRYNÓW | IRR4/4 | Katowice - Brynów | 1 | 1.035 | 3.005 | upgrade | 76 | 24 | 1824 | 60 | 100 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28 | traffic interruption – single-track line, train traffic on tracks No. 1 and 2 LK 139 | 2024-04-15 | 2025-02-28
636 | 4 | 659 | BĘDZIN - SOSNOWIEC GŁÓWNY T3 | IRR4/4 | Będzin - Sosnowiec Główny | 1 (3) | 306.15 | 308.5 | technology commissioning activities | 45 | 4 | 180 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 28 | traffic interruption | 2024-10-30 | 2025-04-22
637 | 4 | 659 | BĘDZIN - SOSNOWIEC GŁÓWNY T3 | IRR4/4 | Będzin - Sosnowiec Główny | 1 (3) | 306.15 | 308.5 | upgrade | 274 | 24 | 6576 | 60 | 80 |  |  |  | 17 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | single-track two-way traffic on the active track | 2025-06-07 | 2026-07-11
638 | 4 | 659 | BĘDZIN - SOSNOWIEC GŁÓWNY T3 | IRR4/4 | Sosnowiec Główny - Katowice Zawodzie | 2 (4) | 310.9 | 312.2 | technology commissioning activities | 24 | 4 | 96 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 11; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-02-12 | 2026-07-11
639 | 4 | 660 | SOSNOWIEC POŁUDNIOWY - SOSNOWIEC GŁÓWNY | IRR4/4 | Sosnowiec Główny - Katowice Zawodzie | 1 (6) | 0 | 0 | technology commissioning activities | 110 | 4 | 440 | 60 | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 19 | traffic interruption | 2025-10-25 | 2026-02-11
640 | 4 | 660 | SOSNOWIEC POŁUDNIOWY - SOSNOWIEC GŁÓWNY | IRR4/4 | Sosnowiec Południowy - Sosnowiec Główny | 1 | 0.532 | 1.05 | upgrade | 140 | 24 | 3360 | not applicable | 80 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 1 | traffic interruption | 2025-06-07 | 2025-08-05
641 | 4 | 694 | BRONÓW PODG - BIENIOWIEC | IRR4/4 | Bronów - Bieniowiec | 1 | 0 | 2.6 | upgrade | 128 | 24 | 3072 | not applicable | 120 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 21 | traffic interruption – single-track line | 2024-10-20 | 2025-04-21
642 | 4 | 703 | KUCELINKA - CZĘSTOCHOWA | IZ Częstochowa | Częstochowa Towarowa - Częstochowa | 1 | 4.425 | 5.072 | facilities, railroad surface, network, RTC, power supply | 62 | 24 | 1488 | 50 |  | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31 | traffic interruption | 2025-07-01 | 2025-08-31 | 1.204
643 | 4 | 713 | KATOWICE - CHORZÓW BATORY | IRR4/4 | st. Katowice | 30,32a,19,19a,41,42,61,62,63,200 | 0 | 2.002 | upgrade | 16 | 24 | 384 | 40 | 120 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 16 | traffic on active track at the station | 2024-04-15 | 2024-12-30
644 | 5 | 743 | LIPOWA TUCHOLSKA - SZLACHTA | IRR2/7 | Lipowa Tucholska - Szlachta | 1 | 94.73 | 43.433 | end-to-end upgrade | 177 | 24 | 4248 | not applicable | 120 | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 11; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-06-20 | 2025-12-16
645 | 7 | 801 | POZNAŃ STAROŁĘKA PSK - POZNAŃ GÓRCZYN | IRR5/7 | st. Poznań Starołęka PSK 2 | 2 | 0 | 0.2 | renovation | 7 | 24 | 168 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 7 | traffic on active track at the station | 2025-04-07 | 2025-04-13 | 1.117
646 | 7 | 801 | POZNAŃ STAROŁĘKA PSK - POZNAŃ GÓRCZYN | IRR5/7 | st. Poznań Starołęka PSK 2 | 2 | 0 | 0.2 | renovation | 154 | 24 | 3696 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 14 | traffic on active track at the station | 2025-04-14 | 2025-09-14 | 1.117
647 | 7 | 801 | POZNAŃ STAROŁĘKA PSK - POZNAŃ GÓRCZYN | IRR5/7 | Poznań Starołęka PSK 2 - Poznań Górczyn | 2 | 0.2 | 2.25 | renovation | 105 | 24 | 2520 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 9; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 6 | single-track two-way traffic on the active track | 2024-12-23 | 2025-04-06 | 1.117
648 | 7 | 801 | POZNAŃ STAROŁĘKA PSK - POZNAŃ GÓRCZYN | IRR5/7 | Poznań Starołęka PSK 2 - Poznań Górczyn | 1 | 0.5 | 3.25 | renovation | 9 | 24 | 216 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 9 | single-track two-way traffic on the active track | 2024-09-01 | 2024-12-21 | 1.117
649 | 7 | 801 | POZNAŃ STAROŁĘKA PSK - POZNAŃ GÓRCZYN | IRR5/7 | Poznań Starołęka PSK 2 - Poznań Górczyn | 1 | 0.5 | 3.25 | renovation | 9 | 4 | 36 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 9 | traffic interruption | 2024-12-23 | 2024-12-29 | 1.117
650 | 7 | 802 | POZNAŃ STAROŁĘKA PSK - LUBOŃ K. POZNANIA | IRR5/7 | st. Poznań Starołęka PSK 2 | 2 | 0 | 0.2 | renovation | 154 | 24 | 3696 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 17; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 14 | traffic on active track at the station | 2025-04-14 | 2025-09-14 | 1.117
651 | 7 | 802 | POZNAŃ STAROŁĘKA PSK - LUBOŃ K. POZNANIA | IRR5/7 | Poznań Starołęka PSK 2 - Luboń koło Poznania | 2 | 0.15 | 4.15 | renovation | 9 | 24 | 216 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 9 | single-track two-way traffic on the active track | 2024-09-01 | 2024-12-21 | 1.117
652 | 7 | 802 | POZNAŃ STAROŁĘKA PSK - LUBOŃ K. POZNANIA | IRR5/7 | Poznań Starołęka PSK 2 - Luboń koło Poznania | 2 | 0.15 | 4.15 | renovation | 7 | 4 | 28 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 7 | traffic interruption | 2024-12-23 | 2024-12-29 | 1.117
653 | 7 | 802 | POZNAŃ STAROŁĘKA PSK - LUBOŃ K. POZNANIA | IRR5/7 | Poznań Starołęka PSK 2 - Luboń koło Poznania | 1 | 0.3 | 3.4 | renovation | 105 | 24 | 2520 | 50 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 9; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 28; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 III: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 6 | single-track two-way traffic on the active track | 2024-12-23 | 2025-04-06 | 1.117
654 | 7 | 803 | POZNAŃ PIĄTKOWO - SUCHY LAS | IRR5/7 | Poznań Piątkowo - Suchy Las | 1 | 0 | 0.9 | renovation | 35 | 24 | 840 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 8; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 27 | traffic interruption – single-track line | 2025-06-23 | 2025-07-27 | 1.117
655 | 7 | 805 | SWARZĘDZ - STARY MŁYN | IRR5/7 | Swarzędz - Stary Młyn | 1 | 0 | 1.45 | renovation | 164 | 24 | 3936 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IV: 27; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 V: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 14 | traffic interruption – single-track line | 2025-04-07 | 2025-09-14 | 1.117
656 | 7 | 823 | POZNAŃ FRANOWO PFD - STARY MŁYN | IRR5/7 | Poznań Franowo - Stary Młyn | 1 | 0 | 4.7 | renovation of facility at km 3.956 (Obstacle: Railway line No. 352 km 2.950) | 56 | 24 | 1344 | no limit | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 9; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 I: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 II: 16 | traffic interruption – single-track line | 2024-12-23 | 2025-02-16 | 1.117
657 | 4 | 864 | KATOWICE LIGOTA - KWK WUJEK | IRR4/4 | Katowice Ligota - KWK Wujek | 1 | 0.657 | 2.96 | line removal | 364 | 24 | 8736 | 60 |  | 17 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 13 | traffic interruption – single-track line | 2024-03-12 | 2027-03-30
658 | 1 | 902 | WARSZAWA WSCHODNIA - WARSZAWA WSCHODNIA TOWAROWA T2P | IRR1/11 | Warszawa Wschodnia - Warszawa Podskarbińska | 2P | 4.516 | 6.545 | Upgrade of railway lines and railway stations | 184 | 24 | 4416 | 20 | no limit | Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VI: 18; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 VIII: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 IX: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 X: 31; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XI: 30; Number of planned closing days in the timetable 2024/2025 in individual months from December 2024 to December 2025 XII: 13 | traffic interruption | 2025-06-13 | 2027-06-13 | 1.093
In the absence of a determination of the length of the speed limit on the adjacent track, a section of 2000 m is assumed for the calculation of the upgrade allowance. Speed limits for works lasting more than 4 months are assumed as the basis for the RRJ development.
* Track closures indicated in items: 53 - 87 (line 3), 518 - 525 (line 289) included conditionally and the option of granting them will be considered at the periodic planning stage.