## SHZT II korekta 2022-2023
Annex 5.1 - NETWORK STATEMENT 2022/2023 Network schedule of track closures planned for execution in the 2022/2023 timetable - SECOND CORRECTION
No. | IDDE code | Line No. | Line name | Principal | Identification of the station, route or line section, on wich the works will be performed | Track No. | Km from | Km to | Type of work performed | No. of days of track, route, section closure | No. of hours of closure per day | Total No. of closure hours | Speed limit km/h - on adjacted track | Speed limit km/h - after works finish | Number of planned closing days in the timetable 2022/2023 in individual months | [12 empty] | Description of operating railway traffic | Proposed deadlines from | Proposed deadlines to | KPK projects
[15 empty] | XII | I | II | III | IV | V | VI | VII | VIII | IX | X | XI | XII
1 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/5 | szlak Biała Podlaska - Sokule | 1, 2 | 160.556 | 171.799 | upgrade | 342 | 4 | 1368 | traffic interruption | no limit |  | 30 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2023-01-02 | 2023-12-22 | 1.123
2 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/5 | Stacja Biała Podlaska | 1, 2 | 171.799 | 174.121 | upgrade | 342 | 4 | 1368 | no limit | no limit |  | 30 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2023-01-02 | 2023-12-22 | 1.123
3 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/5 | szlak Biała Podlaska - Chotyłów | 1, 2 | 174.121 | 188.019 | upgrade | 342 | 4 | 1368 | traffic interruption | no limit |  | 30 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2023-01-02 | 2023-12-22 | 1.123
4 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/5 | szlak Małaszewicze Południowe - Terespol | 1, 2 | 200.118 | 207.502 | upgrade | 342 | 4 | 1368 | traffic interruption | no limit |  | 30 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2023-01-02 | 2023-12-22 | 1.123
5 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/5 | Stacja Terespol | 1, 2 | 207.502 | 210.3 | upgrade | 342 | 4 | 1368 | no limit | no limit |  | 30 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2023-01-02 | 2023-12-22 | 1.123
6 | 1 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR1/9 | Ożarów Mazowiecki - Błonie | 1, 2 | 15.67 | 28.289 | Night service interruption | 266 | 4 | 1064 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 2 |  |  |  | traffic interruption | 2020-12-13 | 2023-09-02 | 1.099
7 | 1 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR1/1 | Teresin Niepokalanów | 1 | 41.73 | 41.75 | construction of a railway viaduct | 98 | 24 | 2352 | 40 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 28; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-09-03 | 2024-03-16 | 1.066
8 | 1 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR1/9 | W-wa Włochy - Ożarów Maz | 1, 2 | 6.804 | 15.67 | Night service interruption | 266 | 4 | 1064 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 2 |  |  |  | traffic interruption | 2020-12-13 | 2023-09-02 | 1.099
9 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | Grodzisk Mazowiecki - Korytów | 1 | 1.605 | 12.295 | replacement of rails, sleepers, spacers, springs, tamping | 15 | 6 | 120 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 11; Number of planned closing days in the timetable 2022/2023 in individual months X: 4 | traffic interruption | 2023-09-20 | 2023-10-04 | 4.010
10 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | Grodzisk Mazowiecki - Korytów | 1 | 1.605 | 12.295 | replacement of rails, sleepers, spacers, springs, tamping | 16 | 24 | 384 | 120 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months X: 16 | single-track two-way traffic on the active track | 2023-10-05 | 2023-10-20 | 4.010
11 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | Grodzisk Mazowiecki - Korytów | 2 | 1.605 | 12.295 | replacement of rails, sleepers, spacers, springs, tamping | 15 | 24 | 360 | 120 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 11; Number of planned closing days in the timetable 2022/2023 in individual months X: 4 | single-track two-way traffic on the active track | 2023-09-20 | 2023-10-04 | 4.010
12 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | Grodzisk Mazowiecki - Korytów | 2 | 1.605 | 12.295 | replacement of rails, sleepers, spacers, springs, tamping | 16 | 6 | 128 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months X: 16 | traffic interruption | 2023-10-05 | 2023-10-20 | 4.010
13 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | Korytów -Szeligi | 1 | 15.385 | 24.351 | System tests during service breaks | 11 | 6 | 66 | 120 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 11 | single-track two-way traffic on the active track | 2023-06-16 | 2023-06-26 | 4.010
14 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | Korytów -Szeligi | 2 | 15.385 | 24.351 | System tests during service breaks | 11 | 6 | 66 | 120 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 4; Number of planned closing days in the timetable 2022/2023 in individual months VII: 7 | single-track two-way traffic on the active track | 2023-06-27 | 2023-07-07 | 4.010
15 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | szlak Korytów - Szeligi | 1 | 15.385 | 21.37 | replacement of rails, sleepers, spacers, springs, tamping | 7 | 24 | 168 | 120 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 7 | single-track two-way traffic on the active track | 2023-09-05 | 2023-09-11 | 4.010
16 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | szlak Korytów - Szeligi | 1 | 15.385 | 21.37 | replacement of rails, sleepers, spacers, springs, tamping | 8 | 6 | 64 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 8 | traffic interruption | 2023-09-12 | 2023-09-19 | 4.010
17 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | szlak Korytów - Szeligi | 2 | 15.385 | 21.37 | replacement of rails, sleepers, spacers, springs, tamping | 7 | 6 | 56 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 7 | traffic interruption | 2023-09-05 | 2023-09-11 | 4.010
18 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | szlak Korytów - Szeligi | 2 | 15.385 | 21.37 | replacement of rails, sleepers, spacers, springs, tamping | 8 | 24 | 192 | 120 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 8 | single-track two-way traffic on the active track | 2023-09-12 | 2023-09-19 | 4.010
19 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | Włoszczowa Płn. - Góra Włodowska | 1 | 155.463 | 207.231 | System tests during service breaks | 12 | 6 | 72 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 12 | single-track two-way traffic on the active track | 2023-09-16 | 2023-09-27 | 4.010
20 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | Włoszczowa Płn. - Góra Włodowska | 2 | 155.463 | 207.231 | System tests during service breaks | 11 | 6 | 66 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 3; Number of planned closing days in the timetable 2022/2023 in individual months X: 8 | single-track two-way traffic on the active track | 2023-09-28 | 2023-10-08 | 4.010
21 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | Góra Włodowska - Zawiercie | 1 | 207.231 | 224.915 | System tests during service breaks | 13 | 6 | 78 | 120 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months X: 13 | single-track two-way traffic on the active track | 2023-10-09 | 2023-10-21 | 4.010
22 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | Góra Włodowska - Zawiercie | 2 | 207.231 | 224.915 | System tests during service breaks | 12 | 6 | 72 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months X: 10; Number of planned closing days in the timetable 2022/2023 in individual months XI: 2 | single-track two-way traffic on the active track | 2023-10-22 | 2023-11-02 | 4.010
23 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | Szeligi - Strzałki | 1 | 24.351 | 58.182 | System tests during service breaks | 12 | 6 | 72 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 12 | single-track two-way traffic on the active track | 2023-07-08 | 2023-07-19 | 4.010
24 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | Szeligi - Strzałki | 2 | 24.351 | 58.182 | System tests during service breaks | 11 | 6 | 66 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 11 | single-track two-way traffic on the active track | 2023-07-20 | 2023-07-30 | 4.010
25 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | Strzałki - Opoczno Pd. | 1 | 58.182 | 93.888 | System tests during service breaks | 12 | 6 | 72 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 1; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 11 | single-track two-way traffic on the active track | 2023-07-31 | 2023-08-11 | 4.010
26 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | Strzałki - Opoczno Pd. | 2 | 58.182 | 93.888 | System tests during service breaks | 12 | 6 | 72 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 12 | single-track two-way traffic on the active track | 2023-08-12 | 2023-08-23 | 4.010
27 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | Opoczno Pd. - Włoszczowa Płn. | 1 | 93.888 | 155.463 | System tests during service breaks | 12 | 6 | 72 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 8; Number of planned closing days in the timetable 2022/2023 in individual months IX: 4 | single-track two-way traffic on the active track | 2023-08-24 | 2023-09-04 | 4.010
28 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | Opoczno Pd. - Włoszczowa Płn. | 2 | 93.888 | 155.463 | System tests during service breaks | 11 | 6 | 66 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 11 | single-track two-way traffic on the active track | 2023-09-05 | 2023-09-15 | 4.010
29 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | szlak Kietlanka - Czyżew | 1, 2 | 107.26 | 111.036 | upgrade | 150 | 4 | 600 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30 | traffic interruption | 2023-02-01 | 2023-06-30 | 1.090
30 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | stacja Czyżew | 1, 2 | 111.036 | 113.505 | upgrade | 202 | 4 | 808 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XII: 21; Number of planned closing days in the timetable 2022/2023 in individual months I: 31; Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30 | traffic on active track at the station | 2022-12-11 | 2023-06-30 | 1.090
31 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | Szlak Czyżew - Szepietowo | 1, 2 | 113.505 | 126.473 | upgrade | 202 | 4 | 808 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XII: 21; Number of planned closing days in the timetable 2022/2023 in individual months I: 31; Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30 | traffic interruption | 2022-12-11 | 2023-06-30 | 1.090
32 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | Stacja Szepietowo | 1, 2 | 126.473 | 128.387 | upgrade | 61 | 4 | 244 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30 | single-track two-way traffic on the active track | 2023-05-01 | 2023-06-30 | 1.090
33 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | Szlak Szepietowo -Racibory | 1 | 128.387 | 139.563 | upgrade | 30 | 24 | 720 | 100 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 30 | single-track two-way traffic on the active track | 2023-06-01 | 2023-06-30 | 1.090
34 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | Szlak Szepietowo -Racibory | 1 | 128.387 | 139.563 | upgrade | 31 | 4 | 124 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 31 | traffic interruption | 2023-07-01 | 2023-07-31 | 1.090
35 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | Szlak Szepietowo -Racibory | 2 | 128.387 | 139.563 | upgrade | 30 | 4 | 120 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 30 | traffic interruption | 2023-06-01 | 2023-06-30 | 1.090
36 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | Szlak Szepietowo -Racibory | 2 | 128.387 | 139.563 | upgrade | 31 | 24 | 744 | 100 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 31 | single-track two-way traffic on the active track | 2023-07-01 | 2023-07-31 | 1.090
37 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | Stacja Racibory | 1 | 139.563 | 141.138 | upgrade | 273 | 4 | 1092 | traffic interruption | no limit |  |  |  | 20 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2023-03-12 | 2023-12-09 | 1.090
38 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | Stacja Racibory | 2, 4 | 139.563 | 141.138 | upgrade | 273 | 24 | 6552 | 40 km/h | no limit |  |  |  | 20 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2023-03-12 | 2023-12-09 | 1.090
39 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | Szlak Racibory - Łapy | 1 | 141.138 | 152.996 | upgrade | 273 | 4 | 1092 | traffic interruption | no limit |  |  |  | 20 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2023-03-12 | 2023-12-09 | 1.090
40 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | Szlak Racibory - Łapy | 2 | 141.138 | 152.996 | upgrade | 273 | 24 | 6552 | 100 km/h | no limit |  |  |  | 20 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | single-track two-way traffic on the active track | 2023-03-12 | 2023-12-09 | 1.090
41 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | Stacja Łapy | 1 | 152.996 | 155.035 | upgrade | 273 | 4 | 1092 | no limit | no limit |  |  |  | 20 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2023-03-12 | 2024-12-07 | 1.090
42 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | Stacja Łapy | 2, 4, 6, 8, 10, 16, 18 | 152.996 | 155.035 | upgrade | 273 | 24 | 6552 | 40 km/h | no limit |  |  |  | 20 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2023-03-12 | 2024-12-07 | 1.090
43 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | Szlak Łapy - Białystok | 1 | 156.846 | 175.054 | upgrade | 336 | 4 | 1344 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 11 |  | traffic interruption | 2022-12-11 | 2023-11-11 | 1.090
44 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | Szlak Łapy - Białystok | 2 | 163.251 | 175.054 | upgrade | 336 | 24 | 8064 | 100 km/h | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 11 |  | single-track two-way traffic on the active track | 2022-12-11 | 2023-11-11 | 1.090
45 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | Stacja Białystok | 3 | 175.054 | 178.002 | upgrade | 180 | 24 | 4320 | 40 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 20; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 7 | traffic on active track at the station | 2023-06-11 | 2023-12-07 | 1.090
46 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | Stacja Białystok | 5, 7 | 175.054 | 178.002 | upgrade | 182 | 24 | 4368 | 40 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 20; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-06-11 | 2024-05-30 | 1.090
47 | 1 | 7 | WARSZAWA WSCHODNIA OSOBOWA - DOROHUSK | IRR1/3 | Warszawa Wawer | 1, 2 | 11.07 | 13.245 | railway line upgrade | 153 | 24 | 3672 | 80 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months III: 11; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 20 | traffic on active track at the station | 2023-03-21 | 2023-08-20 | 1.088
48 | 1 | 7 | WARSZAWA WSCHODNIA OSOBOWA - DOROHUSK | IRR1/3 | Warszawa Wawer | 4, 6, 8 | 11.07 | 13.245 | railway line upgrade | 34 | 24 | 816 | 80 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 11; Number of planned closing days in the timetable 2022/2023 in individual months IX: 23 | traffic on active track at the station | 2023-08-21 | 2023-09-23 | 1.088
49 | 2 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IRR1/2 | Stara Wola - Radom | 1 | 97 | 101.4 | Reconstruction of the contact line, drainage and other colliding infrastructure, construction of a platform in the intertrack space between tracks 1 and 2 of line 8 at km 101.000 – 101.400 | 364 | 4 | 2184 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2022-12-09 | 2023-12-31 | 4.022
50 | 2 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IRR1/2 | Stara Wola - Radom | 2 | 97 | 101.4 | Reconstruction of the contact line, drainage and other colliding infrastructure, construction of a platform in the intertrack space between tracks 1 and 2 of line 8 at km 101.000 – 101.400 | 364 | 4 | 2184 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2022-12-09 | 2023-12-31 | 4.022
51 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Puszcza Mariańska- Mszczonów | 2 | 12.444 | 27.538 | demolition works | 88 | 24 | 2112 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IV: 28; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | single-track two-way traffic on the active track | 2023-04-03 | 2023-06-29 | 4.012
52 | 1 | 12 | SKIERNIEWICE - ŁUKÓW | IRR1/1 | Kępa Gliniecka- Osieck | 2 | 76.6 | 88.6 | demolition works | 88 | 24 | 2112 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IV: 28; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | single-track two-way traffic on the active track | 2023-04-03 | 2023-06-29 | 4.012
53 | 2 | 22 | TOMASZÓW MAZOWIECKI - RADOM | IRR1/2 | Tomaszów Maz. - Brzustów | 1 | 1.968 | 1.968 | Bridge reconstruction at km 1.968 | 15 | 24 | 360 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 2; Number of planned closing days in the timetable 2022/2023 in individual months X: 13 | traffic interruption – single-track line | 2023-09-29 | 2023-10-13 | 4.030
54 | 2 | 22 | TOMASZÓW MAZOWIECKI - RADOM | IRR1/2 | Przysucha - Wolanów | 1 | 48.242 | 74.994 | End-to-end contact line replacement | 159 | 24 | 3816 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months III: 19; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 18 | single-track two-way traffic on the active track | 2023-03-13 | 2023-08-18 | 4.030
55 | 2 | 25 | ŁÓDŹ KALISKA - DĘBICA | IRR1/2 | Tomaszów Maz. - Jeleń | 1 | 56.527 | 60.3 | Bridge reconstruction at km 1.968 of line No. 22 | 15 | 24 | 360 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 2; Number of planned closing days in the timetable 2022/2023 in individual months X: 13 | traffic interruption – single-track line | 2023-09-29 | 2023-10-13 | 4.030
56 | 2 | 26 | ŁUKÓW - RADOM | IRR1/2 | Radom Wschodni | 1 | 115.8 | 116.59 | Reconstruction of the contact line, drainage and other infrastructure colliding with the construction of a platform in the intertrack space between tracks 1 and 2 of line 8 at km 101.000 – 101.400 | 364 | 4 | 2184 | 30 km/h | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2022-12-09 | 2023-12-31 | 4.022
57 | 2 | 26 | ŁUKÓW - RADOM | IRR1/2 | Radom Wschodni | 2 | 115.8 | 116.59 | Reconstruction of the contact line, drainage and other infrastructure colliding with the construction of a platform in the intertrack space between tracks 1 and 2 of line 8 at km 101.000 – 101.400 | 364 | 4 | 2184 | 30 km/h | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2022-12-09 | 2023-12-31 | 4.022
58 | 1 | 35 | OSTROŁĘKA - SZCZYTNO | IRR1/14 | Ostrołęka - Grabowo | 1 | -0.748 | 7.051 | Finishing work, rectification of defects | 122 | 24 | 2928 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30 | traffic interruption – single-track line | 2023-03-01 | 2023-06-30 | 1.171
59 | 1 | 35 | OSTROŁĘKA - SZCZYTNO | IRR1/14 | Grabowo - Chorzele | 1 | 7.051 | 56.755 | Finishing work, rectification of defects | 122 | 24 | 2928 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30 | traffic interruption – single-track line | 2023-03-01 | 2023-06-30 | 1.171
60 | 1 | 36 | OSTROŁĘKA - ŁAPY | IRR1/7 | Szlak Sokoły - Łapy | 1 | 76.782 | 88.17 | upgrade | 98 | 24 | 2352 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 28; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption – single-track line | 2023-09-03 | 2024-06-04 | 1.090
61 | 1 | 60 | KOBYLANY - TERESPOL (SZ) | IRR1/16 | stacja Terespol | 154 | 208.1 | 208.5 | Track upgrade | 16 | 24 | 384 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XI: 7; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-11-24 | 2023-12-23
62 | 7 | 281 | OLEŚNICA - CHOJNICE | IRR1/1 | Miłosław-Września | 1 | 126.725 | 134.673 | construction of a railway viaduct | 182 | 24 | 4368 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months III: 20; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 9 | single-track two-way traffic on the active track | 2023-03-12 | 2023-09-09 | 1.066
63 | 7 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IRR1/1 | Kobylnica | 8 | 0.033 | 0.835 | Construction of road tunnel/rail viaduct | 225 | 24 | 5400 | no limit | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 11 |  | traffic on active track at the station | 2023-04-01 | 2023-11-11 | 1.066
64 | 7 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IRR1/1 | Kobylnica | 4 | 0.054 | 0.879 | Construction of road tunnel/rail viaduct | 225 | 24 | 5400 | no limit | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 11 |  | traffic on active track at the station | 2023-04-01 | 2023-11-11 | 1.066
65 | 7 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IRR1/1 | Kobylnica | 6 | 0.075 | 0.802 | Construction of road tunnel/rail viaduct | 225 | 24 | 5400 | no limit | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 11 |  | traffic on active track at the station | 2023-04-01 | 2023-11-11 | 1.066
66 | 7 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IRR1/1 | Kobylnica | 11 | 0.42 | 0.573 | Construction of road tunnel/rail viaduct | 225 | 24 | 5400 | no limit | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 11 |  | traffic on active track at the station | 2023-04-01 | 2023-11-11 | 1.066
67 | 7 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IRR1/1 | Poznań Wschód - Kobylnica | 2 | 0.71 | 5.807 | Construction of road tunnel/rail viaduct | 225 | 24 | 5400 | 60 km/h | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 11 |  | traffic on active track at the station | 2023-04-01 | 2023-11-11 | 1.066
68 | 7 | 354 | POZNAŃ GŁÓWNY POD - PIŁA GŁÓWNA | IRR1/1 | Poznań POD- Suchy Las | 1 | 0.097 | 5.697 | construction of a road viaduct | 5 | 24 | 120 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XI: 5 | single-track two-way traffic on the active track | 2023-11-14 | 2023-11-18 | 1.066
69 | 7 | 354 | POZNAŃ GŁÓWNY POD - PIŁA GŁÓWNA | IRR1/1 | Poznań POD- Suchy Las | 1 | 0.097 | 5.697 | construction of a road viaduct | 2 | 24 | 48 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XII: 2 | single-track two-way traffic on the active track | 2023-12-08 | 2023-12-15 | 1.066
70 | 7 | 354 | POZNAŃ GŁÓWNY POD - PIŁA GŁÓWNA | IRR1/1 | Poznań POD- Suchy Las | 1, 2 | 0.097 | 5.697 | construction of a road viaduct | 54 | 4 | 216 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months V: 30; Number of planned closing days in the timetable 2022/2023 in individual months VI: 24 | traffic interruption | 2023-05-02 | 2023-06-24 | 1.066
71 | 7 | 354 | POZNAŃ GŁÓWNY POD - PIŁA GŁÓWNA | IRR1/1 | Poznań POD- Suchy Las | 1, 2 | 0.097 | 5.697 | construction of a road viaduct | 16 | 6 | 96 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months X: 16 | traffic interruption | 2023-10-03 | 2023-10-18 | 1.066
72 | 7 | 354 | POZNAŃ GŁÓWNY POD - PIŁA GŁÓWNA | IRR1/1 | Poznań POD- Suchy Las | 1, 2 | 0.097 | 5.697 | construction of a road viaduct | 9 | 4 | 36 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-12-08 | 2024-01-24 | 1.066
73 | 7 | 354 | POZNAŃ GŁÓWNY POD - PIŁA GŁÓWNA | IRR1/1 | Poznań POD- Suchy Las | 1, 2 | 0.097 | 5.697 | construction of a road viaduct | 50 | 6 | 300 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months X: 13; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 7 | traffic interruption | 2023-10-19 | 2023-12-07 | 1.066
74 | 7 | 354 | POZNAŃ GŁÓWNY POD - PIŁA GŁÓWNA | IRR1/1 | Poznań POD- Suchy Las | 2 | 0.097 | 5.697 | construction of a road viaduct | 5 | 24 | 120 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XI: 5 | single-track two-way traffic on the active track | 2023-11-21 | 2023-11-25 | 1.066
75 | 1 | 506 | WARSZAWA ANTONINÓW - WARSZAWA WAWER | IRR1/3 | Warszawa Wschodnia Towarowa- Warszawa Wawer | 1, 2 | -0.248 | 4.111 | railway line upgrade | 84 | 4 | 336 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IV: 24; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic interruption | 2023-04-07 | 2023-06-29 | 1.088
76 | 1 | 507 | WARSZAWA GŁÓWNA TOWAROWA - WARSZAWA GOŁĄBKI | IRR1/9 | WGT - W-wa Gołąbki | 1, 2 | 0.965 | 2.523 | Night service interruption | 266 | 4 | 1064 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 2 |  |  |  | traffic interruption | 2020-12-13 | 2023-09-02 | 1.099
77 | 7 | 808 | WRZEŚNIA - PODSTOLICE | IRR1/1 | Września-Podstolice | 1 | 0.433 | 5.13 | construction of a railway viaduct | 182 | 24 | 4368 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months III: 20; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 9 | single-track two-way traffic on the active track | 2023-03-12 | 2023-09-09 | 1.066
78 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/5 | szlak Chotyłów - Małaszewicze Południowe | 1, 2 | 190.33 | 198.49 | upgrade | 342 | 4 | 1368 | traffic interruption | no limit |  | 30 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2023-01-02 | 2023-12-22 | 1.123
79 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/5 | szlak Magdalenka - Małaszewicze Południowe | 1, 2 | 198.051 | 198.49 | upgrade | 342 | 4 | 1368 | traffic interruption | no limit |  | 30 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2023-01-02 | 2023-12-22 | 1.123
80 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/5 | stacja Małaszewicze Południowe | 1, 2 | 198.49 | 200.118 | upgrade | 342 | 4 | 1368 | no limit | no limit |  | 30 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2023-01-02 | 2023-12-22 | 1.123
81 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja EŁK TOWAROWY 101,141÷103,100 | 101 | 101.141 | 103.1 | Multi-discipline upgrade works | 343 | 24 | 8232 | 50 km/h | no limit |  | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2023-01-01 | 2023-12-25 | 1.144
82 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja EŁK TOWAROWY | 103 | 101.28 | 102.19 | Multi-discipline upgrade works | 343 | 24 | 8232 | 50 km/h | no limit |  | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2023-01-01 | 2023-12-25 | 1.144
83 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja EŁK TOWAROWY 101,141÷103,100 | 102 | 101.28 | 102.19 | Multi-discipline upgrade works | 343 | 24 | 8232 | 50 km/h | no limit |  | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2023-01-01 | 2023-12-25 | 1.144
84 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja EŁK TOWAROWY | 111 | 101.303 | 102.19 | Multi-discipline upgrade works | 343 | 24 | 8232 | 50 km/h | no limit |  | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2023-01-01 | 2023-12-25 | 1.144
85 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja EŁK TOWAROWY | 105 | 101.33 | 102.19 | Multi-discipline upgrade works | 343 | 24 | 8232 | 50 km/h | no limit |  | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2023-01-01 | 2023-12-25 | 1.144
86 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja EŁK TOWAROWY | 127 | 101.349 | 102.247 | Multi-discipline upgrade works | 343 | 24 | 8232 | 50 km/h | no limit |  | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2023-01-01 | 2023-12-25 | 1.144
87 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja EŁK TOWAROWY | 129 | 101.349 | 102.213 | Multi-discipline upgrade works | 343 | 24 | 8232 | 50 km/h | no limit |  | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2023-01-01 | 2023-12-25 | 1.144
88 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja EŁK TOWAROWY | 107 | 101.357 | 102.14 | Multi-discipline upgrade works | 343 | 24 | 8232 | 50 km/h | no limit |  | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2023-01-01 | 2023-12-25 | 1.144
89 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja EŁK TOWAROWY | 109 | 101.357 | 102.14 | Multi-discipline upgrade works | 343 | 24 | 8232 | 50 km/h | no limit |  | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2023-01-01 | 2023-12-25 | 1.144
90 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Ełk | 1 | 102.243 | 103.994 | Multi-discipline upgrade works | 162 | 24 | 3888 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-07-01 | 2023-12-25 | 1.144
91 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Ełk | 10 | 102.243 | 103.994 | Multi-discipline upgrade works | 179 | 24 | 4296 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months I: 30; Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic on active track at the station | 2023-01-02 | 2023-06-29 | 1.144
92 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Ełk | 12 | 102.243 | 103.994 | Multi-discipline upgrade works | 179 | 24 | 4296 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months I: 30; Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic on active track at the station | 2023-01-02 | 2023-06-29 | 1.144
93 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Ełk | 14 | 102.243 | 103.994 | Multi-discipline upgrade works | 179 | 24 | 4296 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months I: 30; Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic on active track at the station | 2023-01-02 | 2023-06-29 | 1.144
94 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Ełk | 16 | 102.243 | 103.994 | Multi-discipline upgrade works | 179 | 24 | 4296 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months I: 30; Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic on active track at the station | 2023-01-02 | 2023-06-29 | 1.144
95 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Ełk | 20 | 102.243 | 103.994 | Multi-discipline upgrade works | 179 | 24 | 4296 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months I: 30; Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic on active track at the station | 2023-01-02 | 2023-06-29 | 1.144
96 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Ełk | 3 | 102.243 | 103.994 | Multi-discipline upgrade works | 179 | 24 | 4296 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months I: 30; Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic on active track at the station | 2023-01-02 | 2023-06-29 | 1.144
97 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Ełk | 4 | 102.243 | 103.994 | Multi-discipline upgrade works | 179 | 24 | 4296 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months I: 30; Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic on active track at the station | 2023-01-02 | 2023-06-29 | 1.144
98 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Ełk | 5 | 102.243 | 103.994 | Multi-discipline upgrade works | 179 | 24 | 4296 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months I: 30; Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic on active track at the station | 2023-01-02 | 2023-06-29 | 1.144
99 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Ełk | 8 | 102.243 | 103.994 | Multi-discipline upgrade works | 179 | 24 | 4296 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months I: 30; Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic on active track at the station | 2023-01-02 | 2023-06-29 | 1.144
100 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Ełk | 2 | 102.857 | 103.574 | Multi-discipline upgrade works | 162 | 24 | 3888 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-07-01 | 2023-12-25 | 1.144
101 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Ełk | 6 | 102.974 | 103.574 | Multi-discipline upgrade works | 162 | 24 | 3888 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-07-01 | 2023-12-25 | 1.144
102 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Ełk | 22 | 103.225 | 103.551 | Multi-discipline upgrade works | 162 | 24 | 3888 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-07-01 | 2023-12-25 | 1.144
103 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Ełk | 24 | 103.551 | 103.782 | Multi-discipline upgrade works | 162 | 24 | 3888 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-07-01 | 2023-12-25 | 1.144
104 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Ełk - Giżycko | 1 | 103.706 | 152.85 | Track works, engineering structure works, contact line, Railway Traffic Controlling system [srk], telecommunications | 364 | 24 | 8736 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption – single-track line | 2022-03-06 | 2024-02-03 | 1.119
105 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Szlak Giżycko - Sterławki Wielkie | 1 | 152.85 | 164.615 | Track works, engineering structure works, contact line, Railway Traffic Controlling system [srk], telecommunications | 251 | 24 | 6024 | traffic interruption | no limit |  |  |  |  | 28 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption – single-track line | 2023-04-03 | 2025-03-20
106 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Sterławki Wielkie | 1 | 164.615 | 166.65 | Track works, engineering structure works, contact line, Railway Traffic Controlling system [srk], telecommunications | 254 | 24 | 6096 | traffic interruption | no limit |  |  |  | 1 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2023-03-31 | 2025-03-20
107 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Szlak Sterławki Wielkie - Kętrzyn | 1 | 166.65 | 178.7 | Track works, engineering structure works, contact line, Railway Traffic Controlling system [srk], telecommunications | 254 | 24 | 6096 | traffic interruption | no limit |  |  |  | 1 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption – single-track line | 2023-03-31 | 2025-03-20
108 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Kętrzyn | 1 | 178.7 | 181 | Track works, engineering structure works, contact line, Railway Traffic Controlling system [srk], telecommunications | 254 | 24 | 6096 | traffic interruption | no limit |  |  |  | 1 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2023-03-31 | 2025-03-20
109 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Szlak Kętrzyn - Tołkiny | 1 | 181 | 191.95 | Track works, engineering structure works, contact line, Railway Traffic Controlling system [srk], telecommunications | 254 | 24 | 6096 | traffic interruption | no limit |  |  |  | 1 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption – single-track line | 2023-03-31 | 2025-03-20
110 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Tołkiny | 1 | 191.95 | 193.8 | Track works, engineering structure works, contact line, Railway Traffic Controlling system [srk], telecommunications | 254 | 24 | 6096 | traffic interruption | no limit |  |  |  | 1 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2023-03-31 | 2025-03-20
111 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Szlak Tołkiny - Korsze | 1 | 193.8 | 200.1 | Track works, engineering structure works, contact line, Railway Traffic Controlling system [srk], telecommunications | 254 | 24 | 6096 | traffic interruption | no limit |  |  |  | 1 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption – single-track line | 2023-03-31 | 2025-03-20
112 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Korsze | 1 | 200.1 | 202.826 | Track works, engineering structure works, contact line, Railway Traffic Controlling system [srk], telecommunications | 254 | 24 | 6096 | no limit | no limit |  |  |  | 1 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2023-03-31 | 2025-03-20
113 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Stacja Kościerzyna | 1, 2, 3, 4, 6, 133, 143 | 136.105 | 138.068 | Reconstruction of the track system | 154 | 24 | 3696 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 23; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-07-09 | 2023-12-09
114 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Stacja Gołubie Kaszubskie | 1, 2, 4 | 148.344 | 149.701 | Reconstruction of the track system | 154 | 24 | 3696 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 23; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-07-09 | 2026-04-08
115 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Gołubie Kaszubskie - Somonino | 1 | 149.701 | 161.73 | End-to-end route reconstruction | 154 | 24 | 3696 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 23; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption – single-track line | 2023-07-09 | 2026-04-08
116 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Stacja Somonino | 1 | 161.73 | 162.5 | Reconstruction of the track system | 154 | 24 | 3696 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 23; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-07-09 | 2025-01-05
117 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Stacja Somonino | 10, 12 | 161.73 | 163.363 | Reconstruction of the track system | 154 | 24 | 3696 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 23; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-07-09 | 2025-01-05
118 | 5 | 214 | SOMONINO - KARTUZY | IRR2/7 | Somonino-Kartuzy | 1 | 0.64 | 6.991 | End-to-end route reconstruction | 154 | 24 | 3696 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 23; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption – single-track line | 2023-07-09 | 2024-05-11
119 | 5 | 216 | DZIAŁDOWO - OLSZTYN GŁÓWNY | IRR2/8 | stacja Olsztyn | 3 | 82.132 | 83.635 | upgrade | 101 | 24 | 2424 | 60 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 9; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30 | traffic on active track at the station | 2023-06-22 | 2023-09-30 | 2.007
120 | 5 | 219 | OLSZTYN GŁÓWNY - EŁK | IRR2/8 | stacja Olsztyn | 5 | -0.425 | 1.48 | upgrade | 101 | 24 | 2424 | 30 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months III: 8; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 2 | traffic on active track at the station | 2023-03-24 | 2023-07-02 | 2.007
121 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IRSK2/1/4 | Ostróda | 3, 301, 302, 303, 304, 305, 306, 308, 309, 310, 311, 312 | 258 | 258 | construction work at the station | 48 | 24 | 1152 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months X: 9; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-10-23 | 2024-03-21
122 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IRSK2/1/4 | Ostróda | 4 | 258.105 | 259.4 | construction work at the station | 272 | 24 | 6528 | 50 km/h | no limit |  |  |  | 19 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2023-03-13 | 2024-01-08
123 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IRSK2/1/4 | Ostróda | 10, 106 | 258.185 | 259.04 | construction work at the station | 272 | 24 | 6528 | 50 km/h | no limit |  |  |  | 19 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2023-03-13 | 2024-01-08
124 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IRSK2/1/4 | Ostróda | 6 | 258.67 | 259.03 | construction work at the station | 43 | 24 | 1032 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 22; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 21 | traffic on active track at the station | 2023-07-10 | 2023-08-21
125 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IRSK2/1/4 | Ostróda | 8 | 258.67 | 259.03 | construction work at the station | 43 | 24 | 1032 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 11; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 2 | traffic on active track at the station | 2023-08-21 | 2023-10-02
126 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IRSK2/1/4 | Ostróda | 105 | 258.825 | 258.89 | construction work at the station | 22 | 24 | 528 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months X: 22 | traffic on active track at the station | 2023-10-02 | 2023-10-23
127 | 2 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IRR3/1 | st. Sędziszów | 1, 3a, 5, 7, 9, 11, 13, 15, 19, 51, 55, 53, 206, 41, 45, 47, 43 | 249.15 | 250.25 | Upgrade of the line/reconstruction of the track system and other infrastructure components | 131 | 24 | 3144 | 60 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-08-01 | 2024-07-31
128 | 2 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IRR3/1 | st. Sędziszów | 2 | 249.15 | 250.25 | Upgrade of the line/reconstruction of the track system and other infrastructure components | 131 | 4 | 524 | 60 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-08-01 | 2024-07-31
129 | 2 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IRR3/1 | st. Sędziszów | 63, 65, 59, 61 | 249.3 | 250.066 | Upgrade of the line/reconstruction of the track system and other infrastructure components | 39 | 24 | 936 | 60 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-11-01 | 2024-06-30
130 | 2 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IRR3/1 | st. Sędziszów | 2 | 250.35 | 251.45 | Upgrade of the line/reconstruction of the track system and other infrastructure components | 131 | 4 | 524 | 60 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-08-01 | 2024-07-31
131 | 2 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IRR3/1 | st. Sędziszów - st. Kozłów | 1 | 251.6 | 262.6 | Upgrade of the line/reconstruction of the track system and other infrastructure components | 131 | 24 | 3144 | 60 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | single-track two-way traffic on the active track | 2023-08-01 | 2024-07-31
132 | 2 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IRR3/1 | st. Sędziszów - st. Kozłów | 2 | 251.601 | 262.601 | Upgrade of the line/reconstruction of the track system and other infrastructure components | 131 | 4 | 524 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-08-01 | 2024-07-31
133 | 2 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IRR3/1 | st. Kozłów | 3, 5, 5a, 7, 9, 9b, 11 | 261.368 | 262.535 | Upgrade of the line/reconstruction of the track system and other infrastructure components | 131 | 24 | 3144 | 60 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-08-01 | 2024-06-30
134 | 2 | 25 | ŁÓDŹ KALISKA - DĘBICA | IRR3/1 | Stacja Bodzechów | 1, 3 | 193 | 194.3 | End-to-end surface replacement for track no. 1 at the station, replacement of switches 1, 9, 13, 22 and 24, rebuilding the platform, control-command and signalling, contact line, non-traction power and telecommunication works and ancillary works | 61 | 24 | 1464 | 40 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31 | traffic on active track at the station | 2023-06-01 | 2023-07-31 | 2.004
135 | 2 | 25 | ŁÓDŹ KALISKA - DĘBICA | IRR3/1 | szlak Bodzechów-Ożarów Cementownia | 1 | 194.3 | 205.5 | Replacement of the switch 27, reconstruction of platforms at passenger stops, signalling, contact line, non-traction power and telecommunication works and ancillary works | 61 | 24 | 1464 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31 | single-track two-way traffic on the active track | 2023-06-01 | 2023-07-31 | 2.004
136 | 2 | 25 | ŁÓDŹ KALISKA - DĘBICA | IRR3/1 | szlak Bodzechów-Ożarów Cementownia | 2 | 194.3 | 205.5 | Carrying out and supervision of overhead contact line network works, unloading materials, switching of Railway Traffic Controlling system [srk] equipment. | 61 | 4 | 244 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31 | traffic interruption | 2023-06-01 | 2023-07-31 | 2.004
137 | 2 | 25 | ŁÓDŹ KALISKA - DĘBICA | IRR3/1 | P. odg. Zalesie Gorzyckie | 1, 2 | 229.6 | 230.6 | Carrying out and supervision of overhead contact line network works, unloading materials, switching of Railway Traffic Controlling system [srk] equipment. | 182 | 4 | 728 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XII: 19; Number of planned closing days in the timetable 2022/2023 in individual months I: 31; Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 12 | traffic interruption | 2022-12-13 | 2023-06-12 | 2.004
138 | 2 | 25 | ŁÓDŹ KALISKA - DĘBICA | IRR3/1 | szlak Zalesie Gorzyckie - Sandomierz | 1 | 229.6 | 230.6 | Carrying out and supervision of overhead contact line network works, unloading materials, switching of Railway Traffic Controlling system [srk] equipment. | 182 | 4 | 728 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XII: 20; Number of planned closing days in the timetable 2022/2023 in individual months I: 31; Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 11 | traffic interruption – single-track line | 2022-12-12 | 2023-06-11 | 2.004
139 | 2 | 25 | ŁÓDŹ KALISKA - DĘBICA | IRR3/1 | Sandomierz - Sobów | 1 | 242.62 | 249.75 | Replacement of railroad surface, reconstruction of platforms at passenger stations, reconstruction of engineering structures, non-traction electrical and telecommunications works and associated works | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption – single-track line | 2023-09-01 | 2024-06-27
140 | 2 | 25 | ŁÓDŹ KALISKA - DĘBICA | IRR3/1 | Sobów - Chmielów | 1 | 249.75 | 260.922 | Replacement of railroad surface, reconstruction of platforms at passenger stations, reconstruction of engineering structures, non-traction electrical and telecommunications works and associated works | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption – single-track line | 2023-09-01 | 2024-06-27
141 | 3 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR3/8 | Jaroszowiec Olkuski - Olkusz | 1 | 35.898 | 44 | service interruption | 61 | 6 | 366 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months V: 12; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 19 | single-track two-way traffic on the active track | 2023-05-20 | 2023-07-19 | 4.027
142 | 3 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR3/8 | Jaroszowiec Olkuski - Olkusz | 1 | 35.898 | 44 | Contact line reconstruction | 39 | 24 | 936 | 40 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months X: 1; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 8 | single-track two-way traffic on the active track | 2023-10-31 | 2023-12-08 | 4.027
143 | 3 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR3/8 | Jaroszowiec Olkuski - Olkusz | 2 | 35.898 | 44 | service interruption | 39 | 6 | 234 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months X: 1; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 8 | traffic interruption | 2023-10-31 | 2023-12-08 | 4.027
144 | 3 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR3/8 | Jaroszowiec Olkuski - Olkusz | 1 | 36.237 | 44 | service interruption | 103 | 6 | 618 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 12; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 30 | traffic interruption | 2023-07-20 | 2023-10-30 | 4.027
145 | 3 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR3/8 | Jaroszowiec Olkuski - Olkusz | 2 | 36.237 | 44 | Contact line reconstruction, improvement of track quality | 103 | 24 | 2472 | 40 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 12; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 30 | single-track two-way traffic on the active track | 2023-07-20 | 2023-10-30 | 4.027
146 | 3 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR3/8 | Jaroszowiec Olkuski - Olkusz | 2 | 43.657 | 43.707 | reconstruction of the engineering structure | 61 | 24 | 1464 | 40 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months V: 12; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 19 | single-track two-way traffic on the active track | 2023-05-20 | 2023-07-19 | 4.027
147 | 3 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR3/8 | Olkusz - Bukowno | 1 | 46.8 | 51.825 | service interruption | 180 | 6 | 1080 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 19; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 8 | traffic interruption | 2023-06-12 | 2023-12-08 | 4.027
148 | 3 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR3/8 | Olkusz - Bukowno | 2 | 46.8 | 51.825 | Contact line reconstruction, improvement of track quality | 180 | 24 | 4320 | 40 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 19; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 8 | single-track two-way traffic on the active track | 2023-06-12 | 2023-12-08 | 4.027
149 | 2 | 74 | SOBÓW - STALOWA WOLA ROZWADÓW | IRR3/1 | Zbydniów - Stalowa Wola | 1 | 17.035 | 23.124 | Replacement of railroad surface, reconstruction of platforms at passenger stations, reconstruction of engineering structures, non-traction electrical and telecommunications works and associated works | 100 | 24 | 2400 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | single-track two-way traffic on the active track | 2023-09-01 | 2025-03-24
150 | 2 | 74 | SOBÓW - STALOWA WOLA ROZWADÓW | IRR3/1 | Zbydniów - Stalowa Wola | 2 | 17.035 | 23.124 | Carrying out and supervision of overhead contact line network works, unloading materials, switching of Railway Traffic Controlling system [srk] equipment. | 100 | 4 | 400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-09-01 | 2025-03-24
151 | 3 | 79 | PADEW - WOLA BARANOWSKA | IRR3/6 | Padew - Wola Baranowska | 1 | 0.211 | 4.972 | surface replacement + two structures | 60 | 24 | 1440 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months V: 30; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30 | traffic interruption – single-track line | 2023-05-02 | 2023-06-30 | 4.022
152 | 3 | 91 | KRAKÓW GŁÓWNY - MEDYKA | IRR3/3 | Kraków Główny - Kraków Płaszów | 1 | 0.358 | 2.85 | replacement of surface, contact line, construction of flyover, engineering structures, viaducts lk 91 - W11(km 2.631); W12(km 2.956); W13(3.019) | 202 | 24 | 4848 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XII: 21; Number of planned closing days in the timetable 2022/2023 in individual months I: 31; Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30 | single-track two-way traffic on the active track | 2019-07-02 | 2023-06-30 | 1.094
153 | 3 | 91 | KRAKÓW GŁÓWNY - MEDYKA | IRR3/6 | Żurawica - Przemyśl | 1, 2 | 242.962 | 244.234 | Reconstruction of the bridge at km 243.845 (Przemyśl) | 364 | 6 | 2184 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2022-08-29 | 2023-12-29 | 1.067
154 | 3 | 91 | KRAKÓW GŁÓWNY - MEDYKA | IRR3/6 | Żurawica - Przemyśl | 2 | 242.962 | 244.234 | Reconstruction of the bridge at km 243.845 (Przemyśl) | 184 | 24 | 4416 | 30 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31 | single-track two-way traffic on the active track | 2023-05-01 | 2023-10-31 | 1.067
155 | 3 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR3/4 | stacja Oświęcim | 2b | 24,046 (ukres rozjadzu nr 9 stargo/ 4 nowego w st. Oświęcim) | 24,600 (ukres rozjazdu nr 47 nowego w st.Oświęcim) | technology commissioning activities | 72 | 5 | 360 | 30 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months V: 17; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 25 | traffic on active track at the station | 2023-05-15 | 2023-07-25 | 1.091
156 | 3 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR3/4 | stacja Oświęcim | 202, 204 | 24,046 (ukres rozjazdu nr 9 starego / 4 nowego) | 24,600 (ukres rozjazdu nr 47 nowego) | technology commissioning – installation of switches 3, 4 | 61 | 24 | 1464 | 30 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months V: 16; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 15 | traffic on active track at the station | 2023-05-16 | 2023-07-15 | 1.091
157 | 3 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR3/4 | stacja Oświęcim | cały zakres stacji | 24.053 | 27.861 | Grinding and stabilisation tamping – technology commissioning of track groups without traffic interruption | 31 | 12 | 372 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 16; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 15 | traffic interruption | 2023-07-16 | 2023-08-15 | 1.091
158 | 3 | 94 | KRAKÓW PŁASZÓW - OŚWIĘCIM | IRR3/8 | Podbory Skawińskie - Brzeźnica | 1 | 20.6 | 29.5 | service interruption | 91 | 6 | 546 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30 | traffic interruption | 2023-04-01 | 2023-06-30 | 4.027
159 | 3 | 94 | KRAKÓW PŁASZÓW - OŚWIĘCIM | IRR3/8 | Podbory Skawińskie - Brzeźnica | 1 | 20.6 | 29.5 | network overhead contact line replacement, pavement replacement, revitalisation of engineering structures | 162 | 24 | 3888 | 40 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | single-track two-way traffic on the active track | 2023-07-01 | 2023-12-09 | 4.027
160 | 3 | 94 | KRAKÓW PŁASZÓW - OŚWIĘCIM | IRR3/8 | Podbory Skawińskie - Brzeźnica | 2 | 20.6 | 29.5 | network overhead contact line replacement, pavement replacement, revitalisation of engineering structures | 91 | 24 | 2184 | 40 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30 | single-track two-way traffic on the active track | 2023-04-01 | 2023-06-30 | 4.027
161 | 3 | 94 | KRAKÓW PŁASZÓW - OŚWIĘCIM | IRR3/8 | Podbory Skawińskie - Brzeźnica | 2 | 20.6 | 29.5 | service interruption | 162 | 6 | 972 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-07-01 | 2023-12-09 | 4.027
162 | 3 | 94 | KRAKÓW PŁASZÓW - OŚWIĘCIM | IRR3/8 | Brzeźnica | 1 | 29.5 | 30.8 | service interruption | 91 | 6 | 546 | 40 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30 | traffic on active track at the station | 2023-04-01 | 2023-06-30 | 4.027
163 | 3 | 94 | KRAKÓW PŁASZÓW - OŚWIĘCIM | IRR3/8 | Brzeźnica | 1 | 29.5 | 30.8 | network overhead contact line replacement, revitalisation of civil engineering structures, reconstruction of the platform | 162 | 24 | 3888 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-07-01 | 2023-12-09 | 4.027
164 | 3 | 94 | KRAKÓW PŁASZÓW - OŚWIĘCIM | IRR3/8 | Brzeźnica | 2 | 29.5 | 30.8 | network overhead contact line replacement, revitalisation of civil engineering structures, reconstruction of the platform | 91 | 24 | 2184 | 40 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30 | traffic on active track at the station | 2023-04-01 | 2023-06-30 | 4.027
165 | 3 | 94 | KRAKÓW PŁASZÓW - OŚWIĘCIM | IRR3/8 | Brzeźnica | 2 | 29.5 | 30.8 | service interruption | 162 | 6 | 972 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-07-01 | 2023-12-09 | 4.027
166 | 3 | 94 | KRAKÓW PŁASZÓW - OŚWIĘCIM | IRR3/8 | Brzeźnica - Spytkowice | 1 | 30.8 | 40.708 | network overhead contact line replacement, pavement replacement, revitalisation of engineering structures | 91 | 24 | 2184 | 40 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30 | single-track two-way traffic on the active track | 2023-04-01 | 2023-06-30 | 4.027
167 | 3 | 94 | KRAKÓW PŁASZÓW - OŚWIĘCIM | IRR3/8 | Brzeźnica - Spytkowice | 1 | 30.8 | 40.708 | service interruption | 162 | 6 | 972 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-07-01 | 2023-12-09 | 4.027
168 | 3 | 94 | KRAKÓW PŁASZÓW - OŚWIĘCIM | IRR3/8 | Brzeźnica - Spytkowice | 2 | 30.8 | 40.708 | service interruption | 91 | 6 | 546 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30 | traffic interruption | 2023-04-01 | 2023-06-30 | 4.027
169 | 3 | 94 | KRAKÓW PŁASZÓW - OŚWIĘCIM | IRR3/8 | Brzeźnica - Spytkowice | 2 | 30.8 | 40.708 | network overhead contact line replacement, pavement replacement, revitalisation of engineering structures | 162 | 24 | 3888 | 40 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | single-track two-way traffic on the active track | 2023-07-01 | 2023-12-09 | 4.027
170 | 3 | 94 | KRAKÓW PŁASZÓW - OŚWIĘCIM | IRR3/4 | Dwory - Oświęcim | 1 | 56.405 | 62,945 (ukres rozjazdu nr 6 w stacji Oświęcim) | upgrade – installation of switches 2, 3, 4 | 61 | 24 | 1464 | 30 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months V: 16; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 15 | single-track two-way traffic on the active track | 2023-05-16 | 2023-07-15 | 1.091
171 | 3 | 94 | KRAKÓW PŁASZÓW - OŚWIĘCIM | IRR3/8 | Dwory - Oświęcim | 1 | 58.128 | 64.71 | network overhead contact line replacement, revitalisation of engineering structures | 131 | 24 | 3144 | 40 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | single-track two-way traffic on the active track | 2023-08-01 | 2023-12-09 | 4.027
172 | 3 | 94 | KRAKÓW PŁASZÓW - OŚWIĘCIM | IRR3/8 | Dwory - Oświęcim | 2 | 58.128 | 64.71 | network overhead contact line replacement, revitalisation of engineering structures | 97 | 24 | 2328 | 40 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IV: 5; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31 | single-track two-way traffic on the active track | 2023-04-26 | 2023-07-31 | 4.027
173 | 3 | 94 | KRAKÓW PŁASZÓW - OŚWIĘCIM | IRR3/8 | Dwory - Oświęcim | 2 | 58.128 | 64.71 | service interruption | 131 | 6 | 786 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-08-01 | 2023-12-09 | 4.027
174 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | szlak Sucha Beskidzka - Maków Podhalański | 1 | 0.818 | 6.629 | line upgrade | 115 | 24 | 2760 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 23 | traffic interruption – single-track line | 2023-03-01 | 2023-06-23 | 1.136
175 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | szlak Sucha Beskidzka - Maków Podhalański | 1 | 0.818 | 6.629 | line upgrade | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption – single-track line | 2023-09-01 | 2023-12-21 | 1.136
176 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | stacja Osielec | 1, 2, 3, 4 | 15.661 | 17.6 | line upgrade | 115 | 24 | 2760 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 23 | traffic interruption | 2023-03-01 | 2023-06-23 | 1.136
177 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | stacja Osielec | 1, 2, 3, 4 | 16.116 | 16.832 | line upgrade | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-09-01 | 2023-12-21 | 1.136
178 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | szlak Osielec - Jordanów | 1 | 17.6 | 23.752 | line upgrade | 115 | 24 | 2760 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 23 | traffic interruption – single-track line | 2023-03-01 | 2023-06-23 | 1.136
179 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | szlak Osielec - Jordanów | 1 | 17.6 | 23.752 | line upgrade | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption – single-track line | 2023-09-01 | 2023-12-21 | 1.136
180 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | stacja Jordanów | 1, 3 | 23.752 | 25.335 | line upgrade | 121 | 24 | 2904 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic interruption | 2023-03-01 | 2023-06-29 | 1.136
181 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | stacja Jordanów | 1, 3 | 23.752 | 25.335 | line upgrade | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-09-01 | 2023-12-21 | 1.136
182 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | Skawa | 1, 3 | 27.386 | 28.912 | line upgrade | 149 | 24 | 3576 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic interruption | 2023-02-01 | 2023-06-29 | 1.136
183 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | Skawa | 1, 3 | 27.386 | 28.912 | line upgrade | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-09-01 | 2023-12-29 | 1.136
184 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | Skawa - Chabówka | 1 | 28.912 | 34.114 | line upgrade | 149 | 24 | 3576 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic interruption – single-track line | 2023-02-01 | 2023-06-29 | 1.136
185 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | Skawa - Chabówka | 1 | 28.912 | 34.114 | line upgrade | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption – single-track line | 2023-09-01 | 2023-12-29 | 1.136
186 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | stacja Chabówka | 1 | 34.114 | 35.313 | line upgrade | 115 | 24 | 2760 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 23 | traffic interruption | 2023-03-01 | 2023-06-23 | 1.136
187 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | stacja Chabówka | 1 | 34.114 | 35.313 | line upgrade | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-09-01 | 2023-12-21 | 1.136
188 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | Maków Podhalański-Osielec | 1 | 7.761 | 16.116 | line upgrade | 115 | 24 | 2760 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 23 | traffic interruption – single-track line | 2023-03-01 | 2023-06-23 | 1.136
189 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | Maków Podhalański-Osielec | 1 | 7.761 | 16.116 | line upgrade | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption – single-track line | 2023-09-01 | 2023-12-21 | 1.136
190 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Chabówka | 1,2,4,5,6,7,8,9,10,11,11a,12,12a,13,14,15,16,18 | -0.334 | 0.858 | line upgrade | 149 | 24 | 3576 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic interruption | 2023-02-01 | 2023-06-29 | 1.136
191 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Chabówka | 1,2,4,5,6,7,8,9,10,11,11a,12,12a,13,14,15,16,18 | -0.334 | 0.858 | line upgrade | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-09-01 | 2023-12-29 | 1.136
192 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Chabówka - Raba Wyżna | 1 | 0.858 | 4.733 | line upgrade | 149 | 24 | 3576 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic interruption – single-track line | 2023-02-01 | 2023-06-29 | 1.136
193 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Chabówka - Raba Wyżna | 1 | 0.858 | 4.733 | line upgrade | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption – single-track line | 2023-09-01 | 2023-12-29 | 1.136
194 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Sieniawa | 1,2,3,5 | 10.026 | 11.791 | line upgrade | 149 | 24 | 3576 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic interruption | 2023-02-01 | 2023-06-29 | 1.136
195 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Sieniawa | 1,2,3,5 | 10.026 | 11.791 | line upgrade | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-09-01 | 2023-12-29 | 1.136
196 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Sieniawa - Lasek | 1 | 11.791 | 17.505 | line upgrade | 149 | 24 | 3576 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic interruption – single-track line | 2023-02-01 | 2023-06-29 | 1.136
197 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Sieniawa - Lasek | 1 | 11.791 | 17.505 | line upgrade | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption – single-track line | 2023-09-01 | 2023-12-29 | 1.136
198 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Lasek | 1,2,3 | 17.505 | 18.797 | line upgrade | 149 | 24 | 3576 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic interruption | 2023-02-01 | 2023-06-29 | 1.136
199 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Lasek | 1,2,3 | 17.505 | 18.797 | line upgrade | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-09-01 | 2023-12-29 | 1.136
200 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Lasek - Nowy Targ | 1 | 18.797 | 21.864 | line upgrade | 149 | 24 | 3576 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic interruption – single-track line | 2023-02-01 | 2023-06-29 | 1.136
201 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Lasek - Nowy Targ | 1 | 18.797 | 21.864 | line upgrade | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption – single-track line | 2023-09-01 | 2023-12-29 | 1.136
202 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Nowy Targ | 1,2,3,4,5,6,17,7a,7b,11,13,15,19,21 | 21.864 | 23.611 | line upgrade | 149 | 24 | 3576 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic interruption | 2023-02-01 | 2023-06-29 | 1.136
203 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Nowy Targ | 1,2,3,4,5,6,17,7a,7b,11,13,15,19,21 | 21.864 | 23.611 | line upgrade | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-09-01 | 2023-12-29 | 1.136
204 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Nowy Targ-Szaflary | 1 | 23.611 | 25.511 | line upgrade | 149 | 24 | 3576 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic interruption – single-track line | 2023-02-01 | 2023-06-29 | 1.136
205 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Nowy Targ-Szaflary | 1 | 23.611 | 25.511 | line upgrade | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption – single-track line | 2023-09-01 | 2023-12-29 | 1.136
206 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Szaflary | 1,2,3,4 | 25.511 | 27.318 | line upgrade | 149 | 24 | 3576 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic interruption | 2023-02-01 | 2023-06-29 | 1.136
207 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Szaflary | 1,2,3,4 | 25.511 | 27.318 | line upgrade | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-09-01 | 2023-12-29 | 1.136
208 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Szaflary-Biały Dunajec | 1 | 27.318 | 32.88 | line upgrade | 149 | 24 | 3576 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic interruption – single-track line | 2023-02-01 | 2023-06-29 | 1.136
209 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Szaflary-Biały Dunajec | 1 | 27.318 | 32.88 | line upgrade | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption – single-track line | 2023-09-01 | 2023-12-29 | 1.136
210 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Biały Dunajec | 1,2,3,4 | 32.88 | 34.736 | line upgrade | 149 | 24 | 3576 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic interruption | 2023-02-01 | 2023-06-29 | 1.136
211 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Biały Dunajec | 1,2,3,4 | 32.88 | 34.736 | line upgrade | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-09-01 | 2023-12-29 | 1.136
212 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Biały Dunajec - Poronin | 1 | 34.736 | 37.117 | line upgrade | 149 | 24 | 3576 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic interruption – single-track line | 2023-02-01 | 2023-06-29 | 1.136
213 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Biały Dunajec - Poronin | 1 | 34.736 | 37.117 | line upgrade | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption – single-track line | 2023-09-01 | 2023-12-29 | 1.136
214 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Statcja Poronin | 1,2,3,4 | 37.117 | 38.433 | line upgrade | 149 | 24 | 3576 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic interruption | 2023-02-01 | 2023-06-29 | 1.136
215 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Statcja Poronin | 1,2,3,4 | 37.117 | 38.433 | line upgrade | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-09-01 | 2023-12-29 | 1.136
216 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Poronin-Zakopane | 1 | 37.75 | 41.778 | line upgrade | 149 | 24 | 3576 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic interruption – single-track line | 2023-02-01 | 2023-06-29 | 1.136
217 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Poronin-Zakopane | 1 | 37.75 | 41.778 | line upgrade | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption – single-track line | 2023-09-01 | 2023-12-29 | 1.136
218 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Raba Wyżna | 1,2,3,5 | 4.773 | 6.442 | line upgrade | 149 | 24 | 3576 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic interruption | 2023-02-01 | 2023-06-29 | 1.136
219 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Raba Wyżna | 1,2,3,5 | 4.773 | 6.442 | line upgrade | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-09-01 | 2023-12-29 | 1.136
220 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Zakopane | 1,2,3,4,5,6,21,23 | 41.778 | 43.451 | line upgrade | 343 | 24 | 8232 | traffic interruption | no limit |  | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2023-01-01 | 2023-12-31 | 1.136
221 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Raba Wyżna - Sieniawa | 1 | 6.442 | 10.026 | line upgrade | 149 | 24 | 3576 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 29 | traffic interruption – single-track line | 2023-02-01 | 2023-06-29 | 1.136
222 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Raba Wyżna - Sieniawa | 1 | 6.442 | 10.026 | line upgrade | 100 | 24 | 2400 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption – single-track line | 2023-09-01 | 2023-12-29 | 1.136
223 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/7 | Chabówka - Rabka Zaryte | 1 | 0.576 | 5.142 | line upgrade | 364 | 24 | 8736 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption – single-track line | 2022-11-06 | 2024-12-07
224 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/7 | Mszana Dolna | 1.3 | 14.393 | 15.091 | line upgrade | 182 | 24 | 4368 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 20; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-06-11 | 2025-06-14
225 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/7 | Mszana Dolna - Tymbark | 1 | 15.091 | 36.35 | line upgrade | 182 | 24 | 4368 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 20; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption – single-track line | 2023-06-11 | 2025-06-14
226 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/7 | Tymbark - Limanowa | 1 | 37.352 | 46.768 | line upgrade | 273 | 24 | 6552 | traffic interruption | no limit |  |  |  | 20 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption – single-track line | 2023-03-12 | 2026-03-14
227 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/7 | Limanowa | 1,2,3,3a,4 | 46.768 | 47.569 | line upgrade | 273 | 24 | 6552 | traffic interruption | no limit |  |  |  | 20 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2023-03-12 | 2026-03-14
228 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/7 | Rabka Zaryte | 1.3 | 5.142 | 5.841 | line upgrade | 364 | 24 | 8736 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2022-11-06 | 2024-12-07
229 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/7 | Rabka Zaryte - Mszana Dolna | 1 | 5.841 | 14.393 | line upgrade | 364 | 24 | 8736 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption – single-track line | 2022-11-06 | 2025-06-14
230 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/7 | Marcinkowice | 1, 2, 3, 3a, 4 | 66.969 | 67.81 | line upgrade | 364 | 24 | 8736 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2022-11-06 | 2024-12-07
231 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/7 | Marcinkowice - Nowy Sącz | 1 | 67.81 | 76.652 | line upgrade | 364 | 24 | 8736 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption – single-track line | 2022-11-06 | 2024-12-07
232 | 3 | 123 | HURKO - KRÓWNIKI (SZ) | IRR3/6 | stacja Krówniki | 104 | 1.761 | 2.522 | surface replacement | 40 | 24 | 960 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months V: 3; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 7 | traffic on active track at the station | 2023-05-29 | 2023-07-07 | 4.025
233 | 3 | 133 | DĄBROWA GÓRNICZA ZĄBKOWICE - KRAKÓW GŁÓWNY | IRR3/1 | Szlak Trzebinia - Krzeszowice | 1.2 | 30.4 | 45.097 | night-time line closure | 353 | 4 | 1412 | traffic interruption | no limit | 10 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2022-12-22 | 2024-03-29 | 1.075
234 | 3 | 133 | DĄBROWA GÓRNICZA ZĄBKOWICE - KRAKÓW GŁÓWNY | IRR3/1 | Szlak Trzebinia - Krzeszowice | 1.2 | 30.4 | 45.097 | construction of the Młoszowa and Wola Filipowska road viaducts | 4 | 24 | 96 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 4 | traffic interruption | 2023-07-14 | 2023-07-17 | 1.075
235 | 3 | 133 | DĄBROWA GÓRNICZA ZĄBKOWICE - KRAKÓW GŁÓWNY | IRR3/1 | Szlak Trzebinia - Krzeszowice | 1.2 | 30.4 | 45.097 | construction of the Młoszowa and Wola Filipowska road viaducts | 4 | 24 | 96 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 4 | traffic interruption | 2023-07-28 | 2023-07-31 | 1.075
236 | 3 | 133 | DĄBROWA GÓRNICZA ZĄBKOWICE - KRAKÓW GŁÓWNY | IRR3/1 | Szlak Trzebinia - Krzeszowice | 1.2 | 30.4 | 45.097 | construction of the Młoszowa and Wola Filipowska road viaducts | 4 | 24 | 96 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 4 | traffic interruption | 2023-08-11 | 2023-08-14 | 1.075
237 | 3 | 133 | DĄBROWA GÓRNICZA ZĄBKOWICE - KRAKÓW GŁÓWNY | IRR3/1 | Szlak Trzebinia - Krzeszowice | 1.2 | 30.4 | 45.097 | construction of the Młoszowa and Wola Filipowska road viaducts | 4 | 24 | 96 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 4 | traffic interruption | 2023-08-25 | 2023-08-28 | 1.075
238 | 3 | 133 | DĄBROWA GÓRNICZA ZĄBKOWICE - KRAKÓW GŁÓWNY | IRR3/1 | Szlak Krzeszowice-Zabierzów | 1.2 | 45.097 | 57.515 | night-time line closure | 353 | 4 | 1412 | traffic interruption | no limit | 10 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2022-12-22 | 2024-03-29 | 1.075
239 | 3 | 133 | DĄBROWA GÓRNICZA ZĄBKOWICE - KRAKÓW GŁÓWNY | IRR3/1 | Szlak Krzeszowice-Zabierzów | 1.2 | 45.097 | 57.515 | construction of the Pisary and Niegoszowice road viaducts | 4 | 24 | 96 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 4 | traffic interruption | 2023-07-21 | 2023-07-24 | 1.075
240 | 3 | 133 | DĄBROWA GÓRNICZA ZĄBKOWICE - KRAKÓW GŁÓWNY | IRR3/1 | Szlak Krzeszowice-Zabierzów | 1.2 | 45.097 | 57.515 | construction of the Pisary and Niegoszowice road viaducts | 4 | 24 | 96 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 4 | traffic interruption | 2023-08-04 | 2023-08-07 | 1.075
241 | 3 | 133 | DĄBROWA GÓRNICZA ZĄBKOWICE - KRAKÓW GŁÓWNY | IRR3/1 | Szlak Krzeszowice-Zabierzów | 1.2 | 45.097 | 57.515 | construction of the Pisary and Niegoszowice road viaducts | 4 | 24 | 96 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 4 | traffic interruption | 2023-08-18 | 2023-08-21 | 1.075
242 | 3 | 133 | DĄBROWA GÓRNICZA ZĄBKOWICE - KRAKÓW GŁÓWNY | IRR3/1 | Szlak Krzeszowice-Zabierzów | 1.2 | 45.097 | 57.515 | construction of the Pisary and Niegoszowice road viaducts | 4 | 24 | 96 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 4 | traffic interruption | 2023-09-01 | 2023-09-04 | 1.075
243 | 3 | 133 | DĄBROWA GÓRNICZA ZĄBKOWICE - KRAKÓW GŁÓWNY | IRR3/1 | Szlak Zabierzów - Kraków Mydlniki | 1.2 | 57.515 | 63.304 | night-time line closure | 299 | 4 | 1196 | traffic interruption | no limit | 10 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 16 |  |  | traffic interruption | 2022-12-22 | 2023-10-16 | 1.075
244 | 3 | 624 | KRAKÓW ZABŁOCIE - KRAKÓW BONARKA | IRR3/3 | Kraków Zabłocie - Kraków Podgórze | 1 | 0 | 1.053 | replacement of surface, contact line, construction of flyover, engineering structures, viaducts lk 91 - W11(km 2.631); W12(km 2.956); W13(3.019) | 202 | 24 | 4848 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XII: 21; Number of planned closing days in the timetable 2022/2023 in individual months I: 31; Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30 | single-track two-way traffic on the active track | 2020-05-29 | 2023-06-30 | 1.094
245 | 3 | 624 | KRAKÓW ZABŁOCIE - KRAKÓW BONARKA | IRR3/3 | Kraków Zabłocie - Kraków Podgórze | 2 | 0.01 | 1.053 | decommissioning of rz 629, track construction, tamping, contact line adjustment | 46 | 24 | 1104 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 15 | single-track two-way traffic on the active track | 2023-07-01 | 2023-08-15 | 1.094
246 | 4 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR4/4 | stacja Czechowice Dziedzice | 1,3,5,7,9,11,13,15,17,19,21 | 45.5 | 47 | upgrade | 248 | 24 | 5952 | no limit | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 15 |  |  |  |  | traffic on active track at the station | 2022-01-27 | 2023-08-15 | 1.152
247 | 4 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR4/4 | stacja Zebrzydowice | 6, 8, 7-15, 100-109 | 76 | 77.8 | upgrade | 34 | 24 | 816 | 60 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XI: 25; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-11-06 | 2023-12-17
248 | 4 | 127 | RADZIONKÓW - TARNOWSKIE GÓRY TGB T3 | IRR4/5 | Szlak Radzionków - Nakło | T3 | 28.12 | 30.143 | Closing the tangent line | 253 | 24 | 6072 | traffic interruption | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption – single-track line | 2023-04-01 | 2024-03-31 | 1.095
249 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | stacja Chorzów Stary | 2, 22,24,26, 6,10,12,14 | 11.68 | 12.82 | surface replacement, construction of engineering structures, replacement of contact line | 270 | 24 | 6480 | 40 km/h | no limit |  |  |  | 17 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2023-03-15 | 2024-03-15 | 1.095
250 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Chorzów Stary - Bytom | 1 | 12.85 | 16.85 | transport of materials on the active track | 253 | 5 | 1265 | traffic interruption | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2023-04-01 | 2024-03-31 | 1.095
251 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Chorzów Stary - Bytom | 2 | 12.85 | 16.85 | surface replacement, construction of engineering structures, replacement of contact line | 253 | 24 | 6072 | 50 km/h | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | single-track two-way traffic on the active track | 2023-04-01 | 2024-03-31 | 1.095
252 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Rusiec Łódzki - Chociw Łaski | 1 | 136.465 | 146.56 | transport of materials on the active track | 213 | 4 | 852 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 29 | traffic interruption | 2023-03-01 | 2023-09-29 | 1.095
253 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Rusiec Łódzki - Chociw Łaski | 1 | 136.465 | 146.56 | works on the bridge at km 138.402 | 72 | 24 | 1728 | 30 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 2; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | single-track two-way traffic on the active track | 2023-09-29 | 2024-04-30 | 1.095
254 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Rusiec Łódzki - Chociw Łaski | 2 | 136.465 | 146.56 | works on the bridge at km 138.402 | 213 | 24 | 5112 | 30 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 29 | single-track two-way traffic on the active track | 2023-03-01 | 2023-09-29 | 1.095
255 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Rusiec Łódzki - Chociw Łaski | 2 | 136.465 | 146.56 | transport of materials on the active track | 69 | 4 | 276 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months X: 30; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-10-02 | 2024-04-30 | 1.095
256 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | stacja Bytom | 1, 3,5,7,11,13, 1a, 2a, 3a, 4a, 5a, 7a, 8a, 9a, 9b, 11a, 11b, 13a, 13b, 49a, | 16.85 | 18.55 | surface replacement, construction of engineering structures, replacement of contact line | 364 | 24 | 8736 | 40 km/h | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2022-09-12 | 2024-03-11 | 1.095
257 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | stacja Bytom | 2, 4,6,9,10,16,18, 20,24,26,28,30,32, 34, 36, 38, 40, 42 | 16.85 | 18.55 | surface replacement, construction of engineering structures, replacement of contact line | 364 | 24 | 8736 | 40 km/h | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2022-09-12 | 2024-03-11 | 1.095
258 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | stacja Bytom Karb | 2 | 20.15 | 21.04 | transport of materials on the active track | 253 | 5 | 1265 | 40 km/h | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2023-04-01 | 2024-03-31 | 1.095
259 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | stacja Bytom Karb | 1, 3,3a, 3b | 20.4 | 21.04 | surface replacement, construction of engineering structures, replacement of contact line | 253 | 24 | 6072 | 40 km/h | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2023-04-01 | 2024-03-31 | 1.095
260 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Bytom Karb - Bytom Północny | 1 | 21.04 | 26.8 | surface replacement, construction of engineering structures, replacement of contact line | 253 | 24 | 6072 | 50 km/h | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | single-track two-way traffic on the active track | 2023-04-01 | 2024-03-31 | 1.095
261 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Bytom Karb - Bytom Północny | 2 | 21.04 | 26.8 | delivery of materials on active track | 253 | 5 | 1265 | traffic interruption | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2023-04-01 | 2024-03-31 | 1.095
262 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Bytom Północny - Radzionków | 1 | 21.04 | 26.8 | surface replacement, construction of engineering structures, replacement of contact line | 364 | 24 | 8736 | no limit | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | single-track two-way traffic on the active track | 2022-09-04 | 2023-12-31 | 1.095
263 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Bytom Północny - Radzionków | 2 | 21.04 | 26.8 | delivery of materials on active track | 364 | 5 | 1820 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2022-09-04 | 2023-12-31 | 1.095
264 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | stacja Radzionków | 1, 3, 5 | 26.8 | 28 | surface replacement, construction of engineering structures, replacement of contact line | 253 | 24 | 6072 | 40 km/h | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2023-04-01 | 2024-03-31 | 1.095
265 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | stacja Radzionków | 2 | 26.8 | 28 | transport of materials on the active track | 253 | 5 | 1265 | 40 km/h | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2023-04-01 | 2024-03-31 | 1.095
266 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Radzionków - Nakło Śląskie | 1 | 28 | 29.5 | surface replacement, construction of engineering structures, replacement of contact line | 253 | 24 | 6072 | 50 km/h | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | single-track two-way traffic on the active track | 2023-04-01 | 2024-03-31 | 1.095
267 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Radzionków - Nakło Śląskie | 2 | 28 | 29.5 | delivery of materials on active track | 253 | 5 | 1265 | traffic interruption | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2023-04-01 | 2024-03-31 | 1.095
268 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Chorzów Batory - Chorzów Miasto | 1.2 | 6.115 | 8.15 | surface replacement, construction of engineering structures, replacement of contact line | 364 | 24 | 8736 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2022-03-14 | 2024-01-17 | 1.095
269 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | stacja Chorzów Miasto | 1,2,4,6,8,10 | 8.15 | 9.4 | surface replacement, construction of engineering structures, replacement of contact line | 364 | 24 | 8736 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2022-03-14 | 2024-01-17 | 1.095
270 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Chorzów Miasto - Chorzów Stary | 1.2 | 9.4 | 11.68 | surface replacement, construction of engineering structures, replacement of contact line | 364 | 24 | 8736 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2022-03-14 | 2024-01-17 | 1.095
271 | 4 | 135 | GLIWICE ŁABĘDY - PYSKOWICE | IRR4/5 | szlak Gliwice Łabędy - Pyskowice | 2 | -0.219 | 4.744 | Reconstruction of track systems including contact line and traffic control, demolition and construction of engineering structures | 52 | 24 | 1248 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months X: 13; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | single-track two-way traffic on the active track | 2023-10-19 | 2023-12-18
272 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | Kobiór - Pszczyna | 1 | 25.556 | 35.918 | technology commissioning activities | 168 | 4 | 672 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months III: 19; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 27 | traffic interruption | 2023-03-13 | 2023-08-27
273 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | Kobiór - Pszczyna | 1 | 25.556 | 35.918 | upgrade | 105 | 24 | 2520 | 60 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 5; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | single-track two-way traffic on the active track | 2023-08-27 | 2024-03-23
274 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | Kobiór - Pszczyna | 2 | 25.556 | 35.918 | upgrade | 168 | 24 | 4032 | 60 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months III: 19; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 27 | single-track two-way traffic on the active track | 2023-03-13 | 2023-08-27
275 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | Kobiór - Pszczyna | 2 | 25.556 | 35.918 | technology commissioning activities | 105 | 4 | 420 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 5; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-08-27 | 2024-03-23
276 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | stacja Pszczyna | 1 | 35.25 | 36.69 | upgrade | 76 | 24 | 1824 | 60 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 6; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-09-25 | 2024-03-23
277 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | stacja Pszczyna | 2 | 35.5 | 34 | upgrade | 168 | 24 | 4032 | 60 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months III: 19; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 27 | traffic on active track at the station | 2023-03-13 | 2023-08-27
278 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | Pszczyna - Most Wisła | 1 | 36.62 | 41.8 | technology commissioning activities | 248 | 4 | 992 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 15 |  |  |  |  | traffic interruption | 2021-12-20 | 2023-08-15 | 1.152
279 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | Pszczyna - Most Wisła | 2 | 36.62 | 41.8 | upgrade | 248 | 24 | 5952 | no limit | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 15 |  |  |  |  | single-track two-way traffic on the active track | 2021-12-20 | 2023-08-15 | 1.152
280 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | podg Most Wisła - Czechowice Dziedzice | 1.2 | 42.1 | 45 | upgrade | 248 | 24 | 5952 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 15 |  |  |  |  | traffic interruption | 2021-12-20 | 2023-08-15 | 1.152
281 | 4 | 148 | PSZCZYNA - RYBNIK | IRR4/4 | Pszczyna - Radostowice | 1 | 0 | 7.621 | upgrade | 16 | 24 | 384 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 16 | traffic interruption – single-track line | 2023-09-11 | 2023-09-26
282 | 4 | 148 | PSZCZYNA - RYBNIK | IRR4/4 | stacja Pszczyna | 3 | -0.632 | 2.75 | upgrade | 76 | 24 | 1824 | 60 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 6; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-09-25 | 2024-03-23
283 | 4 | 161 | KATOWICE SZOPIENICE PÓŁNOCNE - CHORZÓW STARY | IRR4/1 | Katowice Szopienice Płn. | 1, 3, 3a, 5,7,9,11,13,15,39,41 | 0 | 1.45 | end-to-end reconstruction of KSz Płn. station STAGE 3 | 232 | 24 | 5568 | 40 km/h | no limit |  | 8 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 12 |  |  |  | traffic on active track at the station | 2023-01-24 | 2023-09-12 | 1.092
284 | 4 | 161 | KATOWICE SZOPIENICE PÓŁNOCNE - CHORZÓW STARY | IRR4/1 | Katowice Szopienice Płn. | 2,4,6 | 0 | 0.8 | alterations to contact lines, sheet piling, delivery and unloading of construction materials STAGE 3,4, SUB-STAGE 1 | 276 | 4 | 1656 | no limit | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 12 |  |  |  | traffic on active track at the station | 2021-11-16 | 2023-09-12 | 1.092
285 | 4 | 161 | KATOWICE SZOPIENICE PÓŁNOCNE - CHORZÓW STARY | IRR4/5 | Siemianowice Śląskie - Chorzów Stary | 1 | 11.55 | 11.77 | Closing the tangent line | 9 | 24 | 216 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | single-track two-way traffic on the active track | 2023-12-01 | 2024-08-31 | 1.095
286 | 4 | 165 | BYTOM BOBREK - BYTOM KARB | IRR4/5 | Bytom Bobrek - Bytom Karb | 1 | 1.185 | 1.285 | Closing the tangent line | 9 | 24 | 216 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | single-track two-way traffic on the active track | 2023-12-01 | 2024-08-31 | 1.095
287 | 4 | 167 | SZOBISZOWICE - GLIWICE PORT | IRR4/5 | stacja Gliwice Port | 1 | 3.386 | 3.81 | Reconstruction of track systems including railway traffic control | 5 | 24 | 120 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XII: 5 | traffic on active track at the station | 2023-12-05 | 2023-12-18
288 | 4 | 171 | DĄBROWA GÓRNICZA TOWAROWA - PANEWNIK | IRR4/4 | K-ce Muchowiec - Podg. Panewnik | 2 | 40.335 | 41.5 | upgrade | 264 | 24 | 6336 | 60 km/h | no limit |  |  |  | 20 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 |  | single-track two-way traffic on the active track | 2023-03-12 | 2023-11-30
289 | 4 | 182 | TARNOWSKIE GÓRY - ZAWIERCIE | IRR4/1 | szlak Poręba -Zawiercie | 1 | 37.184 | 43.1 | For the following disciplines: track, 1KV power, contact line, Railway Traffic Controlling system [srk] and DSAT, traveller facilities, power telecommunications. Engineering structures | 243 | 24 | 5832 | traffic interruption | no limit |  | 16 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 15 |  |  |  | traffic interruption – single-track line | 2023-01-16 | 2023-09-15 | 1.109
290 | 4 | 182 | TARNOWSKIE GÓRY - ZAWIERCIE | IRR4/1 | Stacja Zawiercie | 7,9,21 | 43.004 | 45.393 | For the following disciplines: track, 1KV power, contact line, Railway Traffic Controlling system [srk] and DSAT, traveller facilities, power telecommunications. Engineering structures | 279 | 24 | 6696 | no limit | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 15 |  |  |  | traffic on active track at the station | 2021-07-16 | 2023-09-15 | 1.109
291 | 4 | 654 | SZABELNIA - KATOWICE SZOPIENICE PÓŁNOCNE | IRR4/4 | Szabelnia - Katowice Szopienice Północne | 1 | 0.15 | 1.29 | upgrade | 253 | 24 | 6072 | traffic interruption | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption – single-track line | 2023-04-01 | 2024-01-01
292 | 4 | 657 | KATOWICE SZOPIENICE PÓŁNOCNE - KATOWICE MUCHOWIEC KMA | IRR4/1 | Katowice Szopienice Płn. -podg Stawiska | 1 | 0 | 0.106 | alterations to the contact line, driving of sheet piling, delivery and unloading of construction materials. STAGE 3,4 SUB-STAGE 1 | 232 | 4 | 1392 | traffic interruption | no limit |  | 8 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 12 |  |  |  | traffic interruption – single-track line | 2023-01-24 | 2023-09-12 | 1.092
293 | 4 | 657 | KATOWICE SZOPIENICE PÓŁNOCNE - KATOWICE MUCHOWIEC KMA | IRR4/4 | Katowice Szopienice Północne - Stawiska | 1 | 0.153 | 0.97 | upgrade | 253 | 24 | 6072 | traffic interruption | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption – single-track line | 2023-04-01 | 2024-01-01
294 | 4 | 705 | ZAWIERCIE R125 - ZAWIERCIE R97 | IRR4/1 | Stacja Zawiercie | 25 | 0 | 1.292 | For the following disciplines: track, 1KV power, contact line, Railway Traffic Controlling system [srk] and DSAT, traveller facilities, power telecommunications. Engineering structures | 279 | 24 | 6696 | no limit | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 15 |  |  |  | traffic on active track at the station | 2021-01-11 | 2023-09-15 | 1.109
295 | 1 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/1 | Sochaczew-Stara Wieś | 1 lub 2 | 60.5 | 109 | rectification of defects from final acceptance reports and defects | 364 | 4 | 1456 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic interruption | 2022-03-14 | 2023-12-11 | 1.106
296 | 8 | 351 | POZNAŃ GŁÓWNY - SZCZECIN GŁÓWNY | IRR5/5 | Podlesiec - Dobiegniew | 1 | 97.148 | 106.605 | Line upgrade | 212 | 24 | 5088 | no limit | no limit |  |  |  | 16 | 30 | 31 | 19 | 31 | 31 | 30 | 24 |  |  | single-track two-way traffic on the active track | 2023-03-15 | 2023-10-24 | 1.153
297 | 8 | 351 | POZNAŃ GŁÓWNY - SZCZECIN GŁÓWNY | IRR5/5 | Bierzwnik - Rębusz | 1 | 116.55 | 128.68 | Unloading of materials, works on Railway Traffic Controlling system [srk] | 28 | 24 | 672 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months X: 5; Number of planned closing days in the timetable 2022/2023 in individual months XI: 23 | single-track two-way traffic on the active track | 2023-10-27 | 2023-11-23 | 1.153
298 | 8 | 351 | POZNAŃ GŁÓWNY - SZCZECIN GŁÓWNY | IRR5/5 | Bierzwnik - Rębusz | 2 | 116.55 | 128.68 | Unloading of materials, works on Railway Traffic Controlling system [srk] | 28 | 6 | 168 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months X: 5; Number of planned closing days in the timetable 2022/2023 in individual months XI: 23 | traffic interruption | 2023-10-27 | 2023-11-23 | 1.153
299 | 8 | 351 | POZNAŃ GŁÓWNY - SZCZECIN GŁÓWNY | IRR5/5 | Stacja Rębusz | 1 | 116.55 | 128.68 | Track works, works on Railway Traffic Controlling system [srk] | 28 | 24 | 672 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months X: 5; Number of planned closing days in the timetable 2022/2023 in individual months XI: 23 | traffic on active track at the station | 2023-10-27 | 2023-11-23 | 1.153
300 | 8 | 351 | POZNAŃ GŁÓWNY - SZCZECIN GŁÓWNY | IRR5/5 | Stacja Rębusz | 2 | 116.577 | 127 | Line upgrade | 28 | 6 | 168 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months X: 5; Number of planned closing days in the timetable 2022/2023 in individual months XI: 23 | traffic on active track at the station | 2023-10-27 | 2023-11-23 | 1.153
301 | 8 | 351 | POZNAŃ GŁÓWNY - SZCZECIN GŁÓWNY | IRR5/5 | Rębusz - Słonice | 1 | 121.2 | 127 | Line upgrade | 223 | 24 | 5352 | 50 km/h | no limit |  |  |  |  | 16 | 31 | 30 | 31 | 31 | 30 | 31 | 23 |  | single-track two-way traffic on the active track | 2023-04-15 | 2023-11-23 | 1.153
302 | 8 | 351 | POZNAŃ GŁÓWNY - SZCZECIN GŁÓWNY | IRR5/5 | Rębusz - Słonice | 2 | 121.2 | 127 | Line upgrade | 223 | 6 | 1338 | traffic interruption | no limit |  |  |  |  | 16 | 31 | 30 | 31 | 31 | 30 | 31 | 23 |  | traffic interruption | 2023-04-15 | 2023-11-23 | 1.153
303 | 8 | 351 | POZNAŃ GŁÓWNY - SZCZECIN GŁÓWNY | IRR5/5 | Rębusz - Słonice | 2 | 121.2 | 127 | Line upgrade | 16 | 24 | 384 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XI: 7; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | single-track two-way traffic on the active track | 2023-11-24 | 2023-12-18 | 1.153
304 | 8 | 351 | POZNAŃ GŁÓWNY - SZCZECIN GŁÓWNY | IRR5/5 | Rębusz - Słonice | 1 | 121.2 | 127 | Line upgrade | 16 | 6 | 96 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XI: 7; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-11-24 | 2023-12-18 | 1.153
305 | 8 | 351 | POZNAŃ GŁÓWNY - SZCZECIN GŁÓWNY | IRR5/5 | szlak Słonice- Choszczno | 1 | 121.574 | 128.68 | Line upgrade | 125 | 6 | 750 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XII: 21; Number of planned closing days in the timetable 2022/2023 in individual months I: 31; Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 14 | traffic interruption | 2023-02-17 | 2023-06-30 | 1.153
306 | 8 | 351 | POZNAŃ GŁÓWNY - SZCZECIN GŁÓWNY | IRR5/5 | szlak Słonice- Choszczno | 2 | 121.574 | 128.68 | Line upgrade | 125 | 24 | 3000 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XII: 21; Number of planned closing days in the timetable 2022/2023 in individual months I: 31; Number of planned closing days in the timetable 2022/2023 in individual months II: 28; Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 14 | single-track two-way traffic on the active track | 2023-02-17 | 2023-06-30 | 1.153
307 | 8 | 351 | POZNAŃ GŁÓWNY - SZCZECIN GŁÓWNY | IRR5/5 | Stacja Słonice tor nr 1 i 3 | 1;3 | 127 | 128.588 | Line upgrade | 223 | 24 | 5352 | 50 km/h | no limit |  |  |  |  | 16 | 31 | 30 | 31 | 31 | 30 | 31 | 23 |  | traffic on active track at the station | 2023-04-15 | 2023-11-23 | 1.153
308 | 8 | 351 | POZNAŃ GŁÓWNY - SZCZECIN GŁÓWNY | IRR5/5 | Stacja Słonice tor nr 2 i 4 | 2;4 | 127 | 128.588 | Line upgrade | 223 | 6 | 1338 | traffic interruption | no limit |  |  |  |  | 16 | 31 | 30 | 31 | 31 | 30 | 31 | 23 |  | traffic interruption | 2023-04-15 | 2023-11-23 | 1.153
309 | 8 | 351 | POZNAŃ GŁÓWNY - SZCZECIN GŁÓWNY | IRR5/5 | szlak Słonice- Choszczno | 2 | 121.574 | 128.68 | Line upgrade | 58 | 24 | 1392 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IV: 16; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 11 | single-track two-way traffic on the active track | 2021-04-15 | 2023-06-11 | 1.153
310 | 8 | 351 | POZNAŃ GŁÓWNY - SZCZECIN GŁÓWNY | IRR5/5 | szlak Słonice- Choszczno | 1 | 128.53 | 128.68 | Line upgrade | 58 | 6 | 348 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IV: 16; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 11 | traffic interruption | 2023-04-15 | 2023-06-11 | 1.153
311 | 8 | 351 | POZNAŃ GŁÓWNY - SZCZECIN GŁÓWNY | IRR5/5 | Stargard | 1 | 171.12 | 176.54 | Line upgrade | 264 | 24 | 6336 | 40 km/h | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 |  |  |  |  | traffic on active track at the station | 2020-03-16 | 2023-08-31 | 1.086
312 | 8 | 351 | POZNAŃ GŁÓWNY - SZCZECIN GŁÓWNY | IRR5/5 | Stargard | 60 | 171.12 | 176.54 | Line upgrade | 375 | 24 | 9000 | 40 km/h | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 20 | traffic on active track at the station | 2022-12-11 | 2023-12-20 | 1.086
313 | 8 | 351 | POZNAŃ GŁÓWNY - SZCZECIN GŁÓWNY | IRR5/5 | Stargard | 66 | 171.12 | 176.54 | Line upgrade | 375 | 24 | 9000 | 40 km/h | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 20 | traffic on active track at the station | 2022-12-11 | 2023-12-20 | 1.086
314 | 8 | 351 | POZNAŃ GŁÓWNY - SZCZECIN GŁÓWNY | IRR5/5 | Stargard | 8 | 171.12 | 176.54 | Line upgrade | 375 | 24 | 9000 | 40 km/h | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 20 | traffic on active track at the station | 2022-12-11 | 2023-12-20 | 1.086
315 | 8 | 351 | POZNAŃ GŁÓWNY - SZCZECIN GŁÓWNY | IRR5/5 | Stargard | 3 | 172.45 | 173.307 | Line upgrade | 375 | 24 | 9000 | 40 km/h | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 20 | traffic on active track at the station | 2022-12-11 | 2023-12-20 | 1.086
316 | 8 | 351 | POZNAŃ GŁÓWNY - SZCZECIN GŁÓWNY | IRR5/5 | Stargard | 5 | 172.45 | 173.307 | Line upgrade | 375 | 24 | 9000 | 40 km/h | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 20 | traffic on active track at the station | 2022-12-11 | 2023-12-20 | 1.086
317 | 7 | 352 | SWARZĘDZ - POZNAŃ STAROŁĘKA | IRS5/3 | st. Swarzędz | 2 | 4.1 | 5.35 | renovation | 38 | 24 | 912 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XI: 29; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-11-02 | 2024-03-20 | 1.117
318 | 7 | 394 | POZNAŃ KRZESINY - KOBYLNICA | IRS5/3 | szlak st. Poznań Franowo - p.odg. Stary Młyn - p.odg. Zieliniec | 1 | 4.85 | 12.05 | renovation | 38 | 24 | 912 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XI: 29; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | single-track two-way traffic on the active track | 2023-11-02 | 2024-03-20 | 1.117
319 | 1 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Włochy | 1S, 2S | 3.082 | 6.804 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 35 | 6 | 210 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XI: 26; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-11-05 | 2023-12-09 | 1.093
320 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | Warszawa Rembertów - Sulejówek Miłosna | 1 | 16.2 | 16.4 | tunnel construction | 16 | 24 | 384 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months X: 16 | single-track two-way traffic on the active track | 2023-10-02 | 2023-10-17 | 1.066
321 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | Warszawa Rembertów - Sulejówek Miłosna | 2 | 16.2 | 16.4 | tunnel construction | 17 | 24 | 408 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months X: 14; Number of planned closing days in the timetable 2022/2023 in individual months XI: 3 | single-track two-way traffic on the active track | 2023-10-18 | 2023-11-03 | 1.066
322 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Centralna | 2Śr | -2.425 | 0 | Inclusion of new line blockages | 8 | 6 | 48 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 8 | single-track two-way traffic on the active track | 2023-07-03 | 2023-07-10 | 1.093
323 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Centralna | 2Śr | -2.425 | 0 | Inclusion of new line blockages | 35 | 6 | 210 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XI: 26; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | single-track two-way traffic on the active track | 2023-11-05 | 2023-12-09 | 1.093
324 | 1 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Włochy | 2Ł | 3.082 | 6.804 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 8 | 6 | 48 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 8 | single-track two-way traffic on the active track | 2023-07-03 | 2023-07-10 | 1.093
325 | 1 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Włochy | 2Ł | 3.082 | 6.804 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 35 | 6 | 210 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XI: 26; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | single-track two-way traffic on the active track | 2023-11-05 | 2023-12-09 | 1.093
326 | 1 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IRR1/11 | stacja Warszawa Zachodnia | 401, 402 | 3.238 | 3.439 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 364 | 24 | 8736 | no limit | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2022-12-11 | 2023-12-09 | 1.093
327 | 1 | 20 | WARSZAWA GŁÓWNA TOWAROWA - WARSZAWA PRAGA | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Czyste | 211-214 | 3.587 | 4.36 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 8 | 6 | 48 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 8 | traffic interruption | 2023-07-03 | 2023-07-10 | 1.093
328 | 1 | 20 | WARSZAWA GŁÓWNA TOWAROWA - WARSZAWA PRAGA | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Czyste | 211-214 | 3.587 | 4.36 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 35 | 6 | 210 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XI: 26; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-11-05 | 2023-12-09 | 1.093
329 | 1 | 20 | WARSZAWA GŁÓWNA TOWAROWA - WARSZAWA PRAGA | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Gdańska | 1Z, 2Z | 4.36 | 10.719 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 8 | 6 | 48 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 8 | traffic interruption | 2023-07-03 | 2023-07-10 | 1.093
330 | 1 | 20 | WARSZAWA GŁÓWNA TOWAROWA - WARSZAWA PRAGA | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Gdańska | 1Z, 2Z | 4.36 | 10.719 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 35 | 6 | 210 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XI: 26; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-11-05 | 2023-12-09 | 1.093
331 | 1 | 42 | WARSZAWA GŁÓWNA OSOBOWA - WARSZAWA SZCZĘŚLIWICE T610/202/3,2/68 | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Czyste | 201, 202, 203, 204 | 3.323 | 4.641 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 8 | 6 | 48 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 8 | traffic interruption | 2023-07-03 | 2023-07-10 | 1.093
332 | 1 | 42 | WARSZAWA GŁÓWNA OSOBOWA - WARSZAWA SZCZĘŚLIWICE T610/202/3,2/68 | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Czyste | 201-204 | 3.323 | 4.641 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 35 | 6 | 210 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XI: 26; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-11-05 | 2023-12-09 | 1.093
333 | 1 | 46 | WARSZAWA ZACHODNIA - WARSZAWA CZYSTE T201,2S | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Czyste | 2Sz, 1001, 1002 | 2.642 | 4.553 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 8 | 6 | 48 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 8 | traffic interruption | 2023-07-03 | 2023-07-10 | 1.093
334 | 1 | 46 | WARSZAWA ZACHODNIA - WARSZAWA CZYSTE T201,2S | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Czyste | 2Sz, 1001, 1002 | 2.642 | 4.553 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 35 | 6 | 210 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XI: 26; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-11-05 | 2023-12-09 | 1.093
335 | 1 | 46 | WARSZAWA ZACHODNIA - WARSZAWA CZYSTE T201,2S | IRR1/11 | stacja Warszawa Zachodnia | 10 | 2.74 | 3.288 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 30 | 4 | 120 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 20; Number of planned closing days in the timetable 2022/2023 in individual months VII: 10 | traffic on active track at the station | 2023-06-11 | 2023-07-10 | 1.093
336 | 1 | 46 | WARSZAWA ZACHODNIA - WARSZAWA CZYSTE T201,2S | IRR1/11 | stacja Warszawa Zachodnia | 10 | 2.74 | 3.288 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 152 | 6 | 912 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 21; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-07-11 | 2023-12-09 | 1.093
337 | 1 | 445 | WARSZAWA ZACHODNIA - WARSZAWA ALEJE JEROZOLIMSKIE | IRR1/11 | stacja Warszawa Zachodnia | 21 | 2.6 | 3.5 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 30 | 24 | 720 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 20; Number of planned closing days in the timetable 2022/2023 in individual months VII: 10 | traffic on active track at the station | 2023-06-11 | 2023-07-10 | 1.093
338 | 1 | 445 | WARSZAWA ZACHODNIA - WARSZAWA ALEJE JEROZOLIMSKIE | IRR1/11 | stacja Warszawa Zachodnia | 22 | 2.735 | 3.426 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 152 | 24 | 3648 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 21; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-07-11 | 2023-12-09 | 1.093
339 | 1 | 445 | WARSZAWA ZACHODNIA - WARSZAWA ALEJE JEROZOLIMSKIE | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Al. Jerozolimskie | 3R | 3.082 | 6.068 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 35 | 6 | 210 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XI: 26; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-11-05 | 2023-12-09 | 1.093
340 | 1 | 445 | WARSZAWA ZACHODNIA - WARSZAWA ALEJE JEROZOLIMSKIE | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Aleje Jerozolimskie | 4R | 3.082 | 6.068 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 152 | 24 | 3648 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 21; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | single-track two-way traffic on the active track | 2023-07-11 | 2023-12-09 | 1.093
341 | 1 | 445 | WARSZAWA ZACHODNIA - WARSZAWA ALEJE JEROZOLIMSKIE | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Aleje Jerozolimskie | 3R | 3.5 | 6.068 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 30 | 24 | 720 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 20; Number of planned closing days in the timetable 2022/2023 in individual months VII: 10 | single-track two-way traffic on the active track | 2023-06-11 | 2023-07-10 | 1.093
342 | 1 | 447 | WARSZAWA ZACHODNIA - GRODZISK MAZOWIECKI | IRR1/11 | stacja Warszawa Zachodnia | 23 | 2.6 | 3.37 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 30 | 24 | 720 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 20; Number of planned closing days in the timetable 2022/2023 in individual months VII: 10 | traffic on active track at the station | 2023-06-11 | 2023-07-10 | 1.093
343 | 1 | 447 | WARSZAWA ZACHODNIA - GRODZISK MAZOWIECKI | IRR1/11 | stacja Warszawa Zachodnia | 20 | 2.634 | 3.375 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 152 | 24 | 3648 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 21; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-07-11 | 2023-12-09 | 1.093
344 | 1 | 447 | WARSZAWA ZACHODNIA - GRODZISK MAZOWIECKI | IRR1/11 | stacja Warszawa Zachodnia | 21 | 2.634 | 3.25 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 152 | 24 | 3648 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 21; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-07-11 | 2023-12-09 | 1.093
345 | 1 | 447 | WARSZAWA ZACHODNIA - GRODZISK MAZOWIECKI | IRR1/11 | stacja Warszawa Zachodnia | 23 | 2.634 | 3.205 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 152 | 24 | 3648 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 21; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-07-11 | 2023-12-09 | 1.093
346 | 1 | 447 | WARSZAWA ZACHODNIA - GRODZISK MAZOWIECKI | IRR1/11 | stacja Warszawa Zachodnia | 31 | 2.76 | 3.26 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 30 | 24 | 720 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 20; Number of planned closing days in the timetable 2022/2023 in individual months VII: 10 | traffic on active track at the station | 2023-06-11 | 2023-07-10 | 1.093
347 | 1 | 447 | WARSZAWA ZACHODNIA - GRODZISK MAZOWIECKI | IRR1/11 | stacja Warszawa Zachodnia | 31 | 2.76 | 3.26 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 152 | 6 | 912 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 21; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-07-11 | 2023-12-09 | 1.093
348 | 1 | 447 | WARSZAWA ZACHODNIA - GRODZISK MAZOWIECKI | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Włochy | 3W | 3.082 | 6.804 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 22 | 4 | 88 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 20; Number of planned closing days in the timetable 2022/2023 in individual months VII: 2 | single-track two-way traffic on the active track | 2023-06-11 | 2023-07-02 | 1.093
349 | 1 | 447 | WARSZAWA ZACHODNIA - GRODZISK MAZOWIECKI | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Włochy | 3W | 3.082 | 6.804 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 8 | 6 | 48 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 8 | single-track two-way traffic on the active track | 2023-07-03 | 2023-07-10 | 1.093
350 | 1 | 447 | WARSZAWA ZACHODNIA - GRODZISK MAZOWIECKI | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Włochy | 3W | 3.082 | 6.804 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 35 | 6 | 210 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XI: 26; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-11-05 | 2023-12-09 | 1.093
351 | 1 | 447 | WARSZAWA ZACHODNIA - GRODZISK MAZOWIECKI | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Włochy | 4W | 3.082 | 6.804 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 152 | 24 | 3648 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 21; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | single-track two-way traffic on the active track | 2023-07-11 | 2023-12-09 | 1.093
352 | 1 | 448 | WARSZAWA ZACHODNIA - WARSZAWA REMBERTÓW | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Wschodnia | 3Śr, 4ŚR | -2.696 | 4.254 | Upgrade of railway lines and stations | 35 | 6 | 210 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months XI: 26; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-11-05 | 2023-12-09 | 1.093
353 | 1 | 448 | WARSZAWA ZACHODNIA - WARSZAWA REMBERTÓW | IRR1/11 | Warszawa Podskarbińska - Warszawa Rembertów | 1.2 | 9.4 | 9.6 | Renovation works | 131 | 6 | 786 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption | 2023-08-01 | 2025-07-31 | 1.066
354 | 1 | 546 | WARSZAWA WSCHODNIA TOWAROWA - WARSZAWA REMBERTÓW T6M | IRR1/11 | Warszawa Antoninów - Warszawa Rembertów | 1 | 9.4 | 9.6 | Renovation works | 131 | 6 | 786 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption – single-track line | 2023-08-01 | 2025-07-31 | 1.066
355 | 1 | 901 | WARSZAWA WSCHODNIA TOWAROWA - WARSZAWA REMBERTÓW T5M | IRR1/11 | Warszawa Antoninów - Warszawa Rembertów | 1 | 9.4 | 9.6 | Renovation works | 131 | 6 | 786 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic interruption – single-track line | 2023-08-01 | 2025-07-31 | 1.066
356 | 1 | 919 | WARSZAWA ZACHODNIA - WARSZAWA OCHOTA POSTOJOWA | IRR1/11 | stacja Warszawa Zachodnia | 65 | 3.207 | 3.4 | Upgrade of railway lines and stations | 152 | 6 | 912 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 21; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-07-11 | 2023-12-09 | 1.093
357 | 1 | 919 | WARSZAWA ZACHODNIA - WARSZAWA OCHOTA POSTOJOWA | IRR1/11 | stacja Warszawa Zachodnia | 66 | 3.207 | 3.465 | Upgrade of railway lines and stations | 152 | 24 | 3648 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 21; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | traffic on active track at the station | 2023-07-11 | 2023-12-09 | 1.093
358 | 1 | 919 | WARSZAWA ZACHODNIA - WARSZAWA OCHOTA POSTOJOWA | IRR1/11 | stacja Warszawa Zachodnia | 66 | 3.27 | 3.6 | Upgrade of railway lines and stations | 30 | 4 | 120 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 20; Number of planned closing days in the timetable 2022/2023 in individual months VII: 10 | traffic on active track at the station | 2023-06-11 | 2023-07-10 | 1.093
359 | 1 | 919 | WARSZAWA ZACHODNIA - WARSZAWA OCHOTA POSTOJOWA | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Ochota Postojowa | 65 | 3.274 | 3.6 | Upgrade of railway lines and stations | 30 | 24 | 720 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 20; Number of planned closing days in the timetable 2022/2023 in individual months VII: 10 | single-track two-way traffic on the active track | 2023-06-11 | 2023-07-10 | 1.093
360 | 1 | 920 | WARSZAWA ZACHODNIA R 578 - WARSZAWA ZACHODNIA R 217 | IRR1/11 | stacja Warszawa Zachodnia | 447 | 2.8 | 3.3 | Upgrade of railway lines and stations | 364 | 24 | 8736 | no limit | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 9 | traffic on active track at the station | 2022-12-11 | 2023-12-09 | 1.093
361 | 2 | 7 | WARSZAWA WSCHODNIA OSOBOWA - DOROHUSK | IZ Lublin | Chełm Wschodni - Brzeźno | 1 | 251.9 | 256.8 | Surface replacement from S49 to S60 | 20 | 8 | 160 | 50 km/h | 60 km/h | Number of planned closing days in the timetable 2022/2023 in individual months VI: 15; Number of planned closing days in the timetable 2022/2023 in individual months VII: 5 | single-track two-way traffic on the active track | 2023-06-12 | 2023-07-07
362 | 2 | 61 | KIELCE - FOSOWSKIE | IZ Kielce | Kielce - Kielce Herbskie | 1 | 1,360 | 6,000 | Installation of switches no.: 115/116, 117/118, 126, 138, 139, 140/141 under the KPO | 30 | 24 | 720 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months X: 20; Number of planned closing days in the timetable 2022/2023 in individual months XI: 10 | traffic on active track at the station | 2023-10-10 | 2023-11-10
363 | 2 | 61 | KIELCE - FOSOWSKIE | IZ Kielce | Rykoszyn - Szczukowice | 2 | 8.35 | 14.53 | AHM substructure reinforcement | 62 | 24 | 1488 | 60 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 1; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30 | single-track two-way traffic on the active track | 2023-10-02 | 2023-10-06
364 | 2 | 61 | KIELCE - FOSOWSKIE | IZ Kielce | st. Rykoszyn | 2 | 17.829 | 18.695 | Maintenance and repair works NBO Rykoszyn station track no. 2. | 5 | 24 | 120 | 60 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months X: 5 | traffic on active track at the station | 2023-10-02 | 2023-10-06
365 | 2 | 61 | KIELCE - FOSOWSKIE | IZ Kielce | Czarnca - Włoszczowa | 2 | 48,500 | 52,940 | AHM substructure reinforcement | 59 | 24 | 1416 | 60 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 29 | single-track two-way traffic on the active track | 2023-06-01 | 2023-09-30
366 | 2 | 66 | ZWIERZYNIEC TOWAROWY - STALOWA WOLA POŁUDNIE | IZ Lublin | Zwierzyniec Towarowy - Biłgoraj | Szlak | 6,200 14,100 | 9,200 14,900 | NBO + track bed profiling including track tamping | 10 | 12 | 120 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 10 | traffic interruption – single-track line | 2023-07-03 | 2023-07-12
367 | 2 | 73 | SITKÓWKA NOW. - BUSKO ZDRÓJ | IZ Kielce | Sitkówka Nowiny - Nida | 1 | 1,090; 1,835; 3,185 5,450 | 1,140; 1,885; 3,265 5,490 | Major renovation of engineering structures | 66 | 24 | 1584 | 30 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months V: 22; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 14 | single-track two-way traffic on the active track | 2023-05-10 | 2023-07-14
368 | 2 | 73 | SITKÓWKA NOW. - BUSKO ZDRÓJ | IZ Kielce | Nida - Sitkówka Nowiny | 2 | 1,090; 1,835; 3,185 5,450 | 1,140; 1,885; 3,265 5,490 | Major renovation of engineering structures | 68 | 24 | 1632 | 30 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 17; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 20 | single-track two-way traffic on the active track | 2023-07-15 | 2023-09-20
369 | 2 | 75 | RYTWIANY - POŁANIEC | IZ Kielce | st. Połaniec | 12,16,18 | 16.06 | 16.727 | Adaptation of the track layout of Połaniec station, line no. 75 Rytwiany – Połaniec for the improvement of operations | 61 | 24 | 1464 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months V: 30; Number of planned closing days in the timetable 2022/2023 in individual months VI: 31 | traffic on active track at the station | 2023-06-01 | 2023-07-31
370 | 2 | 568 | SITKÓWKA NOWINY - SZCZUKOWICE | IZ Kielce | Sitkówka Nowiny - Szczukowice | 1 | -0,440 | 6,820 | Major renovation of engineering structures | 144 | 24 | 3456 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months V: 22; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 30; Number of planned closing days in the timetable 2022/2023 in individual months IX: 31 | traffic interruption | 2023-05-10 | 2023-10-31
371 | 4 | 138 | OŚWIĘCIM - KATOWICE | IRR4/4 | Mysłowice MwB R166 - Katowice Zawodzie | 2 | 26.574 | 29.48 | upgrade | 123 | 24 | 2952 | 60 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months III: 19; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 13 | single-track two-way traffic on the active track | 2023-03-12 | 2023-07-13
372 | 4 | 138 | OŚWIĘCIM - KATOWICE | IRR4/4 | Szabelnia - Katowice Zawodzie | 1 | 26.574 | 29.48 | upgrade | 155 | 24 | 3720 | 60 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 18; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 15 | single-track two-way traffic on the active track | 2023-07-14 | 2023-12-15
373 | 4 | 656 | KATOWICE - BRYNÓW | IRR4/4 | Katowice - Brynów | 1 | 0.75 | 3.005 | upgrade | 262 | 24 | 6288 | traffic interruption | no limit |  |  |  |  | 17 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | traffic interruption – single-track line | 2023-04-13 | 2024-02-28
374 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IZ12 Olsztyn | Stare Jabłonki - Biesal | 1 | 275,250 | 275,250 | embankment reinforcement | 184 | 24 | 4416 | 50 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 22; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 9 | single-track two-way traffic on the active track | 2023-06-09 | 2023-12-29 | 4.018
375 | 5 | 221 | OLSZTYN GUTKOWO - BRANIEWO | IZ12 Olsztyn | Dobre Miasto - Orneta | 1 | 23.75 | 44.35 | Engineering structure works, construction of platforms | 303 | 24 | 7272 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 9 |  |  | traffic interruption | 11.12.2022 | 09.10.2023
376 | 5 | 221 | OLSZTYN GUTKOWO - BRANIEWO | IZ12 Olsztyn | Orneta - Pieniężno | 1 | 45.42 | 59.22 | Revitalisation of a section of the line | 303 | 24 | 7272 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 9 |  |  | traffic interruption | 11.12.2022 | 09.10.2023
377 | 6 | 137 | KATOWICE - LEGNICA | IZ Wałbrzych | Jawor | 1 | 261.607 | 262.46 | reconstruction of subway no. 1 | 214 | 24 | 5136 | 20 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months III: 31; Number of planned closing days in the timetable 2022/2023 in individual months IV: 30; Number of planned closing days in the timetable 2022/2023 in individual months V: 31; Number of planned closing days in the timetable 2022/2023 in individual months VI: 30; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30 | traffic on active track at the station | 2023-03-01 | 2023-09-30
378 | 6 | 137 | KATOWICE - LEGNICA | IZ Wałbrzych | Jawor | 3 | 261.614 | 262.452 | reconstruction of subway no. 3 | 92 | 24 | 2208 | 20 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 31 | traffic on active track at the station | 2023-10-01 | 2024-04-30
379 | 6 | 276 | WROCŁAW GŁÓWNY - MIĘDZYLESIE | IZ Wałbrzych | tor nr 1 szlak Kłodzko Miasto- zpr Kłodzko Nowe | 1 | 96.293 | 97.42 | end-to-end surface replacement | 46 | 24 | 1104 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 15 | prohibition of electric traffic on the route Zpr Kłodzko Nowe – Gorzanów | 2023-07-01 | 2023-08-15
380 | 6 | 276 | WROCŁAW GŁÓWNY - MIĘDZYLESIE | IZ Wałbrzych | tor nr 2 w stacji Kłodzko Miasto oraz tor nr 2 szlak Kłodzko Miasto - zpr Kłodzko Nowe | 2 | 96.296 | 97.371 | end-to-end surface replacement | 46 | 24 | 1104 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 16; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30 | single-track two-way traffic on the active track | 2023-08-16 | 2023-09-30
381 | 6 | 276 | WROCŁAW GŁÓWNY - MIĘDZYLESIE | IZ Wałbrzych | zpr Kłodzko Nowe – Gorzanów – Bystrzyca Kłodzka Przedmieście – Domaszków – Międzylesie | 1 | 97.573 | 130.06 | repair of retaining wall at km 102.122; repair of the bridge at km 107.381; replacement of rails at selected locations | 88 | 24 | 2112 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 27; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30 | traffic interruption | 2023-09-04 | 2023-11-30
382 | 6 | 291 | BOGUSZÓW GORCE WSCHÓD - MIEROSZÓW | IZ Wałbrzych | Boguszów Gorce Wschód - Mieroszów | 1 | 17.706 | 28.033 | repair of the viaduct at km 25.445 and repair of the line tunnel at km 21.910 | 119 | 24 | 2856 | traffic interruption | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 27; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 31 | traffic interruption | 2023-09-04 | 2024-12-31
383 | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IZ Poznań | Nowy Tomyśl-Zbąszyń | 2 | 362.518 | 373.1 | Mechanical cleaning, topping up of the ballast and associated works on track 2 from km 362.518 to km 373.100 on line 003 | 61 | 24 | 1464 | 60 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30 | single-track two-way traffic on the active track | 2025-08-01 | 2025-09-30
384 | 7 | 281 | OLEŚNICA - CHOJNICE | IZ Poznań | Wrzesnia-Czerniejewo | 2 | 136.789 | 142.5 | End-to-end track surface replacement and associated works from km 136.789 to km 142.500 | 61 | 24 | 1464 | 60 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30 | single-track two-way traffic on the active track | 2025-08-01 | 2025-09-30
385 | 7 | 281 | OLEŚNICA - CHOJNICE | IZ Ostrów Wielkopolski | Orzechowo Orzechowo - Żerków | 1 | 112.7 | 112.95 | Platform 1 upgrade | 106 | 24 | 2544 | 30 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 12; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 2 | single-track two-way traffic on the active track | 2023-06-18 | 2023-10-02 | Rządowy program peronowy (Government Platform Programme)
386 | 7 | 281 | OLEŚNICA - CHOJNICE | IZ Ostrów Wielkopolski | Miłosław, Miłosław - Września | 2, 4, 2 | 126.035 | 126.285 | Platform 2 upgrade Książno | 97 | 24 | 2328 | 30 km/h | no limit | Number of planned closing days in the timetable 2022/2023 in individual months IX: 21; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 15 | single-track two-way traffic on the active track | 2023-09-10 | 2023-12-15 | Rządowy program peronowy (Government Platform Programme)
387 | 7 | 355 | OSTRÓW WIELKOPOLSKI - GRABOWNO WIELKIE | IZ Ostrów Wielkopolski | Ostrów Wielkopolski - Międzybórz Sycowski | 1 | -1.19 | 31.9 | Track 1 upgrade, reconstruction of platforms on the line | 306 | 24 | 7344 | no limit | no limit |  |  |  | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | traffic interruption – single-track line | 2023-03-06 | 2024-03-31 | KPO
388 | 7 | 370 | ZIELONA GÓRA - ŻARY | IZ Zielona Góra | Zielona Góra Główna- Nowogród Osiedle | 1 | 1.538 | 29.854 | end-to-end surface replacement and reconstruction of engineering structures | 153 | 24 | 3672 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 31 | traffic interruption – single-track line | 2023-08-01 | 2024-12-31
389 | 7 | 370 | ZIELONA GÓRA - ŻARY | IZ Zielona Góra | Nowogród Osiedle- Bieniów | 1 | 29.854 | 40.63 | end-to-end surface replacement and reconstruction of engineering structures | 153 | 24 | 3672 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 31 | traffic interruption – single-track line | 2023-08-01 | 2024-12-31
390 | 7 | 370 | ZIELONA GÓRA - ŻARY | IZ Zielona Góra | Bieniów- Żary | 1 | 40.63 | 52.655 | end-to-end surface replacement and reconstruction of engineering structures | 153 | 24 | 3672 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 31 | traffic interruption – single-track line | 2023-08-01 | 2024-12-31
391 | 8 | 367 | ZBĄSZYNEK - GORZÓW WIELKOPOLSKI | IZ Zielona Góra | Gorzów Wlkp.Zieleniec - Gorzów Wlkp. | 1 | 70.18 | 73.107 | reconstruction of two bridges | 204 | 24 | 4896 | no limit | no limit | Number of planned closing days in the timetable 2022/2023 in individual months VI: 20; Number of planned closing days in the timetable 2022/2023 in individual months VII: 31; Number of planned closing days in the timetable 2022/2023 in individual months VIII: 31; Number of planned closing days in the timetable 2022/2023 in individual months IX: 30; Number of planned closing days in the timetable 2022/2023 in individual months X: 31; Number of planned closing days in the timetable 2022/2023 in individual months XI: 30; Number of planned closing days in the timetable 2022/2023 in individual months XII: 31 | traffic interruption – single-track line | 2023-06-11 | 2025-10-31
In the absence of a determination of the length of the speed limit on the adjacent track, a section of 2000 m is assumed for the calculation of the upgrade allowance. Speed limits for works lasting more than 4 months are assumed as the basis for the RRJ development.