## SHZT 2023-2024 - I korekta
Annex 5.1 - NETWORK STATEMENT 2023/2024 Network schedule of track closures planned for execution in the 2023/2024 timetable - FIRST CORRECTION
No. | IDDE code | Line No. | Line name | Principal | Identification of the station, route or line section, on wich the works will be performed | Track No. | Km from | Km to | Type of work performed | No. of days of track, route, section closure | No. of hours of closure per day | Total No. of closure hours | Speed limit km/h - on adjacted track | Speed limit km/h - after works finish | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 | [12 empty] | Description of operating railway traffic | Proposed deadlines from | Proposed deadlines to | KPK projects
[15 empty] | XII | I | II | III | IV | V | VI | VII | VIII | IX | X | XI | XII
1 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/3 | Częstochowa Towarowa | 13, 15 | 231.195 | 233.595 | facilities, railroad surface, overhead contact line, Railway Traffic Controlling system [srk], power supply | 9 | 24 | 216 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 9 | traffic on active track at the station | 2024-04-01 | 2024-04-09
2 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/3 | Częstochowa Towarowa | 17, 19, 21, 23, 25, 27, 29 | 231.195 | 233.595 | facilities, railroad surface, overhead contact line, Railway Traffic Controlling system [srk], power supply | 29 | 24 | 696 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 8 | traffic on active track at the station | 2024-04-10 | 2024-05-08
3 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/3 | Częstochowa Towarowa | 31, 33, 35, 37 | 231.195 | 233.595 | facilities, railroad surface, overhead contact line, Railway Traffic Controlling system [srk], power supply | 60 | 24 | 1440 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 23; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 7 | traffic on active track at the station | 2024-05-09 | 2024-07-07
4 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/3 | Częstochowa Towarowa | 5, 7, 9, 11 | 231.195 | 233.595 | facilities, railroad surface, overhead contact line, Railway Traffic Controlling system [srk], power supply | 30 | 24 | 720 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 9 | traffic on active track at the station | 2024-06-10 | 2024-07-09
5 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/3 | Częstochowa Towarowa | 39, 41, 43, 45 | 231.195 | 233.595 | facilities, railroad surface, overhead contact line, Railway Traffic Controlling system [srk], power supply | 20 | 24 | 480 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 20 | traffic on active track at the station | 2024-07-09 | 2024-07-29
6 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/3 | Częstochowa Towarowa | 49, 51, 53, 55 | 231.195 | 233.595 | facilities, railroad surface, overhead contact line, Railway Traffic Controlling system [srk], power supply | 19 | 24 | 456 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 2; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 17 | traffic on active track at the station | 2024-07-30 | 2024-08-17
7 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/3 | Częstochowa Towarowa | 47 | 231.195 | 233.595 | facilities, railroad surface, overhead contact line, Railway Traffic Controlling system [srk], power supply | 8 | 24 | 192 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 8 | traffic on active track at the station | 2024-08-18 | 2024-08-25
8 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | Dąbrowa Górnicza -Będzin | 1 | 300.81 | 305.1 | upgrade | 22 | 24 | 528 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 1 | single-track two-way traffic on the active track | 2023-11-23 | 2024-01-01
9 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | Dąbrowa Górnicza -Będzin | 2 | 300.81 | 305.1 | technology commissioning activities | 22 | 4 | 88 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 1 | traffic interruption | 2023-11-23 | 2024-01-01
10 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | Dąbrowa Górnicza -Będzin | 2 | 300.81 | 305.1 | upgrade | 173 | 24 | 4152 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 23 | single-track two-way traffic on the active track | 2024-01-02 | 2024-06-23
11 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | Dąbrowa Górnicza -Będzin | 1 | 300.81 | 305.1 | technology commissioning activities | 173 | 4 | 692 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 23 | traffic interruption | 2024-01-02 | 2024-06-23
12 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | Stacja Będzin | 1 | 305.1 | 306.15 | upgrade | 195 | 24 | 4680 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 23 | traffic on active track at the station | 2023-05-01 | 2024-06-23
13 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | Stacja Będzin | 2 | 305.15 | 306.1 | upgrade | 242 | 24 | 5808 | 60 km/h | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 9 |  |  |  |  | traffic on active track at the station | 2023-05-01 | 2024-08-09
14 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | Stacja Będzin | 6 | 305.2 | 306.1 | upgrade | 195 | 24 | 4680 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 23 | traffic on active track at the station | 2023-04-01 | 2024-06-23
15 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | Stacja Będzin | 4 | 305.2 | 306.1 | upgrade | 173 | 24 | 4152 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 23 | traffic on active track at the station | 2024-01-02 | 2024-06-23
16 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | Stacja Będzin | 3 | 305.3 | 306.84 | upgrade | 22 | 24 | 528 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 1 | traffic on active track at the station | 2023-05-01 | 2024-01-01
17 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | Będzin - Sosnowiec Główny | 2 | 306.1 | 308.5 | upgrade | 222 | 24 | 5328 | traffic interruption | no limit |  | 18 | 28 | 31 | 30 | 31 | 30 | 31 | 23 |  |  |  |  | traffic interruption | 2024-01-14 | 2024-08-23
18 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | Będzin - Sosnowiec Główny | 1 | 306.18 | 308.4 | upgrade | 174 | 24 | 4176 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 18; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 6 | traffic interruption | 2024-01-14 | 2024-07-06
19 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | stacja Sosnowiec Główny | 3,5,7,9, 11,13 | 308.4 | 309.8 | upgrade | 16 | 24 | 384 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 16 | traffic on active track at the station | 2024-08-08 | 2024-08-23
20 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | stacja Sosnowiec Główny | 3,5,7,9, 11,13 | 308.4 | 309.8 | upgrade | 99 | 24 | 2376 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 24; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-09-07 | 2025-09-16
21 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | stacja Sosnowiec Główny | 2 | 308.55 | 309.8 | upgrade | 129 | 24 | 3096 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 24; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-08-08 | 2025-01-23
22 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | stacja Sosnowiec Główny | 1 | 308.55 | 310 | upgrade | 99 | 24 | 2376 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 24; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-09-07 | 2025-01-07
23 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | stacja Sosnowiec Główny | 2 | 310 | 311.315 | upgrade | 52 | 24 | 1248 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 8; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-10-24 | 2025-10-02
24 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | Sosnowiec Główny - tymczasowy PODG Katowice Szopienice Południowe | 2 | 310.615 | 312.8 | upgrade | 113 | 24 | 2712 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 14; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 7 | single-track two-way traffic on the active track | 2024-02-16 | 2024-06-07
25 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | Sosnowiec Główny - Katowice Zawodzie | 1 | 310.615 | 312.8 | technology commissioning activities | 112 | 4 | 448 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 13; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 7 | traffic interruption | 2024-02-16 | 2024-06-07
26 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | Sosnowiec Główny - Katowice Zawodzie | 2 | 310.615 | 314.767 | technology commissioning activities | 190 | 4 | 760 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 23; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption | 2024-06-08 | 2024-12-15
27 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | Sosnowiec Główny - Katowice Zawodzie | 1 | 310.651 | 312.6 | upgrade | 190 | 24 | 4560 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 23; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-06-08 | 2024-12-15
28 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | Sosnowiec Główny - tymczasowy PODG Katowice Szopienice Południowe | 2 | 311.315 | 312.195 | upgrade | 52 | 24 | 1248 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 8; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption | 2024-10-24 | 2025-10-02
29 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | stacja Katowice Zawodzie | 1 | 314.75 | 315.75 | upgrade | 61 | 24 | 1464 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 15; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 15 | traffic on active track at the station | 2024-09-16 | 2024-11-15
30 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | stacja Katowice | 529, 531 | 317.6 | 317.9 | upgrade | 36 | 24 | 864 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 15 | traffic on active track at the station | 2023-09-01 | 2024-01-15
31 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | stacja Katowice | 12 | 317.6 | 317.9 | upgrade | 61 | 24 | 1464 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 15; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 15 | traffic on active track at the station | 2024-07-17 | 2024-09-15
32 | 4 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR4/4 | stacja Katowice | 11,13,15,17 | 317.65 | 317.9 | upgrade | 151 | 24 | 3624 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 15; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-07-17 | 2025-02-14
33 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/5 | szlak Biała Podlaska - Sokule | 1, 2 | 160.556 | 171.799 | upgrade | 12 | 4 | 48 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 12 | traffic interruption | 2023-01-02 | 2023-12-22 | 1.123
34 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/5 | Stacja Biała Podlaska | 1, 2 | 171.799 | 174.121 | upgrade | 12 | 4 | 48 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 12 | traffic interruption | 2023-01-02 | 2023-12-22 | 1.123
35 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/5 | szlak Biała Podlaska - Chotyłów | 1, 2 | 174.121 | 188.019 | upgrade | 12 | 4 | 48 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 12 | traffic interruption | 2023-01-02 | 2023-12-22 | 1.123
36 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/5 | St. Biała Podlaska | 12b | 174.592 | 176.564 | upgrade | 42 | 24 | 1008 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 21 | traffic on active track at the station | 2023-10-07 | 2024-01-21 | 1.123
37 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/5 | szlak Chotyłów - Małaszewicze | 1, 2 | 190.33 | 198.49 | upgrade | 12 | 4 | 48 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 12 | traffic interruption | 2023-01-02 | 2023-12-22 | 1.123
38 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/5 | szlak Magdalenka - Małaszewicze Południowe | 1, 2 | 198.051 | 198.49 | upgrade | 12 | 4 | 48 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 12 | traffic interruption | 2023-01-02 | 2023-12-22 | 1.123
39 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/5 | stacja Małaszewicze | 1, 2 | 198.49 | 200.118 | upgrade | 12 | 4 | 48 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 12 | traffic on active track at the station | 2023-01-02 | 2023-12-22 | 1.123
40 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/5 | szlak Małaszewicze - Terespol | 1, 2 | 200.118 | 207.502 | upgrade | 12 | 4 | 48 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 12 | traffic interruption | 2023-01-02 | 2023-12-22 | 1.123
41 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/5 | Stacja Terespol | 1, 2 | 207.502 | 210.3 | upgrade | 12 | 4 | 48 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 12 | traffic interruption | 2023-01-02 | 2023-12-22 | 1.123
42 | 1 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR1/1 | Teresin | 1 | 41.73 | 41.75 | construction of a railway viaduct | 96 | 24 | 2304 | 40 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 16 | traffic on active track at the station | 2023-09-03 | 2024-03-16 | 1.066
43 | 1 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR5/1 | Kutno | 205N,207N,207c | 125.903 | 125.903 | reconstruction of the track system, overhead line, traffic control works | 1 | 24 | 24 | no limit | no limit | [13 empty] | traffic on active track at the station | 2022-12-12 | 2023-12-11 | 1.106 | bar: Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII
44 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | stacja Psary | 2,4,6 | 169.251 | 170.967 | piling, installation of new substructures, gantry supports, fixtures, reconstruction of the existing contact line, | 70 | 24 | 1680 | 100 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 24; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 15 | traffic on active track at the station | 2024-02-05 | 2024-04-15
45 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | stacja Psary | 1,3 | 169.251 | 170.967 | piling, installation of new substructures, gantry supports, fixtures, reconstruction of the existing contact line, | 70 | 6 | 420 | 100 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 24; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 15 | traffic on active track at the station | 2024-02-05 | 2024-04-15
46 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | stacja Psary | 1,3 | 169.251 | 170.967 | piling, installation of new substructures, gantry supports, fixtures, reconstruction of the existing contact line, | 41 | 24 | 984 | 100 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 15; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 26 | traffic on active track at the station | 2024-04-16 | 2024-05-26
47 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | stacja Psary | 2 | 169.251 | 170.967 | piling, installation of new substructures, gantry supports, fixtures, reconstruction of the existing contact line, | 41 | 6 | 246 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 15; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 26 | traffic on active track at the station | 2024-04-16 | 2024-05-26
48 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | stacja Psary | 2 | 169.251 | 170.967 | piling, installation of new substructures, gantry supports, fixtures, reconstruction of the existing contact line, | 26 | 24 | 624 | 100 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 5; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic on active track at the station | 2024-05-27 | 2024-06-21
49 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | stacja Psary | 1,3,4 | 169.251 | 170.967 | piling, installation of new substructures, gantry supports, fixtures, reconstruction of the existing contact line, | 26 | 6 | 156 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 5; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic on active track at the station | 2024-05-27 | 2024-06-21
50 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | stacja Psary | 4,6 | 169.251 | 170.967 | piling, installation of new substructures, gantry supports, fixtures, reconstruction of the existing contact line, | 26 | 24 | 624 | 100 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 9; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 17 | traffic on active track at the station | 2024-06-22 | 2024-07-17
51 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | Knapówka - Psary | 2 | 169.321 | 170.474 | track, overhead contact line system, Railway Traffic Controlling system [srk], drainage and electric switch heating: end-to-end replacement of track no. 1, end-to-end replacement of switches | 70 | 24 | 1680 | 100 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 24; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 15 | single-track two-way traffic on the active track | 2024-02-05 | 2024-04-15
52 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | Knapówka - Psary | 1 | 169.321 | 170.474 | track, overhead contact line system, Railway Traffic Controlling system [srk], drainage and electric switch heating: end-to-end replacement of track no. 1, end-to-end replacement of switches | 70 | 6 | 420 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 24; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 15 | traffic interruption | 2024-02-05 | 2024-04-15
53 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | Psary - Góra Włodowska | 1 | 169.439 | 170.285 | track,overhead contact line system, Railway Traffic Controlling system [srk], drainage and electric switch heating: end-to-end replacement of track no. 2, replacement of switches no. 1, 4, 6, 9, 11, hanging of L8P sections and crossovers | 70 | 6 | 420 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 24; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 15 | single-track two-way traffic on the active track | 2024-02-05 | 2024-04-15
54 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | Psary - Góra Włodowska | 1 | 169.439 | 170.285 | track,overhead contact line system, Railway Traffic Controlling system [srk], drainage and electric switch heating: end-to-end replacement of track no. 2, replacement of switches no. 1, 4, 6, 9, 11, hanging of L8P sections and crossovers | 41 | 24 | 984 | 100 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 15; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 26 | single-track two-way traffic on the active track | 2024-04-16 | 2024-05-26
55 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | Psary - Góra Włodowska | 2 | 169.439 | 170.285 | track,overhead contact line system, Railway Traffic Controlling system [srk], drainage and electric switch heating: end-to-end replacement of track no. 2, replacement of switches no. 1, 4, 6, 9, 11, hanging of L8P sections and crossovers | 41 | 6 | 246 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 15; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 26 | traffic interruption | 2024-04-16 | 2024-05-26
56 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | Psary - Góra Włodowska | 2 | 169.439 | 170.285 | track,overhead contact line system, Railway Traffic Controlling system [srk], drainage and electric switch heating: end-to-end replacement of track no. 2, replacement of switches no. 1, 4, 6, 9, 11, hanging of L8P sections and crossovers | 26 | 24 | 624 | 100 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 5; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | single-track two-way traffic on the active track | 2024-05-27 | 2024-06-21
57 | 2 | 4 | GRODZISK MAZOWIECKI - ZAWIERCIE | IRR1/13 | Psary - Góra Włodowska | 1 | 169.439 | 170.285 | track,overhead contact line system, Railway Traffic Controlling system [srk], drainage and electric switch heating: end-to-end replacement of track no. 2, replacement of switches no. 1, 4, 6, 9, 11, hanging of L8P sections and crossovers | 26 | 6 | 156 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 5; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption | 2024-05-27 | 2024-06-21
58 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | Stacja Łapy | 1 | 152.996 | 155.035 | upgrade | 362 | 4 | 1448 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 7 | traffic interruption | 2023-03-12 | 2024-12-07 | 1.090
59 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | Stacja Białystok | 23-33 | 175.054 | 178.002 | upgrade | 110 | 24 | 2640 | 40 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 30 | traffic on active track at the station | 2023-07-01 | 2024-03-30 | 1.090
60 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | Stacja Białystok | 113-126 | 175.054 | 178.002 | upgrade | 110 | 24 | 2640 | 40 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 30 | traffic on active track at the station | 2021-06-13 | 2024-03-30 | 1.090
61 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | Stacja Białystok | 1,3,5,7 | 175.054 | 178.002 | upgrade | 110 | 24 | 2640 | 40 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 30 | traffic on active track at the station | 2023-07-01 | 2024-03-30 | 1.090
62 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | Geniusze | 12 | 210.726 | 212.237 | upgrade | 369 | 24 | 8856 | 40 km/h | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic on active track at the station | 2023-07-15 | 2025-01-10
63 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | Geniusze | 2 | 210.726 | 212.237 | upgrade | 369 | 24 | 8856 | 40 km/h | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic on active track at the station | 2023-07-15 | 2025-01-10
64 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | Geniusze | 4 | 210.726 | 212.237 | upgrade | 369 | 24 | 8856 | 40 km/h | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic on active track at the station | 2023-07-15 | 2025-01-10
65 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | Geniusze | 6 | 210.726 | 212.237 | upgrade | 369 | 24 | 8856 | 40 km/h | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic on active track at the station | 2023-07-15 | 2025-01-10
66 | 1 | 6 | ZIELONKA - KUŹNICA BIAŁOSTOCKA | IRR1/7 | Geniusze | 8 | 210.726 | 212.237 | upgrade | 369 | 24 | 8856 | 40 km/h | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic on active track at the station | 2023-07-15 | 2025-01-10
67 | 1 | 7 | WARSZAWA WSCHODNIA OSOBOWA - DOROHUSK | IRR1/3 | Warszawa Wschodnia Osobowa - Warszawa Wawer | 1.2 | 4.254 | 12.569 | railway line upgrade | 21 | 24 | 504 | 80 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21 | single-track two-way traffic on the active track | 2023-06-10 | 2023-12-31 | 1.088
68 | 1 | 7 | WARSZAWA WSCHODNIA OSOBOWA - DOROHUSK | IRR1/3 | Warszawa Wawer - Otwock | 1, 2 | 13.81 | 26.05 | Upgrade | 369 | 4 | 1476 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption | 2023-12-10 | 2024-12-14
69 | 1 | 7 | WARSZAWA WSCHODNIA OSOBOWA - DOROHUSK | IRR1/3 | Warszawa Miedzylesie - Otwock | 2 | 13.81 | 26.05 | Upgrade | 105 | 24 | 2520 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-09-01 | 2025-09-01
70 | 2 | 7 | WARSZAWA WSCHODNIA OSOBOWA - DOROHUSK | IRR1/3 | Otwock - Lublin | 1 lub 2 | 26.05 | 175.85 | troubleshooting during the warranty period | 368 | 4 | 1472 | no limit | no limit | 20 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | single-track two-way traffic on the active track | 2023-12-12 | 2024-12-14 | 1.088
71 | 2 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IRR1/2 | Lesiów - Radom Główny | 1 | 97 | 101.4 | Reconstruction of the overhead contact line, drainage and other colliding infrastructure, construction of a platform in the intertrack space between tracks 1 and 2 of line 8 at km 101.000 – 101.400 | 21 | 6 | 126 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21 | traffic interruption | 2022-12-09 | 2023-12-31 | 4.022
72 | 2 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IRR1/2 | Lesiów - Radom Główny | 2 | 97 | 101.4 | Reconstruction of the overhead contact line, drainage and other colliding infrastructure, construction of a platform in the intertrack space between tracks 1 and 2 of line 8 at km 101.000 – 101.400 | 21 | 6 | 126 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21 | traffic interruption | 2022-12-09 | 2023-12-31 | 4.022
73 | 1 | 14 | ŁÓDŹ KALISKA - TUPLICE | IRR1/9 | Łódź Kaliska - Retkinia tor 1 | 1 | 0.502 | 2.5 | Touch-up painting of substructures | 10 | 24 | 240 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 10 | single-track two-way traffic on the active track | 2024-03-11 | 2024-03-20 | 1.105
74 | 1 | 14 | ŁÓDŹ KALISKA - TUPLICE | IRR1/9 | Łódź Kaliska - Retkinia tor 2 | 2 | 0.502 | 2.5 | Touch-up painting of substructures | 9 | 24 | 216 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 9 | single-track two-way traffic on the active track | 2024-03-21 | 2024-03-29 | 1.105
75 | 1 | 14 | ŁÓDŹ KALISKA - TUPLICE | IRR1/9 | Lublinek - Pabianice tor 1 | 1 | 7.491 | 13.51 | Touch-up painting of substructures | 16 | 24 | 384 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 16 | single-track two-way traffic on the active track | 2024-04-15 | 2024-04-30 | 1.105
76 | 1 | 14 | ŁÓDŹ KALISKA - TUPLICE | IRR1/9 | St. Pabianice tor 1,5 | 1,5 | 13.362 | 15.209 | Touch-up painting of substructures | 10 | 24 | 240 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 10 | traffic on active track at the station | 2024-05-13 | 2024-05-22 | 1.105
77 | 1 | 14 | ŁÓDŹ KALISKA - TUPLICE | IRR1/9 | St. Pabianice tor 2,4 | 2,4 | 13.362 | 15.209 | Touch-up painting of substructures | 8 | 24 | 192 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 8 | traffic on active track at the station | 2024-05-23 | 2024-05-30 | 1.105
78 | 1 | 14 | ŁÓDŹ KALISKA - TUPLICE | IRR1/9 | Pabianice - Łask tor 1 | 1 | 21.664 | 31.271 | Touch-up painting of substructures | 13 | 24 | 312 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 1; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 12 | single-track two-way traffic on the active track | 2024-05-31 | 2024-06-12 | 1.105
79 | 1 | 14 | ŁÓDŹ KALISKA - TUPLICE | IRR1/9 | Pabianice - Łask tor 2 | 2 | 21.664 | 31.271 | Touch-up painting of substructures | 11 | 24 | 264 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 11 | single-track two-way traffic on the active track | 2024-06-13 | 2024-06-23 | 1.105
80 | 1 | 14 | ŁÓDŹ KALISKA - TUPLICE | IRR1/9 | St. Łask tor 1,3 | 1,3 | 30.143 | 31.459 | Touch-up painting of substructures | 20 | 24 | 480 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 7; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 13 | traffic on active track at the station | 2024-06-24 | 2024-07-13 | 1.105
81 | 1 | 14 | ŁÓDŹ KALISKA - TUPLICE | IRR1/9 | St. Łask tor 2,4,6 | 2,4,6 | 30.143 | 31.459 | Touch-up painting of substructures | 20 | 24 | 480 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 17; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 3 | traffic on active track at the station | 2024-07-15 | 2024-08-03 | 1.105
82 | 1 | 14 | ŁÓDŹ KALISKA - TUPLICE | IRR1/9 | Łask - Gajewniki tor nr 1 | 1 | 30.143 | 39.63 | Touch-up painting of substructures | 20 | 24 | 480 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 20 | single-track two-way traffic on the active track | 2024-08-05 | 2024-08-24 | 1.105
83 | 1 | 14 | ŁÓDŹ KALISKA - TUPLICE | IRR1/9 | Łask - Gajewniki tor nr 2 | 2 | 30.143 | 39.63 | Touch-up painting of substructures | 25 | 24 | 600 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 6; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 19 | single-track two-way traffic on the active track | 2024-08-26 | 2024-09-19 | 1.105
84 | 1 | 14 | ŁÓDŹ KALISKA - TUPLICE | IRR1/9 | Gajewniki - Zduńska Wola tor 1 | 1 | 39.85 | 43 | Touch-up painting of substructures | 11 | 24 | 264 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 11 | single-track two-way traffic on the active track | 2024-09-19 | 2024-09-29 | 1.105
85 | 1 | 14 | ŁÓDŹ KALISKA - TUPLICE | IRR1/9 | Gajewniki - Zduńska Wola tor 2 | 2 | 39.85 | 43 | Touch-up painting of substructures | 15 | 24 | 360 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 1; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 14 | single-track two-way traffic on the active track | 2024-09-30 | 2024-10-14 | 1.105
86 | 1 | 14 | ŁÓDŹ KALISKA - TUPLICE | IRR1/9 | st. Zduńska Wola tor 2,4 | 2,4 | 41.368 | 43.02 | Touch-up painting of substructures | 15 | 24 | 360 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 15 | traffic on active track at the station | 2024-10-13 | 2024-10-27 | 1.105
87 | 1 | 14 | ŁÓDŹ KALISKA - TUPLICE | IRR1/9 | st. Zduńska Wola tor 1, 3, 5, 7 | 1, 3 ,5, 7 | 41.368 | 43.02 | Touch-up painting of substructures | 16 | 24 | 384 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 4; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 12 | traffic on active track at the station | 2024-10-28 | 2024-11-12 | 1.105
88 | 2 | 25 | ŁÓDŹ KALISKA - DĘBICA | IRR3/1 | Sandomierz - Sobów | 1 | 242.62 | 249.75 | Replacement of railroad surface, reconstruction of platforms at passenger stations, reconstruction of engineering structures, non-traction electrical and telecommunications works and associated works | 199 | 24 | 4776 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 27 | traffic interruption – single-track line | 2023-09-01 | 2024-06-27
89 | 2 | 25 | ŁÓDŹ KALISKA - DĘBICA | IRR3/1 | Sobów - Chmielów | 1 | 249.75 | 260.922 | Replacement of railroad surface, reconstruction of platforms at passenger stations, reconstruction of engineering structures, non-traction electrical and telecommunications works and associated works | 199 | 24 | 4776 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 27 | traffic interruption – single-track line | 2023-09-01 | 2024-06-27
90 | 2 | 25 | ŁÓDŹ KALISKA - DĘBICA | IRR3/1 | Chmielów - Padew | 1 | 260.922 | 275.3 | Replacement of railroad surface, reconstruction of platforms at passenger stations, reconstruction of engineering structures, non-traction electrical and telecommunications works and associated works | 170 | 24 | 4080 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 3; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption – single-track line | 2024-06-28 | 2025-04-24
91 | 2 | 26 | ŁUKÓW - RADOM | IRR1/2 | Radom Wschodni | 1 | 115.8 | 116.59 | Reconstruction of the overhead contact line, drainage and other infrastructure colliding with the construction of a platform in the intertrack space between tracks 1 and 2 of line 8 at km 101.000 – 101.400 | 21 | 6 | 126 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21 | traffic interruption | 2022-12-09 | 2023-12-31 | 4.022
92 | 2 | 26 | ŁUKÓW - RADOM | IRR1/2 | Radom Wschodni | 2 | 115.8 | 116.59 | Reconstruction of the overhead contact line, drainage and other infrastructure colliding with the construction of a platform in the intertrack space between tracks 1 and 2 of line 8 at km 101.000 – 101.400 | 21 | 6 | 126 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21 | traffic interruption | 2022-12-09 | 2023-12-31 | 4.022
93 | 1 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Białystok - Osowiec - Ełk | 1 | 3.8 | 57.232 | upgrade works | 105 | 24 | 2520 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption – single-track line | 2024-09-01 | 2024-12-14 | also planned in 2025
94 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja EŁK TOWAROWY 101,141÷103,100 | 101 | 101.141 | 103.1 | Multi-discipline upgrade works | 15 | 24 | 360 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 15 | traffic on active track at the station | 2023-01-01 | 2023-12-25 | 1.144
95 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja EŁK TOWAROWY | 103 | 101.28 | 102.19 | Multi-discipline upgrade works | 15 | 24 | 360 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 15 | traffic on active track at the station | 2023-01-01 | 2023-12-25 | 1.144
96 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja EŁK TOWAROWY 101,141÷103,100 | 102 | 101.28 | 102.19 | Multi-discipline upgrade works | 15 | 24 | 360 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 15 | traffic on active track at the station | 2023-01-01 | 2023-12-25 | 1.144
97 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja EŁK TOWAROWY | 111 | 101.303 | 102.19 | Multi-discipline upgrade works | 15 | 24 | 360 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 15 | traffic on active track at the station | 2023-01-01 | 2023-12-25 | 1.144
98 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja EŁK TOWAROWY | 105 | 101.33 | 102.19 | Multi-discipline upgrade works | 15 | 24 | 360 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 15 | traffic on active track at the station | 2023-01-01 | 2023-12-25 | 1.144
99 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja EŁK TOWAROWY | 127 | 101.349 | 102.247 | Multi-discipline upgrade works | 15 | 24 | 360 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 15 | traffic on active track at the station | 2023-01-01 | 2023-12-25 | 1.144
100 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja EŁK TOWAROWY | 129 | 101.349 | 102.213 | Multi-discipline upgrade works | 15 | 24 | 360 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 15 | traffic on active track at the station | 2023-01-01 | 2023-12-25 | 1.144
101 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja EŁK TOWAROWY | 107 | 101.357 | 102.14 | Multi-discipline upgrade works | 15 | 24 | 360 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 15 | traffic on active track at the station | 2023-01-01 | 2023-12-25 | 1.144
102 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja EŁK TOWAROWY | 109 | 101.357 | 102.14 | Multi-discipline upgrade works | 15 | 24 | 360 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 15 | traffic on active track at the station | 2023-01-01 | 2023-12-25 | 1.144
103 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Ełk Towarowy-Prostki | 1 | 101.74 | 98.8 | Multi-discipline upgrade works | 15 | 4 | 60 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 15 | traffic interruption – single-track line | 2023-01-01 | 2023-12-25 | 1.144
104 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Ełk | 1 | 102.243 | 103.994 | Multi-discipline upgrade works | 15 | 24 | 360 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 15 | traffic on active track at the station | 2023-07-01 | 2023-12-25 | 1.144
105 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Ełk | 2 | 102.857 | 103.574 | Multi-discipline upgrade works | 15 | 24 | 360 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 15 | traffic on active track at the station | 2023-07-01 | 2023-12-25 | 1.144
106 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Ełk | 6 | 102.974 | 103.574 | Multi-discipline upgrade works | 15 | 24 | 360 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 15 | traffic on active track at the station | 2023-07-01 | 2023-12-25 | 1.144
107 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Ełk | 22 | 103.225 | 103.551 | Multi-discipline upgrade works | 15 | 24 | 360 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 15 | traffic on active track at the station | 2023-07-01 | 2023-12-25 | 1.144
108 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Ełk | 24 | 103.551 | 103.782 | Multi-discipline upgrade works | 15 | 24 | 360 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 15 | traffic on active track at the station | 2023-07-01 | 2023-12-25 | 1.144
109 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Ełk - Giżycko | 1 | 103.706 | 152.85 | Track works, engineering structure works, overhead contact line, Railway Traffic Controlling system [srk], telecommunications | 55 | 24 | 1320 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 3 | traffic interruption – single-track line | 2022-03-06 | 2024-02-03 | 1.119
110 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Szlak Giżycko - Sterławki Wielkie | 1 | 152.85 | 164.615 | Track works, engineering structure works, overhead contact line, Railway Traffic Controlling system [srk], telecommunications | 369 | 24 | 8856 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption – single-track line | 2023-04-03 | 2025-03-20
111 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Giżycko - Korsze | 1 | 152.85 | 202.824 | Track works, engineering structure works, overhead contact line, Railway Traffic Controlling system [srk], telecommunications | 369 | 24 | 8856 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption – single-track line | 2023-05-04 | 2025-10-31
112 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Sterławki Wielkie | 1 | 164.615 | 166.65 | Track works, engineering structure works, overhead contact line, Railway Traffic Controlling system [srk], telecommunications | 369 | 24 | 8856 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption | 2023-03-31 | 2025-03-20
113 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Szlak Sterławki Wielkie - Kętrzyn | 1 | 166.65 | 178.7 | Track works, engineering structure works, overhead contact line, Railway Traffic Controlling system [srk], telecommunications | 369 | 24 | 8856 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption – single-track line | 2023-03-31 | 2025-03-20
114 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Kętrzyn | 1 | 178.7 | 181 | Track works, engineering structure works, overhead contact line, Railway Traffic Controlling system [srk], telecommunications | 369 | 24 | 8856 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption | 2023-03-31 | 2025-03-20
115 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Szlak Kętrzyn - Tołkiny | 1 | 181 | 191.95 | Track works, engineering structure works, overhead contact line, Railway Traffic Controlling system [srk], telecommunications | 369 | 24 | 8856 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption – single-track line | 2023-03-31 | 2025-03-20
116 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Tołkiny | 1 | 191.95 | 193.8 | Track works, engineering structure works, overhead contact line, Railway Traffic Controlling system [srk], telecommunications | 369 | 24 | 8856 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption | 2023-03-31 | 2025-03-20
117 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Szlak Tołkiny - Korsze | 1 | 193.8 | 200.1 | Track works, engineering structure works, overhead contact line, Railway Traffic Controlling system [srk], telecommunications | 369 | 24 | 8856 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption – single-track line | 2023-03-31 | 2025-03-20
118 | 5 | 38 | BIAŁYSTOK - GŁOMNO | IRR2/2 | Stacja Korsze | 1 | 200.1 | 202.826 | Track works, engineering structure works, overhead contact line, Railway Traffic Controlling system [srk], telecommunications | 369 | 24 | 8856 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption | 2023-03-31 | 2025-03-20
119 | 1 | 60 | KOBYLANY - TERESPOL (SZ) | IRR1/16 | stacja Terespol | 1S | 205.126 | 205.2 | Turnout 665 construction | 8 | 24 | 192 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 8 | traffic on active track at the station | 2024-06-10 | 2024-06-17
120 | 1 | 60 | KOBYLANY - TERESPOL (SZ) | IRR1/16 | szlak Kobylany-Terespol | 1S | 205.2 | 208.9 | Track upgrade | 31 | 24 | 744 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 15; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 16 | single-track two-way traffic on the active track | 2024-06-16 | 2024-07-16
121 | 1 | 60 | KOBYLANY - TERESPOL (SZ) | IRR1/16 | stacja Terespol | 101S | 206.5 | 208.894 | Track adjustment | 7 | 24 | 168 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 7 | traffic on active track at the station | 2024-06-18 | 2024-06-24
122 | 1 | 60 | KOBYLANY - TERESPOL (SZ) | IRR1/16 | stacja Terespol | 154 | 208.1 | 208.5 | Track upgrade | 13 | 24 | 312 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 13 | traffic on active track at the station | 2023-11-24 | 2023-12-23
123 | 1 | 60 | KOBYLANY - TERESPOL (SZ) | IRR1/16 | stacja Terespol | 102S | 208.5 | 208.9 | Integration of track 102S into track 154 | 7 | 24 | 168 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 7 | traffic on active track at the station | 2024-06-01 | 2024-06-07
124 | 3 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR3/8 | Jaroszowiec Olkuski - Olkusz | 2 | 36.237 | 43.6 | Contact line reconstruction, Olkusz station reconstruction | 188 | 24 | 4512 | 40 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-06-10 | 2025-03-07
125 | 3 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR3/8 | Jaroszowiec Olkuski - Olkusz | 1 | 36.237 | 43.6 | service interruption | 188 | 6 | 1128 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption | 2024-06-10 | 2025-03-07
126 | 3 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR3/8 | Olkusz | 2, 4, 6 | 43.6 | 46.8 | Station reconstruction | 188 | 24 | 4512 | 40 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-06-10 | 2025-03-07
127 | 3 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR3/8 | Olkusz | 1, 3 | 43.6 | 46.8 | service interruption | 188 | 6 | 1128 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption | 2024-06-10 | 2025-03-07
128 | 3 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR3/8 | Olkusz - Bukowno | 2 | 46.8 | 51.825 | Contact line reconstruction, Olkusz station reconstruction | 188 | 24 | 4512 | 40 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-06-10 | 2025-03-07
129 | 3 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR3/8 | Olkusz - Bukowno | 1 | 46.8 | 51.825 | service interruption | 188 | 6 | 1128 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption | 2024-06-10 | 2025-03-07
130 | 4 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR4/4 | Sosnowiec Południowy - Sosnowiec Główny | 1 | 83.35 | 83.7 | upgrade | 32 | 24 | 768 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 25; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 7 | traffic interruption – single-track line | 2024-07-07 | 2024-08-07
131 | 4 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR4/4 | stacja Sosnowiec Główny | 4 | 83.7 | 84.95 | upgrade | 206 | 24 | 4944 | 60 km/h | no limit |  | 18 | 28 | 31 | 30 | 31 | 30 | 31 | 7 |  |  |  |  | traffic on active track at the station | 2024-01-14 | 2024-08-07
132 | 4 | 62 | TUNEL - SOSNOWIEC GŁÓWNY | IRR4/4 | stacja Sosnowiec Główny | 6,8,10 | 84.15 | 84.95 | upgrade | 206 | 24 | 4944 | 60 km/h | no limit |  | 18 | 28 | 31 | 30 | 31 | 30 | 31 | 7 |  |  |  |  | traffic on active track at the station | 2024-01-14 | 2024-08-07
133 | 2 | 64 | KOZŁÓW - KONIECPOL | IRR3/1 | podg Sprowa - Kozłów | 1 | 1.2 | 1.6 | Upgrade of the line/reconstruction of the track system and other infrastructure components | 35 | 24 | 840 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-11-09 | 2025-03-11
134 | 2 | 64 | KOZŁÓW - KONIECPOL | IRR3/1 | podg Sprowa - Kozłów | 2 | 1.2 | 1.6 | Upgrade of the line/reconstruction of the track system and other infrastructure components | 35 | 4 | 140 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption | 2024-11-09 | 2025-03-11
135 | 2 | 74 | SOBÓW - STALOWA WOLA ROZWADÓW | IRR3/1 | Sobów - Grębów | 1 | -1.021 | 8.577 | Replacement of railroad surface, reconstruction of platforms at passenger stations, reconstruction of engineering structures, non-traction electrical and telecommunications works and associated works | 151 | 24 | 3624 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 13; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 16 | traffic interruption – single-track line | 2024-03-19 | 2024-08-16
136 | 2 | 74 | SOBÓW - STALOWA WOLA ROZWADÓW | IRR3/1 | Grębów - Zbydniów | 1 | 8.577 | 17.035 | Replacement of railroad surface, reconstruction of platforms at passenger stations, reconstruction of engineering structures, non-traction electrical and telecommunications works and associated works | 120 | 24 | 2880 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 15; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | Traffic interruption | 2024-08-17 | 2025-03-15
137 | 2 | 74 | SOBÓW - STALOWA WOLA ROZWADÓW | IRR3/1 | Grębów - Zbydniów | 2 | 8.577 | 17.035 | Carrying out and supervision of overhead contact line network works, unloading materials, switching of Railway Traffic Controlling system [srk] equipment. | 120 | 4 | 480 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 15; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-08-17 | 2025-03-15
138 | 2 | 74 | SOBÓW - STALOWA WOLA ROZWADÓW | IRR3/1 | Zbydniów - Stalowa Wola | 1 | 17.035 | 23.124 | Replacement of railroad surface, reconstruction of platforms at passenger stations, reconstruction of engineering structures, non-traction electrical and telecommunications works and associated works | 369 | 24 | 8856 | no limit | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | single-track two-way traffic on the active track | 2023-09-01 | 2025-03-24
139 | 2 | 74 | SOBÓW - STALOWA WOLA ROZWADÓW | IRR3/1 | Zbydniów - Stalowa Wola | 2 | 17.035 | 23.124 | Carrying out and supervision of overhead contact line network works, unloading materials, switching of Railway Traffic Controlling system [srk] equipment. | 369 | 4 | 1476 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | Traffic interruption | 2023-09-01 | 2025-03-24
140 | 2 | 78 | SANDOMIERZ - GRĘBÓW | IRR3/1 | Sandomierz - Grębów | 1 | 1.42 | 10.784 | Replacement of railroad surface, reconstruction of platforms at passenger stations, reconstruction of engineering structures, non-traction electrical and telecommunications works and associated works | 98 | 24 | 2352 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 18 | traffic interruption – single-track line | 2023-08-31 | 2024-03-18
141 | 4 | 90 | ZEBRZYDOWICE - CIESZYN | IRR4/4 | Zebrzydowice - Kaczyce | 1 | 13.9 | 14.3 | upgrade | 188 | 24 | 4512 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 16 | traffic interruption – single-track line | 2023-11-06 | 2024-06-16
142 | 3 | 91 | KRAKÓW GŁÓWNY - MEDYKA | IRR3/6 | Żurawica - Przemyśl | 1, 2 | 242.962 | 244.234 | Reconstruction of the bridge at km 243.845 (Przemyśl) | 19 | 6 | 114 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 19 | traffic interruption | 2022-08-29 | 2023-12-29 | 1.067
143 | 4 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR4/4 | Zabrzeg - Bronów | 1, 2 | 53.1 | 58.5 | upgrade | 362 | 24 | 8688 | traffic interruption | no limit | 14 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption | 2023-12-18 | 2024-12-17
144 | 4 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR4/4 | Bronów - Chybie | 1, 2 | 58.5 | 60.2 | upgrade | 181 | 24 | 4344 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 14; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption | 2024-06-17 | 2024-12-17
145 | 4 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR4/4 | stacja Chybie | 2,4,6 | 60.2 | 62 | upgrade | 188 | 24 | 4512 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 16 | traffic on active track at the station | 2023-11-06 | 2024-06-16
146 | 4 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR4/4 | stacja Chybie | 2,4,6 1 (od rozj. 15 do rozj. 55) | 60.2 | 62 | upgrade | 181 | 24 | 4344 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 14; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-06-17 | 2024-12-17
147 | 4 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR4/4 | stacja Pruchna | 2, 4, 6 | 69.1 | 70.2 | upgrade | 188 | 24 | 4512 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 16 | traffic on active track at the station | 2023-11-06 | 2024-06-16
148 | 4 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR4/4 | stacja Zebrzydowice | 6, 8, 7-15, 100-109 | 76 | 77.8 | upgrade | 7 | 24 | 168 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 7 | traffic on active track at the station | 2023-11-06 | 2023-12-17
149 | 4 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR4/4 | stacja Zebrzydowice | 6, 8, 7-15, 17, 100-109, 503 | 76 | 77.8 | upgrade | 181 | 24 | 4344 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 16 | traffic on active track at the station | 2023-12-18 | 2024-06-16
150 | 4 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR4/4 | stacja Zebrzydowice | 1, 2 | 76 | 77.8 | upgrade | 14 | 24 | 336 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 4; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 10 | traffic on active track at the station | 2024-04-27 | 2024-05-10
151 | 4 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR4/4 | stacja Zebrzydowice | 1-17, 6-8, 100-109, 301-303, 503 | 76 | 77.8 | upgrade | 181 | 24 | 4344 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 14; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-06-17 | 2024-12-17
152 | 4 | 93 | TRZEBINIA - ZEBRZYDOWICE | IRR4/4 | Zebrzydowice - granica państwa | 1 | 77.8 | 80.66 | upgrade | 181 | 24 | 4344 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 14; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-06-17 | 2024-12-17
153 | 3 | 97 | SKAWINA - ŻYWIEC | IRR3/2 | Sucha Beskidzka - Żywiec | 1 | 46.239 | 81.392 | Line upgrade | 258 | 24 | 6192 | traffic interruption | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption – single-track line | 2024-04-01 | 2025-10-31
154 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | szlak Sucha Beskidzka - Maków Podhalański | 1 | 0.818 | 6.629 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption – single-track line | 2023-09-01 | 2023-12-21 | 1.136
155 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | szlak Sucha Beskidzka - Maków Podhalański | 1 | 0.818 | 6.629 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-03-01 | 2024-06-21 | 1.136
156 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | Maków Podhalański-Osielec | 1 | 7.761 | 16.116 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption – single-track line | 2023-09-01 | 2023-12-21 | 1.136
157 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | Maków Podhalański-Osielec | 1 | 7.761 | 16.116 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-03-01 | 2024-06-21 | 1.136
158 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | stacja Osielec | 1,2,3,4 | 15.661 | 17.6 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption | 2024-03-01 | 2024-06-21 | 1.136
159 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | stacja Osielec | 1,2,3,4 | 16.116 | 16.832 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption | 2023-09-01 | 2023-12-21 | 1.136
160 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | szlak Osielec - Jordanów | 1 | 17.6 | 23.752 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption – single-track line | 2023-09-01 | 2023-12-21 | 1.136
161 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | szlak Osielec - Jordanów | 1 | 17.6 | 23.752 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-03-01 | 2024-06-21 | 1.136
162 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | stacja Jordanów | 1,3 | 23.752 | 25.335 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption | 2023-09-01 | 2023-12-21 | 1.136
163 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | stacja Jordanów | 1,3 | 23.752 | 25.335 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption | 2024-03-01 | 2024-06-21 | 1.136
164 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | szlak Jordanów - MPO Skawa | 1 | 25.335 | 27.386 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-03-01 | 2024-06-21 | 1.136
165 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | MPO Skawa | 1,3 | 27.386 | 28.912 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption | 2023-09-01 | 2023-12-21 | 1.136
166 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | MPO Skawa | 1,3 | 27.386 | 28.912 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption | 2023-09-01 | 2023-12-21 | 1.136
167 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | Skawa | 1,3 | 27.386 | 28.912 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption | 2023-09-01 | 2023-12-21 | 1.136
168 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | MPO Skawa | 1,3 | 27.386 | 28.912 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption | 2024-03-01 | 2024-06-21 | 1.136
169 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | Skawa | 1,3 | 27.386 | 28.912 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption | 2024-03-01 | 2024-06-21 | 1.136
170 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | Skawa - Chabówka | 1 | 28.912 | 34.114 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption – single-track line | 2023-09-01 | 2023-12-21 | 1.136
171 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | szlak MPO Skawa - Chabówka | 1 | 28.912 | 34.114 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption – single-track line | 2023-09-01 | 2023-12-21 | 1.136
172 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | szlak MPO Skawa - Chabówka | 1 | 28.912 | 34.114 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption – single-track line | 2023-09-01 | 2023-12-21 | 1.136
173 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | Skawa - Chabówka | 1 | 28.912 | 34.114 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-03-01 | 2024-06-21 | 1.136
174 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | szlak MPO Skawa - Chabówka | 1 | 28.912 | 34.114 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-03-01 | 2024-06-21 | 1.136
175 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | stacja Chabówka | 1 | 34.114 | 35.313 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption | 2023-09-01 | 2023-12-21 | 1.136
176 | 3 | 98 | SUCHA BESKIDZKA - CHABÓWKA | IRR3/2 | stacja Chabówka | 1 | 34.114 | 35.313 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption | 2024-03-01 | 2024-06-21 | 1.136
177 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Chabówka | 1,2,4,5,6,7,8,9,10,11,11a,12,12a,13,14,15,16,18 | -0.334 | 0.858 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption | 2023-09-01 | 2023-12-21 | 1.136
178 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Chabówka | 1,2,4,5,6,7,8,9,10,11,11a,12,12a,13,14,15,16,18 | -0.334 | 0.858 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption | 2024-03-01 | 2024-06-21 | 1.136
179 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Chabówka - Raba Wyżna | 1 | 0.858 | 4.733 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption – single-track line | 2023-09-01 | 2023-12-21 | 1.136
180 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Chabówka - Raba Wyżna | 1 | 0.858 | 4.733 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-03-01 | 2024-06-21 | 1.136
181 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Raba Wyżna | 1,2,3,5 | 4.773 | 6.442 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption | 2023-09-01 | 2023-12-21 | 1.136
182 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Raba Wyżna | 1,2,3,5 | 4.773 | 6.442 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption | 2024-03-01 | 2024-06-21 | 1.136
183 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Raba Wyżna - Sieniawa | 1 | 6.442 | 10.026 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption – single-track line | 2023-09-01 | 2023-12-21 | 1.136
184 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Raba Wyżna - Sieniawa | 1 | 6.442 | 10.026 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-03-01 | 2024-06-21 | 1.136
185 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Sieniawa | 1,2,3,5 | 10.026 | 11.791 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption | 2023-09-01 | 2023-12-21 | 1.136
186 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Sieniawa | 1,2,3,5 | 10.026 | 11.791 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption | 2024-03-01 | 2024-06-21 | 1.136
187 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Sieniawa - Lasek | 1 | 11.791 | 17.505 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption – single-track line | 2023-09-01 | 2023-12-21 | 1.136
188 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Sieniawa - Lasek | 1 | 11.791 | 17.505 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-03-01 | 2024-06-21 | 1.136
189 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Lasek | 1,2,3 | 17.505 | 18.797 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption | 2023-09-01 | 2023-12-21 | 1.136
190 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Lasek | 1,2,3 | 17.505 | 18.797 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption | 2024-03-01 | 2024-06-21 | 1.136
191 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Lasek - Nowy Targ | 1 | 18.797 | 21.864 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption – single-track line | 2023-09-01 | 2023-12-21 | 1.136
192 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Lasek - Nowy Targ | 1 | 18.797 | 21.864 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-03-01 | 2024-06-21 | 1.136
193 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Nowy Targ | 1,2,3,4,5,6,17,7a,7b,11,13,15,19,21 | 21.864 | 23.611 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption | 2023-09-01 | 2023-12-21 | 1.136
194 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Nowy Targ | 1,2,3,4,5,6,17,7a,7b,11,13,15,19,21 | 21.864 | 23.611 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption | 2024-03-01 | 2024-06-21 | 1.136
195 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Nowy Targ-Szaflary | 1 | 23.611 | 25.511 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption – single-track line | 2023-09-01 | 2023-12-21 | 1.136
196 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Nowy Targ-Szaflary | 1 | 23.611 | 25.511 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-03-01 | 2024-06-21 | 1.136
197 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Szaflary | 1,2,3,4 | 25.511 | 27.318 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption | 2023-09-01 | 2023-12-21 | 1.136
198 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Szaflary | 1,2,3,4 | 25.511 | 27.318 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption | 2024-03-01 | 2024-06-21 | 1.136
199 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Szaflary-Biały Dunajec | 1 | 27.318 | 32.88 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption – single-track line | 2023-09-01 | 2023-12-21 | 1.136
200 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Szaflary-Biały Dunajec | 1 | 27.318 | 32.88 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-03-01 | 2024-06-21 | 1.136
201 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Biały Dunajec | 1,2,3,4 | 32.88 | 34.736 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption | 2023-09-01 | 2023-12-21 | 1.136
202 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Stacja Biały Dunajec | 1,2,3,4 | 32.88 | 34.736 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption | 2024-03-01 | 2024-06-21 | 1.136
203 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Biały Dunajec - Poronin | 1 | 34.736 | 37.117 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption – single-track line | 2023-09-01 | 2023-12-21 | 1.136
204 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Biały Dunajec - Poronin | 1 | 34.736 | 37.117 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-03-01 | 2024-06-21 | 1.136
205 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Statcja Poronin | 1,2,3,4 | 37.117 | 38.433 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption | 2023-09-01 | 2023-12-21 | 1.136
206 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Statcja Poronin | 1,2,3,4 | 37.117 | 38.433 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption | 2024-03-01 | 2024-06-21 | 1.136
207 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Poronin-Zakopane | 1 | 37.75 | 41.778 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption – single-track line | 2023-09-01 | 2023-12-21 | 1.136
208 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Poronin-Zakopane | 1 | 37.75 | 41.778 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-03-01 | 2024-06-21 | 1.136
209 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/2 | Zakopane | 1,2,3,4,5,6,21,23 | 41.778 | 43.451 | line upgrade | 11 | 24 | 264 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 11 | traffic interruption | 2023-01-01 | 2023-12-21 | 1.136
210 | 3 | 99 | CHABÓWKA - ZAKOPANE | IRR3/3 | Zakopane | 1,2,3,4,5,6,21,24 | 41.778 | 43.451 | line upgrade | 113 | 24 | 2712 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption | 2024-03-01 | 2024-06-21 | 1.137
211 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/7 | Chabówka - Rabka Zaryte | 1 | 0.576 | 5.142 | line upgrade | 362 | 24 | 8688 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 7 | traffic interruption – single-track line | 2022-11-06 | 2024-12-07
212 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/7 | Rabka Zaryte | 1,3 | 5.142 | 5.841 | line upgrade | 362 | 24 | 8688 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 7 | traffic interruption | 2022-11-06 | 2024-12-07
213 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/7 | Rabka Zaryte - Mszana Dolna | 1 | 5.841 | 14.393 | line upgrade | 369 | 24 | 8856 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption – single-track line | 2022-11-06 | 2025-06-14
214 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/7 | Mszana Dolna | 1,3 | 14.393 | 15.091 | line upgrade | 369 | 24 | 8856 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption | 2023-06-11 | 2025-06-14 | 1.201
215 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/7 | Mszana Dolna - Tymbark | 1 | 15.091 | 36.35 | line upgrade | 369 | 24 | 8856 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption – single-track line | 2023-06-11 | 2025-06-14 | 1.201
216 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/7 | Tymbark | 1, 2 | 36.35 | 37.352 | line upgrade | 263 | 24 | 6312 | traffic interruption | no limit |  |  |  | 5 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption | 2024-03-27 | 2026-06-29 | 1.148
217 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/7 | Tymbark - Limanowa | 1 | 37.352 | 46.768 | line upgrade | 369 | 24 | 8856 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption – single-track line | 2023-03-12 | 2026-03-14 | 1.201
218 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/7 | Limanowa | 1,2,3,3a,4 | 46.768 | 47.569 | line upgrade | 369 | 24 | 8856 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption | 2023-03-12 | 2026-03-14 | 1.201
219 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/7 | Limanowa - Marcinkowice | 1 | 47.569 | 66.969 | line upgrade | 362 | 24 | 8688 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 7 | traffic interruption – single-track line | 2022-11-06 | 2024-12-07 | 1.201
220 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/7 | Limanowa - bocznica szlakowa Klęczany | 1 | 47.569 | 64.459 | line upgrade | 289 | 24 | 6936 | traffic interruption | no limit |  |  |  | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption – single-track line | 2024-03-01 | 2027-03-04 | 1.148
221 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/7 | Marcinkowice | 1, 2, 3, 3a, 4 | 66.969 | 67.81 | line upgrade | 362 | 24 | 8688 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 7 | traffic interruption | 2022-11-06 | 2024-12-07
222 | 3 | 104 | CHABÓWKA - NOWY SĄCZ | IRR3/7 | Marcinkowice - Nowy Sącz | 1 | 67.81 | 76.652 | line upgrade | 362 | 24 | 8688 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 7 | traffic interruption – single-track line | 2022-11-06 | 2024-12-07
223 | 3 | 108 | STRÓŻE - KROŚCIENKO | IRR3/6 | Gorlice Zagórzany-Biecz | 1 | 19.6 | 27.028 | Replacement of track surface, installation of switches, reconstruction of track systems, centralisation of the Railway Traffic Controlling system [srk] equipment, reconstruction of contact lines | 107 | 24 | 2568 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 2; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption – single-track line | 2024-08-30 | 2025-05-06
224 | 4 | 127 | RADZIONKÓW - TARNOWSKIE GÓRY TGB T3 | IRR4/5 | Szlak Radzionków - Nakło | T3 | 28.12 | 30.143 | Closing the tangent line | 111 | 24 | 2664 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31 | traffic interruption – single-track line | 2023-04-01 | 2024-03-31 | 1.095
225 | 4 | 128 | RADZIONKÓW - NAKŁO ŚLĄSKIE T4 | IRR4/5 | Szlak Radzionków - Nakło | T4 | 28.13 | 30.143 | Closing the tangent line | 259 | 24 | 6216 | traffic interruption | no limit |  |  |  | 1 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption – single-track line | 2024-03-31 | 2025-03-31 | 1.095
226 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | stacja Chorzów Stary | 2, 22,24,26, 6,10,12,14 | 11.68 | 12.82 | surface replacement, construction of engineering structures, replacement of contact line | 95 | 24 | 2280 | 40 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 15 | traffic on active track at the station | 2023-03-15 | 2024-03-15 | 1.095
227 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | stacja Chorzów Stary | 1, 3, 5, 7, 9 | 11.68 | 12.82 | surface replacement, construction of engineering structures, replacement of contact line | 275 | 24 | 6600 | 40 km/h | no limit |  |  |  | 17 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic on active track at the station | 2024-03-15 | 2025-03-15 | 1.095
228 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Chorzów Stary - Bytom | 2 | 12.85 | 16.85 | surface replacement, construction of engineering structures, replacement of contact line | 111 | 24 | 2664 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31 | single-track two-way traffic on the active track | 2023-04-01 | 2024-03-31 | 1.095
229 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Chorzów Stary - Bytom | 1 | 12.85 | 16.85 | transport of materials on the active track | 111 | 4 | 444 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31 | traffic interruption | 2023-04-01 | 2024-03-31 | 1.095
230 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Chorzów Stary - Bytom | 1 | 13 | 16.75 | surface replacement, construction of engineering structures, replacement of contact line | 258 | 24 | 6192 | 50 km/h | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | single-track two-way traffic on the active track | 2024-04-01 | 2025-03-31 | 1.095
231 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Chorzów Stary - Bytom | 2 | 13 | 16.75 | transport of materials on the active track | 258 | 4 | 1032 | traffic interruption | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption | 2024-04-01 | 2025-03-31 | 1.095
232 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | stacja Bytom | 1, 3,5,7,11,13, 1a, 2a, 3a, 4a, 5a, 7a, 8a, 9a, 9b, 11a, 11b, 13a, 13b, 49a, | 16.85 | 18.55 | surface replacement, construction of engineering structures, replacement of contact line | 91 | 24 | 2184 | 40 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 11 | traffic on active track at the station | 2022-09-12 | 2024-03-11 | 1.095
233 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | stacja Bytom | 2, 4,6,9,10,16,18, 20,24,26,28,30,32, 34, 36, 38, 40, 42 | 16.85 | 18.55 | surface replacement, construction of engineering structures, replacement of contact line | 91 | 24 | 2184 | 40 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 11 | traffic on active track at the station | 2022-09-12 | 2024-03-11 | 1.095
234 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Bytom - Bytom Karb | 2 | 18.5 | 20.15 | surface replacement, construction of engineering structures, replacement of contact line | 258 | 24 | 6192 | 50 km/h | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | single-track two-way traffic on the active track | 2024-04-01 | 2025-03-31 | 1.095
235 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Bytom - Bytom Karb | 1 | 18.5 | 20.15 | delivery of materials on active track | 258 | 4 | 1032 | traffic interruption | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption | 2024-04-01 | 2025-03-31 | 1.095
236 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Bytom - Bytom Karb | 1 | 18.55 | 20.4 | surface replacement, construction of engineering structures, replacement of contact line | 111 | 24 | 2664 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31 | single-track two-way traffic on the active track | 2023-04-01 | 2024-03-31 | 1.095
237 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Bytom - Bytom Karb | 2 | 18.55 | 20.4 | delivery of materials on active track | 111 | 4 | 444 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31 | traffic interruption | 2023-04-01 | 2024-03-31 | 1.095
238 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | stacja Bytom Karb | 2 | 20.15 | 21.04 | transport of materials on the active track | 111 | 4 | 444 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31 | traffic interruption | 2023-04-01 | 2024-03-31 | 1.095
239 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | stacja Bytom Karb | 2, 4, 6 | 20.15 | 21.1 | surface replacement, construction of engineering structures, replacement of contact line | 258 | 24 | 6192 | 40 km/h | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic on active track at the station | 2024-04-01 | 2025-03-31 | 1.095
240 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | stacja Bytom Karb | 1 | 20.15 | 21.04 | transport of materials on the active track | 258 | 4 | 1032 | traffic interruption | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption | 2024-04-01 | 2025-03-31 | 1.095
241 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | stacja Bytom Karb | 1, 3,3a, 3b | 20.4 | 21.04 | surface replacement, construction of engineering structures, replacement of contact line | 111 | 24 | 2664 | 40 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31 | traffic on active track at the station | 2023-04-01 | 2024-03-31 | 1.095
242 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Bytom Północny - Radzionków | 1 | 21.04 | 26.8 | surface replacement, construction of engineering structures, replacement of contact line | 21 | 24 | 504 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21 | single-track two-way traffic on the active track | 2022-09-04 | 2023-12-31 | 1.095
243 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Bytom Północny - Radzionków | 2 | 21.04 | 26.8 | delivery of materials on active track | 21 | 4 | 84 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21 | traffic interruption | 2022-09-04 | 2023-12-31 | 1.095
244 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Bytom Karb - Bytom Północny | 1 | 21.04 | 26.8 | surface replacement, construction of engineering structures, replacement of contact line | 111 | 24 | 2664 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31 | single-track two-way traffic on the active track | 2023-04-01 | 2024-03-31 | 1.095
245 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Bytom Karb - Bytom Północny | 2 | 21.04 | 26.8 | delivery of materials on active track | 111 | 4 | 444 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31 | traffic interruption | 2023-04-01 | 2024-03-31 | 1.095
246 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Bytom Północny - Radzionków | 2 | 21.04 | 26.8 | surface replacement, construction of engineering structures, replacement of contact line | 348 | 24 | 8352 | 50 km/h | no limit |  | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | single-track two-way traffic on the active track | 2024-01-01 | 2024-12-31 | 1.095
247 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Bytom Północny - Radzionków | 1 | 21.04 | 26.8 | delivery of materials on active track | 348 | 4 | 1392 | traffic interruption | no limit |  | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption | 2024-01-01 | 2024-12-31 | 1.095
248 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Bytom Karb - Bytom Północny | 1 | 21.1 | 26.8 | delivery of materials on active track | 258 | 4 | 1032 | traffic interruption | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption | 2024-04-01 | 2024-12-30 | 1.095
249 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Bytom Karb - Bytom Północny | 2 | 21.1 | 26.8 | surface replacement, construction of engineering structures, replacement of contact line | 258 | 24 | 6192 | 50 km/h | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | single-track two-way traffic on the active track | 2024-04-01 | 2025-03-31 | 1.095
250 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | stacja Radzionków | 1, 3, 5 | 26.8 | 28 | surface replacement, construction of engineering structures, replacement of contact line | 111 | 24 | 2664 | 40 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31 | traffic on active track at the station | 2023-04-01 | 2024-03-31 | 1.095
251 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | stacja Radzionków | 2 | 26.8 | 28 | transport of materials on the active track | 111 | 4 | 444 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31 | traffic interruption | 2023-04-01 | 2024-03-31 | 1.095
252 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | stacja Radzionków | 2, 4, 6, 8 | 26.8 | 27.95 | surface replacement, construction of engineering structures, replacement of contact line | 258 | 24 | 6192 | 40 km/h | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic on active track at the station | 2024-04-01 | 2025-03-31 | 1.095
253 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | stacja Radzionków | 1 | 26.8 | 27.95 | transport of materials on the active track | 258 | 4 | 1032 | traffic interruption | no limit |  |  |  |  | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption | 2024-04-01 | 2025-03-31 | 1.095
254 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Radzionków - Nakło Śląskie | 1 | 28 | 29.5 | surface replacement, construction of engineering structures, replacement of contact line | 111 | 24 | 2664 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31 | single-track two-way traffic on the active track | 2023-04-01 | 2024-03-31 | 1.095
255 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Radzionków - Nakło Śląskie | 2 | 28 | 29.5 | delivery of materials on active track | 111 | 4 | 444 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31 | traffic interruption | 2023-04-01 | 2024-03-31 | 1.095
256 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak TGE - Kalety | 1 | 39.558 | 46.93 | surface replacement, construction of engineering structures, replacement of contact line | 70 | 24 | 1680 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 26; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-10-06 | 2025-03-05
257 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak TGE - Kalety | 2 | 39.558 | 46.93 | process transport | 70 | 4 | 280 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 26; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption | 2024-10-06 | 2025-03-05
258 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | stacja Boronów | 1 | 58.721 | 59.678 | surface replacement, construction of engineering structures, replacement of contact line | 70 | 24 | 1680 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 26; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-10-06 | 2025-03-05
259 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | stacja Boronów | 2 | 58.721 | 59.678 | process transport | 70 | 4 | 280 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 26; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption | 2024-10-06 | 2025-03-05
260 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Rusiec Łódzki - Chociw Łaski | 1 | 136.465 | 146.56 | works on the bridge at km 138.402 | 141 | 24 | 3384 | 30 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30 | single-track two-way traffic on the active track | 2023-09-29 | 2024-04-30 | 1.095
261 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Rusiec Łódzki - Chociw Łaski | 2 | 136.465 | 146.56 | transport of materials on the active track | 141 | 4 | 564 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30 | traffic interruption | 2023-10-02 | 2024-04-30 | 1.095
262 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Chociw Łaski - Kozuby | 1 | 146.85 | 156.65 | works on the bridge at km 148.394 | 141 | 24 | 3384 | 30 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30 | single-track two-way traffic on the active track | 2023-09-29 | 2024-04-30 | 1.095
263 | 4 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Chociw Łaski - Kozuby | 2 | 146.85 | 156.65 | transport of materials on the active track | 141 | 4 | 564 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30 | traffic interruption | 2023-10-02 | 2024-04-30 | 1.095
264 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Kozuby - Zduńska Wola Karsznice | 1 | 157.112 | 167.593 | works on the bridge at km 155.639 and 161.848 and on the viaduct at km 160.967 | 141 | 24 | 3384 | 30 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30 | single-track two-way traffic on the active track | 2023-09-29 | 2024-04-30 | 1.095
265 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR4/5 | szlak Kozuby - Zduńska Wola Karsznice | 2 | 157.112 | 167.593 | transport of materials on the active track | 141 | 4 | 564 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30 | traffic interruption | 2023-10-02 | 2024-04-30 | 1.095
266 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Szlak Zduńska Wola Karsznice - Szadek | 2 | 170.2 | 178.45 | end-to-end surface replacement | 105 | 24 | 2520 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-09-01 | 2025-05-01
267 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Szlak Szadek - Otok | 2 | 180.4 | 190.3 | end-to-end surface replacement | 201 | 24 | 4824 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 17; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31 | single-track two-way traffic on the active track | 2024-02-12 | 2024-08-31
268 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Stacja Otok | 2,4 | 190.3 | 192.6 | end-to-end surface replacement | 8 | 24 | 192 | 40 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 8 | traffic on active track at the station | 2024-12-02 | 2025-06-02
269 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Szlak Otok - Poddębice | 2 | 192.6 | 201.8 | end-to-end surface replacement | 8 | 24 | 192 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 8 | single-track two-way traffic on the active track | 2024-12-02 | 2025-06-02
270 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Stacja Poddębice | 2,4 | 201.8 | 203.9 | end-to-end surface replacement | 140 | 24 | 3360 | 40 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 17; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 1 | traffic on active track at the station | 2024-02-12 | 2024-07-01
271 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Stacja Poddębice | 1,3 | 201.8 | 203.9 | end-to-end surface replacement | 153 | 24 | 3672 | 40 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 1 | traffic on active track at the station | 2024-07-02 | 2024-12-01
272 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Szlak Poddębice - Kłudna | 2 | 203.9 | 211.7 | end-to-end surface replacement | 140 | 24 | 3360 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 17; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 1 | single-track two-way traffic on the active track | 2024-02-12 | 2024-07-01
273 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Szlak Poddębice - Kłudna | 1 | 203.9 | 211.7 | end-to-end surface replacement | 153 | 24 | 3672 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 1 | single-track two-way traffic on the active track | 2024-07-02 | 2024-12-01
274 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Stacja Kłudna | 1,3 | 211.7 | 213.7 | end-to-end surface replacement | 8 | 24 | 192 | 40 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 8 | traffic on active track at the station | 2024-12-02 | 2025-05-01
275 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Szlak Kłudna - Kraski | 1 | 213.7 | 220.2 | end-to-end surface replacement | 8 | 24 | 192 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 8 | single-track two-way traffic on the active track | 2024-12-02 | 2025-05-01
276 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Stacja Kraski | 1,3 | 220.2 | 222.3 | end-to-end surface replacement | 140 | 24 | 3360 | 40 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 17; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 1 | traffic on active track at the station | 2024-02-12 | 2024-07-01
277 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Stacja Kraski | 2,4 | 220.2 | 222.3 | end-to-end surface replacement | 153 | 24 | 3672 | 40 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 1 | traffic on active track at the station | 2024-07-02 | 2024-12-01
278 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Kraski-Dąbie nad Nerem | 1 | 222.3 | 228.6 | end-to-end surface replacement | 140 | 24 | 3360 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 17; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 1 | single-track two-way traffic on the active track | 2024-02-12 | 2024-07-01
279 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Kraski-Dąbie nad Nerem | 2 | 222.3 | 228.6 | end-to-end surface replacement | 153 | 24 | 3672 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 1 | single-track two-way traffic on the active track | 2024-07-02 | 2024-12-01
280 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Dąbie nad Nerem (+2,4,8) - Kraski | 2 | 222.3 | 228.6 | end-to-end surface replacement | 15 | 24 | 360 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 1; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-11-30 | 2025-04-28
281 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Stacja Ponętów | 1 | 239.7 | 241.69 | end-to-end surface replacement, installation of Rz29 Ponętów station | 15 | 24 | 360 | 40 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 1; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-11-30 | 2025-01-28
282 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Ponętów - Lipie Góry | 1 | 241.69 | 250.7 | Installation of switches 28 and 34 at Ponętów station | 30 | 24 | 720 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 30 | single-track two-way traffic on the active track | 2024-07-02 | 2024-07-31
283 | 5 | 544 | ZAMKÓW - BORYSŁAWICE | IRR2/9 | Zamków - Borysławice | 1 |  |  | Installation of switches 6 and 7 in Borysławice Podg. | 30 | 24 | 720 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 30 | traffic interruption | 2024-07-02 | 2024-07-31
284 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Ponętów - Lipie Góry | 2 | 241.69 | 250.7 | Installation of turnouts 27, 31, 33 at Ponętów station | 31 | 24 | 744 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31 | single-track two-way traffic on the active track | 2024-08-01 | 2024-08-31
285 | 5 | 809 | BARŁOGI - BORYSŁAWICE | IRR2/9 | Barłogi - Borysławice | 1 |  |  | Installation of switches 5 and 8 in Borysławice Podg. | 31 | 24 | 744 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31 | traffic interruption | 2024-08-01 | 2024-08-31
286 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Lipie Góry (+1,3) - Babiak | 1,3 | 252.46 | 259.6 | end-to-end surface replacement | 87 | 24 | 2088 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 12; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-09-19 | 2025-02-15
287 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Inowrocław Rąbinek (2,4,6,8,10,12) | 2 | 316.95 | 318.8 | end-to-end surface replacement | 105 | 24 | 2520 | 40 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-09-01 | 2024-12-29
288 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Stacja Nowa Wieś Wielka | 15 | 345.2 | 345.9 | Reconstruction of the track system | 52 | 24 | 1248 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 8; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-10-24 | 2025-03-12
289 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Szlak Nowa Wieś Wielka - Brzoza Bydgoska | 1 | 347 | 353.5 | Installation of new switches | 15 | 24 | 360 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 8; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 7 | single-track two-way traffic on the active track | 2024-10-24 | 2024-11-07
290 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Szlak Brzoza Bydgoska - Nowa Wieś Wielka (+2) | 2 | 347.1 | 353.5 | Installation of new switches | 15 | 24 | 360 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 15 | single-track two-way traffic on the active track | 2024-11-08 | 2024-11-22
291 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/9 | Szlak Brzoza Bydgoska (+2, 4) - Trzciniec | 2,4 | 353.6 | 362.35 | end-to-end surface replacement, reconstruction in other areas | 21 | 24 | 504 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 7; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-11-24 | 2025-04-07
292 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/7 | Kotomierz - Maksymilianowo | 2 | 380.2 | 388.614 | end-to-end upgrade | 90 | 24 | 2160 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 20; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 9 | single-track two-way traffic on the active track | 2024-07-12 | 2024-10-09
293 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/7 | Kotomierz - Maksymilianowo | 1 | 380.414 | 388.849 | installation of Rz301 | 15 | 24 | 360 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 15 | single-track two-way traffic on the active track | 2024-04-13 | 2024-04-27
294 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/7 | Maksymilianowo - Kotomierz | 1 | 380.414 | 388.849 | end-to-end upgrade | 66 | 24 | 1584 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 22; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-10-10 | 2025-02-06
295 | 5 | 131 | CHORZÓW BATORY - TCZEW | IRR2/7 | Kotomierz - Maksymilianowo | 2 | 380.48 | 388.614 | installation of Rz302 | 15 | 24 | 360 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 3; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 12 | single-track two-way traffic on the active track | 2024-03-29 | 2024-04-12
296 | 4 | 132 | BYTOM - WROCŁAW GŁÓWNY | IRR4/5 | Szlak Bytom - Bytom Bobrek | 2 | 18.35 | 18.92 | Closing the tangent line | 167 | 24 | 4008 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-07-01 | 2025-03-31 | 1.095
297 | 4 | 132 | BYTOM - WROCŁAW GŁÓWNY | IRR4/5 | Szlak Bytom - Bytom Bobrek | 1 | 18.35 | 18.92 | delivery of materials on active track | 167 | 4 | 668 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption | 2024-07-01 | 2025-03-31 | 1.095
298 | 4 | 132 | BYTOM - WROCŁAW GŁÓWNY | IRR4/5 | Szlak Bytom - Bytom Bobrek | 1 | 18.74 | 18.92 | Closing the tangent line | 202 | 24 | 4848 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30 | single-track two-way traffic on the active track | 2023-09-01 | 2024-06-30 | 1.095
299 | 4 | 132 | BYTOM - WROCŁAW GŁÓWNY | IRR4/5 | Szlak Bytom - Bytom Bobrek | 2 | 18.74 | 18.92 | delivery of materials on active track | 202 | 4 | 808 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30 | traffic interruption | 2023-09-01 | 2024-06-30 | 1.095
300 | 6 | 132 | BYTOM - WROCŁAW GŁÓWNY | IRR4/2 | szl. Opole Główne - Opole Groszowice | 1, 2 | 97.21 | 98.875 | closure at night | 21 | 4 | 84 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21 | traffic interruption | 2021-08-29 | 2023-12-31 | 1.084
301 | 6 | 132 | BYTOM - WROCŁAW GŁÓWNY | IRR4/2 | st. Opole Główne | 1, 2, 3, 4, 5, 6, 8, 10, 12, 15, 17 płd | 98.875 | 99.594 | closure at night | 21 | 4 | 84 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21 | traffic interruption | 2021-08-29 | 2023-12-31 | 1.084
302 | 6 | 132 | BYTOM - WROCŁAW GŁÓWNY | IRR4/2 | szlak Opole Główne - Opole Zachodnie, Opole Główne | 1, 1płn, 4płn, 6płn | 99.215 | 101.1 | Track demolition, switch demolition, track construction, switch construction | 20 | 24 | 480 | 30 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 20 | single-track two-way traffic on the active track | 2023-06-12 | 2023-12-30 | 1.084
303 | 6 | 132 | BYTOM - WROCŁAW GŁÓWNY | IRR4/2 | Opole Główne - Opole Zachodnie | 2 | 99.63 | 101.1 | closure at night | 21 | 4 | 84 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21 | traffic interruption | 2023-06-12 | 2023-12-31 | 1.084
304 | 3 | 133 | DĄBROWA GÓRNICZA ZĄBKOWICE - KRAKÓW GŁÓWNY | IRR3/1 | Szlak Trzebinia - Krzeszowice | 1, 2 | 30.4 | 45.097 | night-time line closure | 109 | 4 | 436 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 29 | Traffic interruption | 2022-12-22 | 2024-03-29 | 1.075
305 | 3 | 133 | DĄBROWA GÓRNICZA ZĄBKOWICE - KRAKÓW GŁÓWNY | IRR3/1 | Szlak Krzeszowice-Zabierzów | 1, 2 | 45.097 | 57.515 | night-time line closure | 109 | 4 | 436 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 29 | Traffic interruption | 2022-12-22 | 2024-03-29 | 1.075
306 | 4 | 135 | GLIWICE ŁABĘDY - PYSKOWICE | IRR4/5 | stacja Gliwice Łabędy | 29 | -0.283 | 0.058 | Reconstruction of track systems including contact line and Railway Traffic Controlling system | 115 | 24 | 2760 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 10; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-08-22 | 2025-03-10
307 | 4 | 135 | GLIWICE ŁABĘDY - PYSKOWICE | IRR4/5 | szlak Gliwice Łabędy - Pyskowice | 2 | -0.219 | 4.744 | Reconstruction of track systems including overhead contact line and Railway Traffic Controlling system, demolition and construction of engineering structures | 8 | 24 | 192 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 8 | single-track two-way traffic on the active track | 2023-10-19 | 2023-12-18
308 | 4 | 135 | GLIWICE ŁABĘDY - PYSKOWICE | IRR4/5 | stacja Gliwice Łabędy | 21 | -0.209 | 5.727 | Reconstruction of track systems. Platform edge construction. | 4 | 24 | 96 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 4 | traffic on active track at the station | 2024-08-19 | 2024-08-22
309 | 4 | 135 | GLIWICE ŁABĘDY - PYSKOWICE | IRR4/5 | szlak Gliwice Łabędy - Pyskowice | 1 | -0.209 | 5.727 | Reconstruction of track systems including overhead contact line and Railway Traffic Controlling system | 115 | 24 | 2760 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 10; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-08-22 | 2025-03-10
310 | 4 | 137 | KATOWICE - LEGNICA | IRR4/4 | stacja Katowice | 1 | 0.93 | 1.9 | upgrade | 36 | 24 | 864 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 15 | traffic on active track at the station | 2023-12-01 | 2024-01-15
311 | 4 | 137 | KATOWICE - LEGNICA | IRR4/4 | stacja Katowice | 2 | 0.93 | 1.9 | upgrade | 112 | 24 | 2688 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 16; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 7 | traffic on active track at the station | 2024-01-16 | 2024-05-07
312 | 4 | 137 | KATOWICE - LEGNICA | IRR4/5 | szlak Szobiszowice - Gliwice Łabędy | 2 | 28.817 | 32.856 | Reconstruction of track systems including overhead contact line and Railway Traffic Controlling system. Platform edge construction. Demolition and construction of engineering structures. | 200 | 24 | 4800 | 50 km/h | no limit | 14 | 31 | 28 | 31 | 30 | 31 | 30 | 5 | [5 empty] | single-track two-way traffic on the active track | 2023-12-18 | 2024-07-05
313 | 4 | 138 | OŚWIĘCIM - KATOWICE | IRR4/6 | Oświęcim - Nowy Bieruń | 2 | 1.3 | 3.5 | end-to-end surface replacement | 102 | 24 | 2448 | 40 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 27; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-09-04 | 2025-01-31
314 | 4 | 138 | OŚWIĘCIM - KATOWICE | IRR4/6 | Nowy Bieruń | 2, 4, 6 | 3.5 | 4.3 | end-to-end surface replacement | 102 | 24 | 2448 |  | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 27; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-09-04 | 2025-01-31
315 | 4 | 138 | OŚWIĘCIM - KATOWICE | IRR4/4 | Katowice Zawodzie - Katowice | 1 | 30.5 | 31.95 | upgrade | 80 | 24 | 1920 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28 | traffic interruption | 2023-09-14 | 2024-02-28
316 | 4 | 138 | OŚWIĘCIM - KATOWICE | IRR4/4 | Katowice Zawodzie - Katowice | 2 | 30.5 | 31.95 | upgrade | 80 | 24 | 1920 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28 | traffic interruption | 2023-09-14 | 2024-02-28
317 | 4 | 138 | OŚWIĘCIM - KATOWICE | IRR4/4 | stacja Katowice | 11,12,14,16,18,20 | 32.2 | 32.45 | upgrade | 182 | 24 | 4368 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 16; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 16 | traffic on active track at the station | 2024-01-16 | 2024-07-16
318 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | stacja Katowice | 10 | 0.05 | 0.6 | upgrade | 29 | 24 | 696 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 15; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-11-16 | 2025-02-14
319 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | stacja Katowice | 8 | 0.1 | 0.6 | upgrade | 122 | 24 | 2928 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 15; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 15 | traffic on active track at the station | 2024-07-17 | 2024-11-15
320 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | stacja Katowice | 4,6 | 0.15 | 0.8 | upgrade | 151 | 24 | 3624 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 13; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 16 | traffic on active track at the station | 2024-02-16 | 2024-07-16
321 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | stacja Katowice | 2,54,56 | 0.6 | 2.1 | upgrade | 81 | 24 | 1944 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 13; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 7 | traffic on active track at the station | 2024-02-16 | 2024-05-07
322 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | stacja Katowice | 2L | 1.1 | 1.95 | upgrade | 29 | 24 | 696 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 15; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-11-16 | 2025-02-14
323 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | Brynów - Katowice Ligota | 1 | 2.4 | 6.3 | upgrade | 151 | 24 | 3624 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 15; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-07-17 | 2025-02-14
324 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | Katowice - K-ce Ligota | 2 | 4.8 | 5.6 | upgrade | 151 | 4 | 604 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 15; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption | 2024-07-17 | 2026-07-01
325 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | stacja Katowice Ligota | 2,4 | 5.8 | 6.75 | upgrade | 67 | 24 | 1608 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 15 | traffic on active track at the station | 2023-10-02 | 2024-02-15
326 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | stacja Katowice Ligota | 1,3 | 5.8 | 6.75 | upgrade | 259 | 24 | 6216 | 60 km/h | no limit |  |  |  | 1 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic on active track at the station | 2024-03-31 | 2025-03-31
327 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | Tychy - Kobiór | 2 | 16.97 | 25.556 | upgrade | 211 | 24 | 5064 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 28 | single-track two-way traffic on the active track | 2024-04-01 | 2024-10-28 | 1.154
328 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | Tychy - Kobiór | 1 | 16.97 | 25.556 | technology commissioning activities | 211 | 4 | 844 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 28 | traffic interruption | 2024-04-01 | 2024-10-28
329 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | Tychy - Kobiór | 1 | 16.97 | 25.556 | upgrade | 47 | 24 | 1128 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 3; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-10-29 | 2025-05-29 | 1.154
330 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | Tychy - Kobiór | 2 | 16.97 | 25.556 | technology commissioning activities | 47 | 4 | 188 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 3; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption | 2024-10-29 | 2025-05-29
331 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | Kobiór - Pszczyna | 1 | 25.556 | 35.918 | upgrade | 103 | 24 | 2472 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 23 | single-track two-way traffic on the active track | 2023-08-21 | 2024-03-23
332 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | Kobiór - Pszczyna | 2 | 25.556 | 35.918 | technology commissioning activities | 103 | 4 | 412 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 23 | traffic interruption | 2023-08-21 | 2024-03-23
333 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | stacja Pszczyna | 2,4,6,8 | 33.83 | 35.25 | upgrade | 243 | 24 | 5832 | 60 km/h | no limit |  |  |  |  | 23 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 6 | traffic on active track at the station | 2024-04-08 | 2024-12-06
334 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | stacja Pszczyna | 1 | 35.25 | 36.69 | upgrade | 103 | 24 | 2472 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 23 | traffic on active track at the station | 2023-09-25 | 2024-03-23
335 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | stacja Pszczyna | 1 | 35.25 | 36.69 | upgrade | 8 | 24 | 192 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 8 | traffic on active track at the station | 2024-12-02 | 2025-07-04
336 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | Pszczyna - Most Wisła | 1 | 36.69 | 40.5 | upgrade | 179 | 24 | 4296 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 24; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 2 | single-track two-way traffic on the active track | 2024-02-05 | 2024-08-02
337 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | Pszczyna - Most Wisła | 2 | 36.69 | 40.5 | technology commissioning activities | 179 | 4 | 716 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 24; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 2 | traffic interruption | 2024-02-05 | 2024-08-02
338 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | Pszczyna - Most Wisła | 2 | 36.69 | 40.5 | upgrade | 132 | 24 | 3168 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 27; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-08-05 | 2025-02-05
339 | 4 | 139 | KATOWICE - ZWARDOŃ | IRR4/4 | Pszczyna - Most Wisła | 1 | 36.69 | 40.5 | technology commissioning activities | 132 | 4 | 528 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 27; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption | 2024-08-05 | 2025-02-05
340 | 4 | 140 | KATOWICE LIGOTA - NĘDZA | IRR4/4 | stacja Katowice Ligota | 5 | 0.3 | 1 | upgrade | 151 | 24 | 3624 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 15; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-07-17 | 2025-02-14
341 | 4 | 140 | KATOWICE LIGOTA - NĘDZA | IRR4/6 | Orzesze - Orzesze Jaśkowice | 1 | 19 | 21.3 | Installation of switches in the eastern head of Orzesze Jaśkowice station | 30 | 24 | 720 |  | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 16; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 14 | traffic interruption – single-track line | 2024-04-15 | 2024-05-14
342 | 4 | 141 | KATOWICE LIGOTA - GLIWICE | IRR4/4 | stacja Katowice Ligota | 1 | 0 | 0.3 | upgrade | 61 | 24 | 1464 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 15; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 15 | traffic on active track at the station | 2024-07-17 | 2024-09-15
343 | 4 | 141 | KATOWICE LIGOTA - GLIWICE | IRR4/4 | Katowice Ligota - Panewnik | 1 | 0.9 | 1.9 | upgrade | 369 | 24 | 8856 | 40 km/h | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | single-track two-way traffic on the active track | 2023-10-02 | 2026-02-14
344 | 4 | 141 | KATOWICE LIGOTA - GLIWICE | IRR4/4 | Katowice Ligota - Panewnik | 2 | 1 | 1.9 | upgrade | 151 | 24 | 3624 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 15; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption | 2024-07-17 | 2026-01-14
345 | 4 | 148 | PSZCZYNA - RYBNIK | IRR4/4 | stacja Pszczyna | 3 | -0.632 | 2.75 | upgrade | 103 | 24 | 2472 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 23 | traffic on active track at the station | 2023-09-25 | 2024-03-23
346 | 4 | 148 | PSZCZYNA - RYBNIK | IRR4/4 | stacja Pszczyna | 3 | -0.632 | 2.75 | upgrade | 8 | 24 | 192 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 8 | traffic on active track at the station | 2024-12-02 | 2025-07-04
347 | 4 | 150 | MOST WISŁA - CHYBIE | IRR4/4 | Zabrzeg Czrnolesie - Bronów | 1 | 7.9 | 11.5 | upgrade | 7 | 24 | 168 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 7 | single-track two-way traffic on the active track | 2023-11-06 | 2023-12-17
348 | 4 | 150 | MOST WISŁA - CHYBIE | IRR4/4 | Bronów - Chybie | 1 | 11.5 | 13.1 | upgrade | 188 | 24 | 4512 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 16 | single-track two-way traffic on the active track | 2023-11-06 | 2024-06-16
349 | 4 | 161 | KATOWICE SZOPIENICE PÓŁNOCNE - CHORZÓW STARY | IRR4/5 | Szlak Chorzów Stary - Siemianowice | 1 | 11.55 | 11.77 | Closing the tangent line | 264 | 24 | 6336 | 50 km/h | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 |  |  |  |  | single-track two-way traffic on the active track | 2023-12-01 | 2024-08-31 | 1.095
350 | 4 | 161 | KATOWICE SZOPIENICE PÓŁNOCNE - CHORZÓW STARY | IRR4/5 | Szlak Chorzów Stary - Siemianowice | 2 | 11.55 | 11.77 | delivery of materials on active track | 264 | 4 | 1056 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 |  |  |  |  | traffic interruption | 2023-12-01 | 2024-08-31 | 1.095
351 | 4 | 161 | KATOWICE SZOPIENICE PÓŁNOCNE - CHORZÓW STARY | IRR4/5 | Szlak Chorzów Stary - Siemianowice | 2 | 11.55 | 11.77 | Closing the tangent line | 106 | 24 | 2544 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 1; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-08-31 | 2025-03-31 | 1.095
352 | 4 | 161 | KATOWICE SZOPIENICE PÓŁNOCNE - CHORZÓW STARY | IRR4/5 | Szlak Chorzów Stary - Siemianowice | 1 | 11.55 | 11.77 | delivery of materials on active track | 106 | 4 | 424 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 1; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption | 2024-08-31 | 2025-03-31 | 1.095
353 | 4 | 165 | BYTOM BOBREK - BYTOM KARB | IRR4/5 | Szlak Bytom Karb - Bytom Bobrek | 1 | 1.185 | 1.285 | Closing the tangent line | 264 | 24 | 6336 | 50 km/h | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 |  |  |  |  | single-track two-way traffic on the active track | 2023-12-01 | 2024-08-31 | 1.095
354 | 4 | 165 | BYTOM BOBREK - BYTOM KARB | IRR4/5 | Szlak Bytom Karb - Bytom Bobrek | 2 | 1.185 | 1.285 | delivery of materials on active track | 264 | 4 | 1056 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 |  |  |  |  | traffic interruption | 2023-12-01 | 2024-08-31 | 1.095
355 | 4 | 165 | BYTOM BOBREK - BYTOM KARB | IRR4/5 | Szlak Bytom Karb - Bytom Bobrek | 2 | 1.185 | 1.285 | Closing the tangent line | 106 | 24 | 2544 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 1; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-08-31 | 2025-03-31 | 1.095
356 | 4 | 165 | BYTOM BOBREK - BYTOM KARB | IRR4/5 | Szlak Bytom Karb - Bytom Bobrek | 1 | 1.185 | 1.285 | delivery of materials on active track | 106 | 4 | 424 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 1; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption | 2024-08-31 | 2025-03-31 | 1.095
357 | 4 | 167 | SZOBISZOWICE - GLIWICE PORT | IRR4/5 | stacja Gliwice Port | 1 | 3.386 | 3.81 | Reconstruction of track systems including Railway Traffic Controlling system | 8 | 24 | 192 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 8 | traffic on active track at the station | 2023-12-05 | 2023-12-18
358 | 4 | 168 | GLIWICE - GLIWICE ŁABĘDY | IRR4/5 | szlak Szobiszowice - Gliwice Łabędy | 3 | 1.559 | 4.086 | Reconstruction of track systems. Platform edge construction. | 43 | 24 | 1032 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 24; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 19 | single-track two-way traffic on the active track | 2024-07-08 | 2024-08-19
359 | 4 | 168 | GLIWICE - GLIWICE ŁABĘDY | IRR4/5 | szlak Szobiszowice - Gliwice Łabędy | 3 | 1.559 | 4.086 | Reconstruction of track systems including overhead contact line and Railway Traffic Controlling system | 115 | 24 | 2760 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 10; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-08-22 | 2025-03-10
360 | 4 | 168 | GLIWICE - GLIWICE ŁABĘDY | IRR4/5 | stacja Gliwice Łabędy | 9,11,15,17,19,21,109,115,215,7,5,31 | 4.674 | 5.333 | Reconstruction of track systems including overhead contact line and Railway Traffic Controlling system | 115 | 24 | 2760 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 10; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-08-22 | 2025-03-10
361 | 4 | 169 | TYCHY - ORZESZE JAŚKOWICE | IRR4/6 | Stacja Łaziska Średnie - Orzesze Jaśkowice | 1 | 7.4 | 16.7 | replacement of Rkpd 43 at Łaziska Średnie station | 10 | 24 | 240 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 10 | traffic interruption – single-track line | 2024-05-15 | 2024-05-24
362 | 4 | 169 | TYCHY - ORZESZE JAŚKOWICE | IRR4/6 | Łaziska Średnie - Orzesze Jaśkowice | 1 | 8.7 | 16.7 | Installation of a switch in the eastern head of Orzesze Jaśkowice station, upgrade of the main track | 120 | 24 | 2880 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 17; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 11 | traffic interruption – single-track line | 2024-05-15 | 2024-09-11
363 | 4 | 169 | TYCHY - ORZESZE JAŚKOWICE | IRR4/6 | Orzesze Jaśkowice | 4 | 16.7 | 17.4 | Installation of switches in the eastern head of Orzesze Jaśkowice station | 120 | 24 | 2880 |  | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 17; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 11 | traffic on active track at the station | 2024-05-15 | 2024-09-11
364 | 4 | 169 | TYCHY - ORZESZE JAŚKOWICE | IRR4/6 | Łaziska Średnie | 1 | 8 | 8.7 | Upgrade of track 1 at Łaziska Średnie station | 120 | 24 | 2880 |  | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 17; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 11 | traffic on active track at the station | 2024-05-15 | 2024-09-11
365 | 4 | 169 | TYCHY - ORZESZE JAŚKOWICE | IRR4/6 | Orzesze Jaśkowice | 2, 4 | 16.8 | 17.4 | Upgrade of tracks 2 and 4 at Orzesze Jaśkowice station | 94 | 24 | 2256 |  | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 19; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-09-12 | 2025-01-09
366 | 4 | 179 | TYCHY - MYSŁOWICE KOSZTOWY MKSB1 | IRR4/6 | Tychy Miasto - Bocznica EC | 1 | 3.85 | 5.25 | Change of route | 10 | 24 | 240 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 10 | traffic interruption – single-track line | 2024-09-04 | 2024-09-13
367 | 4 | 179 | TYCHY - MYSŁOWICE KOSZTOWY MKSB1 | IRR4/6 | szlak: Tychy Miasto - Bieruń Stary - Górki Ściernie | 1 | 4 | 13.1 | end-to-end surface replacement | 102 | 24 | 2448 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 27; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption – single-track line | 2024-09-04 | 2025-01-31
368 | 4 | 179 | TYCHY - MYSŁOWICE KOSZTOWY MKSB1 | IRR4/6 | Tychy - Tychy Miasto | 1 | 0.8 | 3.4 | end-to-end surface replacement | 102 | 24 | 2448 |  | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 27; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-09-04 | 2025-01-31
369 | 4 | 179 | TYCHY - MYSŁOWICE KOSZTOWY MKSB1 | IRR4/6 | Tychy Miasto | 1, 3 | 3.4 | 4 | end-to-end surface replacement | 102 | 24 | 2448 |  | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 27; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-09-04 | 2025-01-31
370 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/9 | Szlak Bydgoszcz Emilianowo - Nowa Wieś Wielka | 2 | 0.7 | 8.7 | Track adjustment, end-to-end surface replacement, reconstruction in other areas | 59 | 24 | 1416 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 15; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-10-17 | 2025-03-15
371 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/9 | Bydgoszcz Emilianowo | 2,4,6 | 0.7 | 10.15 | end-to-end surface replacement, reconstruction in other areas | 59 | 24 | 1416 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 15; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-10-17 | 2025-03-15
372 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Serock - Wierzchucin | 1 | 50.75 | 71.223 | end-to-end upgrade | 30 | 24 | 720 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 5; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 25 | traffic interruption | 2024-08-27 | 2024-09-25
373 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | (Czersk) - Bąk (+2,4) - Kościerzyna | 1 | 77.323 | 136.245 | end-to-end upgrade | 16 | 24 | 384 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 2; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption – single-track line | 2024-11-29 | 2026-11-18
374 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Lipowa Tucholska - Bąk (+1,3) | 1 | 94.73 | 117.53 | end-to-end upgrade | 240 | 24 | 5760 | traffic interruption | no limit |  |  |  |  | 28 | 31 | 30 | 31 | 31 | 30 | 31 | 28 |  | traffic interruption – single-track line | 2024-04-03 | 2024-11-28
375 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Łąg Południowy - Bąk (+1,3) | 1 | 105.2 | 117.53 | end-to-end upgrade | 16 | 24 | 384 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 2; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption – single-track line | 2024-11-29 | 2026-03-23
376 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Stacja Kościerzyna | 1,3 | 136.105 | 138.068 | Reconstruction of the track system | 6 | 24 | 144 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 6 | traffic on active track at the station | 2023-12-10 | 2023-12-16
377 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Stacja Kościerzyna | 3,5,7,9 | 136.105 | 138.068 | Reconstruction of the track system | 143 | 24 | 3432 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 15; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 8 | traffic on active track at the station | 2023-12-17 | 2024-05-08
378 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Stacja Kościerzyna | 3, 5, 7, 9, 11, 13, 15, 17, 19 | 136.105 | 138.068 | Reconstruction of the track system | 153 | 24 | 3672 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 23; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 8 | traffic on active track at the station | 2024-05-09 | 2024-10-08
379 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Stacja Kościerzyna | 15, 17, 19 | 136.105 | 138.068 | Reconstruction of the track system | 67 | 24 | 1608 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 23; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-10-09 | 2026-04-08
380 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Kościerzyna - Gołubie Kaszubskie | 1 | 138.068 | 148.344 | End-to-end route reconstruction | 223 | 24 | 5352 | traffic interruption | no limit | [5 empty] | 26 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption – single-track line | 2024-05-06 | 2026-04-08
381 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Stacja Gołubie Kaszubskie | 1, 2, 4 | 148.344 | 149.701 | Reconstruction of the track system | 369 | 24 | 8856 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption | 2023-07-09 | 2026-04-08
382 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Gołubie Kaszubskie - Somonino | 1 | 149.701 | 161.73 | End-to-end route reconstruction | 369 | 24 | 8856 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption – single-track line | 2023-07-09 | 2026-04-08
383 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Stacja Somonino | 1 | 161.73 | 162.5 | Reconstruction of the track system | 369 | 24 | 8856 | 50 km/h | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic on active track at the station | 2023-07-09 | 2025-01-05
384 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Stacja Somonino | 10, 12 | 161.73 | 163.363 | Reconstruction of the track system | 369 | 24 | 8856 | 50 km/h | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic on active track at the station | 2023-07-09 | 2025-01-05
385 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Somonino - Glincz | 1 | 163.25 | 174.345 | line upgrade, construction of the second track | 139 | 24 | 3336 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 3; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption – single-track line | 2024-07-29 | 2026-09-23
386 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Glincz - Żukowo Wschodnie | 1 | 174.775 | 178.4 | line upgrade, construction of the second track | 139 | 24 | 3336 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 3; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption – single-track line | 2024-07-29 | 2025-08-28
387 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Stacja Żukowo Wschodnie | 1,2,6 | 178.4 | 179.706 | line upgrade, construction of the second track | 139 | 24 | 3336 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 3; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption | 2024-07-29 | 2025-08-28
388 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Żukowo Wschodnie - Gdańsk Osowa | 1 | 179.706 | 184.413 | line upgrade, construction of the second track | 139 | 24 | 3336 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 3; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption – single-track line | 2024-07-29 | 2025-08-28
389 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Stacja Gdańsk Osowa | 2a, tor 3R na linii 253 PKM (km 1,356-1,421) | 184.518 | 186.2 | construction of the new track | 139 | 24 | 3336 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 3; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption | 2024-07-29 | 2025-08-28
390 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Stacja Gdańsk Osowa | 1a, 1b, 1c, tor 1R na linii 248 PKM (km 17,985-18,050) | 186.369 | 188 | construction of the new track | 139 | 24 | 3336 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 3; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-07-29 | 2025-01-27
391 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Stacja Gdańsk Osowa | 2b, 2c, 2d, 2e | 186.4 | 188.36 | station reconstruction | 212 | 24 | 5088 | 50 km/h | no limit | 3 | 31 | 28 | 31 | 30 | 31 | 30 | 28 | [5 empty] | traffic on active track at the station | 2023-12-29 | 2024-07-28
392 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Stacja Gdańsk Osowa | 2, 2d, 2e, 2f, 4 | 188 | 190.054 | construction of the new track | 139 | 24 | 3336 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 3; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-07-29 | 2025-03-28
393 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Stacja Gdańsk Osowa | 2a, 2R na linii 248 PKM | 189.38 | 189.9 | station reconstruction, track adjustments in plane and profile | 61 | 24 | 1464 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 3; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 28 | traffic interruption | 2024-05-29 | 2024-07-28
394 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Stacja Gdańsk Osowa | 1 | 189.38 | 189.9 | station reconstruction | 14 | 24 | 336 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 14 | traffic on active track at the station | 2024-07-15 | 2024-07-28
395 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Gdańsk Osowa - Gdynia Wielki Kack | 2 | 189.4 | 193.858 | construction of the new track 3, upgrade of track 2, installation of switches, | 168 | 24 | 4032 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 1; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-06-30 | 2025-06-13
396 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | Stacja Gdańsk Osowa | 1f | 189.45 | 189.9 | station reconstruction | 212 | 24 | 5088 | 50 km/h | no limit | 3 | 31 | 28 | 31 | 30 | 31 | 30 | 28 | [5 empty] | traffic on active track at the station | 2023-12-29 | 2024-07-28
397 | 5 | 201 | NOWA WIEŚ WIELKA - GDYNIA PORT | IRR2/7 | stacja Gdynia Wielki Kack | 4 | 194.8 | 195 | station reconstruction | 14 | 24 | 336 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 14 | traffic on active track at the station | 2024-06-14 | 2024-06-27
398 | 5 | 202 | GDAŃSK GŁÓWNY - STARGARD | IRR2/1 | szlak Potęgowo - Lębork | 1 | 81.15 | 96.9 | upgrade of tracks and engineering structures | 369 | 24 | 8856 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption – single-track line | 2023-11-05 | 2024-12-14
399 | 5 | 202 | GDAŃSK GŁÓWNY - STARGARD | IRR2/1 | szlak Damnica - Potęgowo | 1 | 99.3 | 111.3 | upgrade of tracks and engineering structures | 82 | 24 | 1968 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 2 | traffic interruption – single-track line | 2023-09-04 | 2024-03-02
400 | 8 | 202 | GDAŃSK GŁÓWNY - STARGARD | IRR2/1 | Jezierzyce Słupskie - Słupsk | 1 | 128.6 | 131.173 | upgrade of tracks and engineering structures | 153 | 24 | 3672 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 24; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 9 | traffic interruption – single-track line | 2024-01-08 | 2024-06-09 | 1.100
401 | 5 | 211 | CHOJNICE - KOŚCIERZYNA | IRR2/7 | Lipusz - Kościerzyna | 1 | 51.99 | 68.66 | End-to-end route reconstruction | 154 | 24 | 3696 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 27; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 5 | traffic interruption – single-track line | 2024-05-05 | 2024-10-05
402 | 5 | 214 | SOMONINO - KARTUZY | IRR2/7 | Somonino-Kartuzy | 1 | 0.64 | 6.991 | End-to-end route reconstruction | 152 | 24 | 3648 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 11 | traffic interruption – single-track line | 2023-07-09 | 2024-05-11
403 | 7 | 272 | KLUCZBORK - POZNAŃ GŁÓWNY | IRS5/3 | st. Krzesiny - st. Poznań Starołęka | 2 | 192.8 | 195.3 | renovation | 150 | 24 | 3600 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 14; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-07-19 | 2024-12-19 | 1.117
404 | 7 | 272 | KLUCZBORK - POZNAŃ GŁÓWNY | IRS5/3 | st. Poznań Starołęka - st. Poznań Główny | 2 | 197.26 | 199.8 | renovation | 156 | 24 | 3744 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 20; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-07-12 | 2024-12-19 | 1.117
405 | 6 | 273 | WROCŁAW GŁÓWNY - SZCZECIN GŁÓWNY | IREST4 | Brzeg Dolny - Wołów | 2 | 30.853 | 40 | Decommissioning of platform 2 at current location P.o. Łososiowice and the construction of a new platform 2 at the new location P.o. Łososiowice at km. 37.665 + track surface replacement, overhead contact line. | 120 | 24 | 2880 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 15; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 16 | single-track two-way traffic on the active track | 2024-01-17 | 2024-05-16 | 4.044
406 | 6 | 274 | WROCŁAW ŚWIEBODZKI - ZGORZELEC | IRRK4/7/1 | Janowice Wielkie - Wojanów | 1, 2 | 118.548 | 118.841 | Revitalisation of the line tunnel at km 118.700 and associated infrastructure | 42 | 24 | 1008 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 16; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 26 | traffic interruption | 2024-02-13 | 2024-03-26 | 4.028
407 | 6 | 274 | WROCŁAW ŚWIEBODZKI - ZGORZELEC | IRRK4/7/1 | Janowice Wielkie - Wojanów | 1 | 118.548 | 118.841 | Revitalisation of the line tunnel at km 118.700 and associated infrastructure | 64 | 24 | 1536 | 20 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 12 | single-track two-way traffic on the active track | 2023-12-10 | 2024-02-12 | 4.028
408 | 6 | 276 | WROCŁAW GŁÓWNY - MIĘDZYLESIE | IRRK4/7/2 | st. Kłodzko Główne | 102 | 0.2 | 0.004 | revitalisation | 185 | 24 | 4440 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 14; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 18 | traffic on active track at the station | 2024-03-18 | 2024-09-18
409 | 6 | 276 | WROCŁAW GŁÓWNY - MIĘDZYLESIE | IRRK4/7/2 | st. Kłodzko Główne | 101 | 0.267 | 1.3 | revitalisation | 185 | 24 | 4440 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 14; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 18 | traffic on active track at the station | 2024-03-18 | 2024-09-18
410 | 6 | 280 | OPOLE GROSZOWICE - OPOLE GŁÓWNE | IRR4/2 | st. Opole Główne | 1, 2, 4, 6, 8 płn | 3.815 | 4.476 | closure at night | 21 | 4 | 84 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21 | traffic on active track at the station | 2021-08-29 | 2023-12-31 | 1.084
411 | 6 | 286 | KŁODZKO GŁÓWNE - WAŁBRZYCH GŁÓWNY | IRRK4/7/2 | st. Kłodzko Główne | 12 | 93.15 | 93.863 | revitalisation | 88 | 24 | 2112 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 13; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-09-18 | 2024-12-31
412 | 6 | 286 | KŁODZKO GŁÓWNE - WAŁBRZYCH GŁÓWNY | IRRK4/7/2 | st. Kłodzko Główne | 14 | 93.216 | 93.805 | revitalisation | 88 | 24 | 2112 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 13; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-09-18 | 2024-12-31
413 | 7 | 352 | SWARZĘDZ - POZNAŃ STAROŁĘKA | IRS5/3 | od ukresu rozjazdu nr 78 do ukresu skrzyżowania torów nr K10 stacja Franowo | 2 | 4.1 | 5.35 | renovation | 156 | 24 | 3744 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 20; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-07-12 | 2024-12-19 | 1.117
414 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IRR2/9 | Inowrocław - Dziarnowo | 2 | 95.8 | 97 | installation of new switches Dziarnowo Podg. | 55 | 24 | 1320 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 27 | single-track two-way traffic on the active track | 2024-09-03 | 2024-10-27
415 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IRSK2/1/4 | Ostróda | 2 | 257.859 | 258.09 | construction work at the station | 43 | 24 | 1032 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 11; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 2 | traffic on active track at the station | 2024-03-21 | 2024-05-02
416 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IRSK2/1/4 | Ostróda | 3, 301, 302, 303 , 304, 305, 306, 308, 309, 310, 311, 312 | 258 | 258 | construction work at the station | 101 | 24 | 2424 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 21 | traffic on active track at the station | 2023-10-23 | 2024-03-21
417 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IRSK2/1/4 | Ostróda | 2 | 258.09 | 261.6 | construction work at the station | 131 | 24 | 3144 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 9 | traffic on active track at the station | 2024-05-02 | 2024-09-09
418 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IRSK2/1/4 | Ostróda | 4 | 258.105 | 259.4 | construction work at the station | 29 | 24 | 696 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 8 | traffic on active track at the station | 2023-03-13 | 2024-01-08
419 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IRSK2/1/4 | Ostróda | 10,106 | 258.185 | 259.04 | construction work at the station | 29 | 24 | 696 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 8 | traffic on active track at the station | 2023-03-13 | 2024-01-08
420 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IRSK2/1/4 | Szlak Ostróda - Stare Jabłonki | 1 | 259.103 | 268.959 | construction work on the bridge at km 261.615 | 180 | 24 | 4320 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 6 | single-track two-way traffic on the active track | 2024-03-11 | 2024-09-06
421 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IRSK2/1/4 | Szlak Ostróda - Stare Jabłonki | 2 | 259.103 | 268.959 | construction work on the bridge at km 261.615 | 100 | 24 | 2400 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 25; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-09-06 | 2025-03-05
422 | 5 | 353 | POZNAŃ WSCHÓD - SKANDAWA | IRSK2/1/4 | Ostróda | 1 | 259.53 | 261.6 | construction work at the station | 97 | 24 | 2328 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 22; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-09-09 | 2025-02-06
423 | 7 | 354 | POZNAŃ GŁÓWNY POD - PIŁA GŁÓWNA | IRS5/3 | p.odg. Poznań PoD - p.odg. Suchy Las | 1 | 0 | 6.1 | renovation | 35 | 24 | 840 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 12; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 23 | single-track two-way traffic on the active track | 2024-04-19 | 2024-05-23 | 1.117
424 | 7 | 354 | POZNAŃ GŁÓWNY POD - PIŁA GŁÓWNA | IRS5/3 | p.odg. Poznań PoD - p.odg. Suchy Las | 2 | 0 | 6.25 | renovation | 21 | 24 | 504 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 8; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 13 | single-track two-way traffic on the active track | 2024-05-24 | 2024-06-13 | 1.117
425 | 7 | 354 | POZNAŃ GŁÓWNY POD - PIŁA GŁÓWNA | IRS5/3 | p.odg. Poznań PoD - p.odg. Suchy Las | 2 | 0 | 6.25 | renovation | 7 | 4 | 28 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 7 | traffic interruption | 2024-04-19 | 2024-04-25 | 1.117
426 | 7 | 354 | POZNAŃ GŁÓWNY POD - PIŁA GŁÓWNA | IRS5/3 | p.odg. Poznań PoD - p.odg. Suchy Las | 1 | 0 | 6.25 | renovation | 7 | 24 | 168 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 7 | single-track two-way traffic on the active track | 2024-10-25 | 2024-10-31 | 1.117
427 | 7 | 354 | POZNAŃ GŁÓWNY POD - PIŁA GŁÓWNA | IRR1/1 | Poznań POD- Suchy Las | 1, 2 | 0.097 | 5.697 | construction of a road viaduct | 42 | 4 | 168 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 21 | traffic interruption | 2023-10-03 | 2024-01-21 | 1.066
428 | 7 | 354 | POZNAŃ GŁÓWNY POD - PIŁA GŁÓWNA | IRR1/1 | Poznań POD- Suchy Las | 1 | 0.097 | 5.697 | construction of a road viaduct | 5 | 24 | 120 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 5 | single-track two-way traffic on the active track | 2023-12-08 | 2023-12-15 | 1.066
429 | 7 | 354 | POZNAŃ GŁÓWNY POD - PIŁA GŁÓWNA | IRR1/1 | Poznań POD- Suchy Las | 2 | 0.097 | 5.697 | construction of a road viaduct | 8 | 24 | 192 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 8 | single-track two-way traffic on the active track | 2023-12-16 | 2023-12-23 | 1.066
430 | 7 | 354 | POZNAŃ GŁÓWNY POD - PIŁA GŁÓWNA | IRR1/1 | Poznań POD- Suchy Las | 1 | 0.097 | 5.697 | construction of a road viaduct | 8 | 10 | 80 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 8 | traffic interruption | 2024-01-07 | 2024-01-14 | 1.066
431 | 7 | 354 | POZNAŃ GŁÓWNY POD - PIŁA GŁÓWNA | IRR1/1 | Poznań POD- Suchy Las | 2 | 0.097 | 5.697 | construction of a road viaduct | 8 | 10 | 80 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 8 | traffic interruption | 2024-01-15 | 2024-01-22 | 1.066
432 | 7 | 354 | POZNAŃ GŁÓWNY POD - PIŁA GŁÓWNA | IRS5/3 | p.odg. Suchy Las - st. Złotniki | 1 | 6.25 | 8.6 | renovation | 7 | 24 | 168 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 7 | single-track two-way traffic on the active track | 2024-10-25 | 2024-10-31 | 1.117
433 | 7 | 394 | POZNAŃ KRZESINY - KOBYLNICA | IRS5/3 | st. Kobylnica - p.odg. Pokrzywno | 1 | 3.2 | 12.615 | unloading of rails | 4 | 24 | 96 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 4 | single-track two-way traffic on the active track | 2023-12-10 | 2023-12-14 | 1.117
434 | 7 | 394 | POZNAŃ KRZESINY - KOBYLNICA | IRS5/3 | st. Poznań Franowo - p.odg. Stary Młyn | 1 | 4.85 | 10.7 | renovation | 156 | 24 | 3744 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 20; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-07-12 | 2024-12-14 | 1.117
435 | 7 | 394 | POZNAŃ KRZESINY - KOBYLNICA | IRS5/3 | st. Poznań Franowo - p.odg. Stary Młyn | 2 | 8.25 | 10.5 | renovation | 7 | 4 | 28 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 7 | traffic interruption | 2024-07-12 | 2024-07-18 | 1.117
436 | 7 | 394 | POZNAŃ KRZESINY - KOBYLNICA | IRS5/3 | p.odg. Stary Młyn - p.odg. Zieliniec | 2 | 8.25 | 10.5 | renovation | 7 | 4 | 28 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 7 | traffic interruption | 2024-07-12 | 2024-07-18 | 1.117
437 | 7 | 394 | POZNAŃ KRZESINY - KOBYLNICA | IRS5/3 | p.odg. Stary Młyn - p.odg. Zieliniec | 1 | 10.7 | 12.05 | renovation | 156 | 24 | 3744 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 20; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-07-12 | 2024-12-14 | 1.117
438 | 7 | 394 | POZNAŃ KRZESINY - KOBYLNICA | IRS5/3 | p.odg. Stary Młyn - p.odg. Zieliniec | 1 | 10.7 | 12 | renovation | 44 | 24 | 1056 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-11-01 | 2024-12-14 | 1.117
439 | 7 | 395 | ZIELINIEC - KIEKRZ | IRS5/3 | szlak st. Koziegłowy - st. Poznań Piątkowo | 1 | 4.42 | 13.41 | installation of a temporary trapezoid track | 7 | 24 | 168 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 7 | single-track two-way traffic on the active track | 2024-06-14 | 2024-06-20 | 1.117
440 | 7 | 395 | ZIELINIEC - KIEKRZ | IRS5/3 | szlak st. Koziegłowy - st. Poznań Piątkowo | 2 | 4.5 | 13.3 | installation of a temporary trapezoid track | 7 | 24 | 168 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 7 | single-track two-way traffic on the active track | 2024-06-21 | 2024-06-27 | 1.117
441 | 7 | 395 | ZIELINIEC - KIEKRZ | IRS5/3 | st. Poznań Franowo - p.odg. Stary Młyn | 1 | 4.85 | 10.7 | renovation | 41 | 24 | 984 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 27; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-11-04 | 2024-12-14 | 1.117
442 | 7 | 395 | ZIELINIEC - KIEKRZ | IRS5/3 | szlak tymczasowy p.odg. Naramowice - st. Poznań Piątkowo | 2 | 7.41 | 13.33 | renovation | 7 | 4 | 28 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 3; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 4 | traffic interruption | 2024-06-28 | 2024-07-04 | 1.117
443 | 7 | 395 | ZIELINIEC - KIEKRZ | IRS5/3 | szlak tymczasowy p.odg. Naramowice - st. Poznań Piątkowo | 2 | 7.41 | 13.33 | renovation | 44 | 24 | 1056 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2024-11-01 | 2024-11-07 | 1.117
444 | 7 | 395 | ZIELINIEC - KIEKRZ | IRS5/3 | szlak tymczasowy p.odg. Naramowice - st. Poznań Piątkowo | 1 | 7.54 | 13.41 | renovation | 126 | 24 | 3024 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 3; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31 | single-track two-way traffic on the active track | 2024-06-28 | 2024-10-31 | 1.117
445 | 7 | 395 | ZIELINIEC - KIEKRZ | IRS5/3 | st. Poznań Franowo - p.odg. Stary Młyn | 2 | 8.25 | 10.5 | renovation | 4 | 4 | 16 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 4 | traffic interruption | 2024-11-04 | 2024-11-07 | 1.117
446 | 7 | 395 | ZIELINIEC - KIEKRZ | IRS5/3 | st. Poznań Piątkowo | 2,4,6,8,10 | 13.1 | 14.45 | renovation | 35 | 24 | 840 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 17; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 18 | traffic on active track at the station | 2024-03-15 | 2024-04-18 | 1.117
447 | 7 | 395 | ZIELINIEC - KIEKRZ | IRS5/3 | st. Poznań Piątkowo | 1, 3, 5 | 13.39 | 14.67 | renovation | 35 | 24 | 840 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 4; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31 | traffic on active track at the station | 2024-09-27 | 2024-10-31 | 1.117
448 | 7 | 395 | ZIELINIEC - KIEKRZ | IRS5/3 | szlak st. Poznań Piątkowo - st. Kiekrz | 2 | 14.45 | 19.65 | renovation | 35 | 24 | 840 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 17; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 18 | single-track two-way traffic on the active track | 2024-03-15 | 2024-04-18 | 1.117
449 | 7 | 395 | ZIELINIEC - KIEKRZ | IRS5/3 | szlak st. Poznań Piątkowo - st. Kiekrz | 1 | 14.47 | 19.73 | renovation | 7 | 4 | 28 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 7 | traffic interruption | 2024-03-15 | 2024-03-21 | 1.117
450 | 7 | 395 | ZIELINIEC - KIEKRZ | IRS5/3 | szlak st. Poznań Piątkowo - st. Kiekrz | 1 | 14.47 | 19.73 | renovation | 56 | 24 | 1344 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 12; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 13 | single-track two-way traffic on the active track | 2024-04-19 | 2024-06-13 | 1.117
451 | 8 | 405 | PIŁA GŁÓWNA - USTKA | IRR2/1 | szlak Słupsk - Ustka | 1 | 175.004 | 193.285 | Works associated with the track works at the head at Sp1 and the railway viaduct of ul. Grunwaldzka | 143 | 24 | 3432 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 24; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 30 | traffic interruption – single-track line | 2024-01-08 | 2024-05-30 | 1.100
452 | 1 | 506 | WARSZAWA ANTONINÓW - WARSZAWA WAWER | IRR1/3 | Warszawa Wschodnia Towarowa- Warszawa Gocławek | 2 | -0.248 | 4.111 | railway line upgrade | 187 | 4 | 748 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 15 | single-track two-way traffic on the active track | 2023-12-10 | 2024-06-15 | 1.088
453 | 1 | 539 | ŁÓDŹ KALISKA TOWAROWA - RETKINIA | IRR1/9 | Łódź Kaliska Towarowa - Retkinia tor 1,2 | 1, 2 | 0 | 1.714 | Touch-up painting of substructures | 1 | 24 | 24 | traffic interruption | no limit | [13 empty] | traffic interruption | 2024-03-20 | 2024-03-20 | 1.105 | bar: Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III
454 | 5 | 542 | GAJEWNIKI - ZDUŃSKA WOLA KARSZNICE | IRR1/9 | Gajewniki - Karsznice tor 1 | 1 | 3.537 | 7.434 | Touch-up painting of substructures | 2 | 24 | 48 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 2 | traffic interruption – single-track line | 2024-10-13 | 2024-10-14 | 1.105
455 | 5 | 543 | GAJEWNIKI - DIONIZÓW | IRR1/9 | Gajewnik - Dionizów tor 1 | 1 | -0.087 | 2.177 | Touch-up painting of substructures | 5 | 24 | 120 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 5 | traffic interruption – single-track line | 2024-08-20 | 2024-08-24 | 1.105
456 | 2 | 570 | PSARY - STARZYNY | IRR1/13 | Psary - Starzyny | 1 | 0.519 | 2.573 | piling, installation of new substructures, gantry supports, fixtures, reconstruction of the existing contact line, installation of relief structures on the viaduct at km 170.833 | 26 | 6 | 156 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 5; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-05-27 | 2024-06-21
457 | 2 | 570 | PSARY - STARZYNY | IRR1/13 | Psary - Starzyny | 1 | 0.519 | 2.573 | piling, installation of new substructures, gantry supports, fixtures, reconstruction of the existing contact line, installation of relief structures on the viaduct at km 170.833 | 16 | 24 | 384 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 15; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 1 | traffic interruption – single-track line | 2024-09-16 | 2024-10-01
458 | 4 | 654 | SZABELNIA - KATOWICE SZOPIENICE PÓŁNOCNE | IRR4/4 | Szabelnia - Katowice Szopienice Północne | 1 | 0.15 | 1.29 | upgrade | 22 | 24 | 528 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 1 | traffic interruption – single-track line | 2023-04-01 | 2024-01-01
459 | 4 | 657 | KATOWICE SZOPIENICE PÓŁNOCNE - KATOWICE MUCHOWIEC KMA | IRR4/4 | Katowice Szopienice Północne - Stawiska | 1 | 0.153 | 0.97 | upgrade | 22 | 24 | 528 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 1 | traffic interruption – single-track line | 2023-04-01 | 2024-01-01
460 | 4 | 660 | SOSNOWIEC POŁUDNIOWY - SOSNOWIEC GŁÓWNY | IRR4/4 | Sosnowiec Południowy - Sosnowiec Główny SG52 | 1 | 0.532 | 1.05 | upgrade | 82 | 24 | 1968 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 24; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 27 | traffic on active track at the station | 2024-09-07 | 2024-11-27
461 | 4 | 694 | BRONÓW PODG - BIENIOWIEC | IRR4/4 | Bronów - Bieniowiec | 1 | 0 | 2.6 | upgrade | 181 | 24 | 4344 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 14; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption – single-track line | 2024-06-17 | 2024-12-17
462 | 4 | 703 | KUCELINKA - CZĘSTOCHOWA | IRR4/3 | Częstochowa Towarowa | 57 | 4.175 | 5.706 | facilities, railroad surface, overhead contact line, Railway Traffic Controlling system [srk], power supply | 13 | 24 | 312 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 6; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 7 | traffic on active track at the station | 2024-08-26 | 2024-09-07
463 | 5 | 737 | PONĘTÓW - BARŁOGI | IRR2/9 | Ponętów - Barłogi | 1 | 1 | 3.637 | end-to-end surface replacement, installation of Rz26, 35 Ponętów station | 15 | 24 | 360 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 1; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption – single-track line | 2024-11-30 | 2025-01-28
464 | 5 | 739 | ZDUŃSKA WOLA KARSZNICE - ZDUŃSKA WOLA | IRR1/9 | Zduńska Wola - Karsznice tor 1 | 1 | -0.301 | 5.214 | Touch-up painting of substructures | 3 | 24 | 72 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 3 | traffic interruption – single-track line | 2024-10-13 | 2024-10-15 | 1.105
465 | 5 | 740 | PONĘTÓW - ZAMKÓW | IRR2/9 | Ponętów - Zamków | 1 | 0.68 | 2.753 | end-to-end surface replacement | 91 | 24 | 2184 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 1; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 29 | traffic interruption – single-track line | 2024-08-31 | 2024-11-29
466 | 5 | 741 | MIMOWOLA - JAKSICE | IRR2/9 | Mimowola - Jaksice | 1 | 0.2 | 6.34 | installation of switches Mimowola Podg. | 30 | 24 | 720 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30 | single-track two-way traffic on the active track | 2024-09-01 | 2024-09-30
467 | 5 | 741 | MIMOWOLA - JAKSICE | IRR2/9 | Jaksice - Mimowola | 2 | 0.2 | 6.34 | installation of switches Mimowola Podg. | 55 | 24 | 1320 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 24 | single-track two-way traffic on the active track | 2024-10-01 | 2024-11-24
468 | 7 | 801 | POZNAŃ STAROŁĘKA PSK - POZNAŃ GÓRCZYN | IRS5/3 | st. Poznań Starołęka | 1 | 0 | 0.2 | renovation | 156 | 24 | 3744 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 20; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-07-12 | 2024-12-19 | 1.117
469 | 7 | 801 | POZNAŃ STAROŁĘKA PSK - POZNAŃ GÓRCZYN | IRS5/3 | st. Poznań Starołęka - st. Poznań Górczyn | 2 | 0.2 | 2.25 | renovation | 7 | 4 | 28 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 7 | traffic interruption | 2022-12-16 | 2023-12-10 | 1.117
470 | 7 | 801 | POZNAŃ STAROŁĘKA PSK - POZNAŃ GÓRCZYN | IRS5/3 | st. Poznań Starołęka - st. Poznań Górczyn | 2 | 0.2 | 2.25 | renovation | 105 | 24 | 2520 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 3; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 11 | single-track two-way traffic on the active track | 2024-03-29 | 2024-07-11 | 1.117
471 | 7 | 801 | POZNAŃ STAROŁĘKA PSK - POZNAŃ GÓRCZYN | IRS5/3 | st. Poznań Starołęka - st. Poznań Górczyn | 1 | 0.5 | 3.25 | renovation | 110 | 24 | 2640 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 22; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 28 | single-track two-way traffic on the active track | 2023-12-10 | 2024-03-28 | 1.117
472 | 7 | 801 | POZNAŃ STAROŁĘKA PSK - POZNAŃ GÓRCZYN | IRS5/3 | st. Poznań Starołęka - st. Poznań Górczyn | 1 | 0.5 | 3.25 | renovation | 7 | 4 | 28 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 3; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 4 | traffic interruption | 2024-03-29 | 2024-04-04 | 1.117
473 | 7 | 802 | POZNAŃ STAROŁĘKA PSK - LUBOŃ K. POZNANIA | IRS5/3 | st. Poznań Starołęka | 2 | 0 | 0.2 | renovation | 150 | 24 | 3600 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 14; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-07-19 | 2024-12-19 | 1.117
474 | 7 | 802 | POZNAŃ STAROŁĘKA PSK - LUBOŃ K. POZNANIA | IRS5/3 | st. Poznań Starołęka - st. Luboń k/Poznania | 2 | 0.15 | 4.15 | renovation | 110 | 24 | 2640 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 22; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 28 | single-track two-way traffic on the active track | 2023-12-10 | 2024-03-28 | 1.117
475 | 7 | 802 | POZNAŃ STAROŁĘKA PSK - LUBOŃ K. POZNANIA | IRS5/3 | st. Poznań Starołęka - st. Luboń k/Poznania | 2 | 0.15 | 4.15 | renovation | 7 | 4 | 28 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 3; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 4 | traffic interruption | 2024-03-29 | 2024-04-04 | 1.117
476 | 7 | 802 | POZNAŃ STAROŁĘKA PSK - LUBOŃ K. POZNANIA | IRS5/3 | st. Poznań Starołęka - st. Luboń k/Poznania | 1 | 0.3 | 3.4 | renovation | 7 | 4 | 28 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 7 | traffic interruption | 2023-12-10 | 2023-12-16 | 1.117
477 | 7 | 802 | POZNAŃ STAROŁĘKA PSK - LUBOŃ K. POZNANIA | IRS5/3 | st. Poznań Starołęka - st. Luboń k/Poznania | 1 | 0.3 | 3.4 | renovation | 105 | 24 | 2520 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 3; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 11 | single-track two-way traffic on the active track | 2024-03-29 | 2024-07-11 | 1.117
478 | 7 | 803 | POZNAŃ PIĄTKOWO - SUCHY LAS | IRS5/3 | szlak st. Poznań Piątkowo - p.odg. Suchy Las | 1 | 0 | 0.9 | renovation | 35 | 24 | 840 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 4; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31 | traffic interruption – single-track line | 2024-09-27 | 2024-10-31 | 1.117
479 | 7 | 805 | SWARZĘDZ - STARY MŁYN | IRS5/3 | st. Swarzędz - p.odg. Stary Młyn | 1 | 0 | 1.45 | renovation | 156 | 24 | 3744 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 20; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption – single-track line | 2024-07-12 | 2024-12-19 | 1.117
480 | 5 | 810 | ZDUŃSKA WOLA - DIONIZÓW | IRR1/9 | Zduńska Wola - Dionizów tor 1 | 1 | -0.296 | 2.85 | Touch-up painting of substructures | 2 | 24 | 48 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 2 | traffic interruption – single-track line | 2024-09-28 | 2024-09-29 | 1.105
481 | 7 | 823 | POZNAŃ FRANOWO PFD - STARY MŁYN | IRS5/3 | st. Poznań Franowo - p.odg. Stary Młyn | 1 | 0 | 4.7 | renovation | 156 | 24 | 3744 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 20; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption – single-track line | 2024-07-12 | 2024-12-19 | 1.117
482 | 7 | 824 | POKRZYWNO - POZNAŃ FRANOWO PFD | IRS5/3 | p.odg. Pokrzywno - st. Poznań Franowo | 1 | 0.15 | 3.3 | renovation | 110 | 24 | 2640 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 22; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 28 | single-track two-way traffic on the active track | 2023-12-10 | 2024-03-28 | 1.117
483 | 1 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR1/11 | stacja Warszawa Zachodnia | 4 | 2,425 | 3,600 | Upgrade of the station layout, construction of subway, roofing of platforms | 14 | 24 | 336 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2023-12-10 | 2023-12-24 | 1.093
484 | 1 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR1/11 | stacja Warszawa Zachodnia | 3 | 2,638 | 2,658 | Speed limit at the temporary crossing at km 2.648 to 20 km/h | 14 | 24 | 336 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2023-12-10 | 2023-12-24 | 1.093
485 | 1 | 1 | WARSZAWA ZACHODNIA - KATOWICE | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Włochy | 1S, 2S | 3,082 | 6,804 | Integration of WZP-WZD station locks into EBILock devices | 50 | 6 | 300 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 29 | traffic interruption | 2023-12-10 | 2024-01-29 | 1.093
486 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | Warszawa Rembertów | 1m, 2m | 11.45 | 11.955 | construction tunnel at ul. Marsa | 141 | 24 | 3384 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30 | traffic on active track at the station | 2023-12-10 | 2024-04-30 | 1.066
487 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | Warszawa Rembertów - Sulejówek Miłosna | 1 | 13.185 | 20.96 | tunnel construction in Warsaw Wesoła | 17 | 24 | 408 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 17 | single-track two-way traffic on the active track | 2024-04-01 | 2024-04-17 | 1.066
488 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | Warszawa Rembertów - Sulejówek Miłosna | 2 | 13.185 | 20.96 | tunnel construction in Warsaw Wesoła | 17 | 24 | 408 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 17 | single-track two-way traffic on the active track | 2024-11-01 | 2024-11-17 | 1.066
489 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | Warszawa Rembertów - Sulejówek Miłosna | 1 | 13.185 | 20.96 | Construction of a road tunnel at ul. Krasińskiego | 31 | 24 | 744 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 25; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 6 | single-track two-way traffic on the active track | 2024-01-07 | 2024-02-06
490 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | Warszawa Rembertów - Sulejówek Miłosna | 1, 2 | 13.185 | 20.96 | tunnel construction in Warsaw Wesoła | 342 | 4 | 1368 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 17 |  | traffic interruption | 2023-09-01 | 2024-11-17
491 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | stacja Warszawa Zachodnia | 301 | -2,378 | -1,922 | Upgrade of the station layout, construction of subway, roofing of platforms | 14 | 24 | 336 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2023-12-10 | 2023-12-24 | 1.093
492 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Centralna | 1 | -2,425 | 0,000 | Upgrade of the station layout, construction of subway, roofing of platforms | 14 | 24 | 336 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2023-12-10 | 2023-12-24 | 1.093
493 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Centralna | 1 | -2,425 | 0,000 | Integration of WZP-WZD station locks into EBILock devices | 36 | 6 | 216 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 7; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 29 | traffic interruption | 2023-12-25 | 2024-01-29 | 1.093
494 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Centralna | 2 | -2,425 | 0,000 | Integration of WZP-WZD station locks into EBILock devices | 50 | 6 | 300 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 29 | traffic interruption | 2023-12-10 | 2024-01-29 | 1.093
495 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Centrana | 1 | -2,425 | 0,000 | Upgrade of the station layout, construction of subway, roofing of platforms | 15 | 6 | 90 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 7; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 8 | traffic interruption | 2023-12-25 | 2024-01-08 | 1.093
496 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | Warszawa Antoninów - Warszawa Rembertów | 1m | 7.85 | 9.855 | construction of a viaduct at ul. Chełmżyńska | 9 | 24 | 216 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 9 | single-track two-way traffic on the active track | 2024-01-08 | 2024-01-16 | 1.066
497 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | Warszawa Rembertów | 1m, 2m | 11.45 | 11.955 | construction tunnel at ul. Marsa | 153 | 4 | 612 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30 | traffic on active track at the station | 2024-05-01 | 2024-09-30 | 1.066
498 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | Warszawa Rembertów | 1m, 2m | 11.45 | 11.955 | construction tunnel at ul. Marsa | 42 | 24 | 1008 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-11-02 | 2025-03-31 | 1.066
499 | 1 | 448 | WARSZAWA ZACHODNIA - WARSZAWA REMBERTÓW | IRR1/11 | Warszawa Rembertów | 3m, 4m | 11.45 | 11.955 | construction tunnel at ul. Marsa | 42 | 4 | 168 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2024-11-02 | 2025-03-31 | 1.066
500 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | Warszawa Antoninów - Warszawa Rembertów | 2m | 7.85 | 9.855 | construction of a viaduct at ul. Chełmżyńska | 11 | 24 | 264 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 6; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 5 | single-track two-way traffic on the active track | 2024-01-26 | 2024-02-05 | 1.066
501 | 1 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR1/11 | stacja Warszawa Zachodnia | 6 | 2,515 | 3,400 | Upgrade of the station layout, construction of subway, roofing of platforms | 14 | 24 | 336 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2023-12-10 | 2023-12-24 | 1.093
502 | 1 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Włochy | 2Ł | 3,082 | 6,804 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 50 | 24 | 1200 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 29 | traffic on the parallel line tracks | 2023-12-10 | 2024-01-29 | 1.093
503 | 1 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IRR1/11 | stacja Warszawa Zachodnia | 5 | 2,638 | 2,658 | Speed limit at the temporary crossing at km 2.648 to 20 km/h | 14 | 24 | 336 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2023-12-10 | 2023-12-24 | 1.093
504 | 1 | 19 | WARSZAWA GŁÓWNA TOWAROWA - JÓZEFINÓW | IRR1/11 | stacja Warszawa Zachodnia | 447 | 2,800 | 3,300 | Upgrade of the station layout, construction of subway, roofing of platforms | 21 | 24 | 504 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 21 | traffic on active track at the station | 2024-01-09 | 2024-01-29 | 1.093
505 | 1 | 23 | WARSZAWA GŁÓWNA OSOBOWA - WARSZAWA ZACHODNIA T2/1G, 12/2G | IRR1/11 | stacja Warszawa Zachodnia - Warszawa Główna Osobowa | 1Gł | 1,930 | 2,461 | Integration of WZP-WZD station locks into EBILock devices | 14 | 6 | 84 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption | 2023-12-10 | 2023-12-24 | 1.093
506 | 1 | 23 | WARSZAWA GŁÓWNA OSOBOWA - WARSZAWA ZACHODNIA T2/1G, 12/2G | IRR1/11 | stacja Warszawa Zachodnia - Warszawa Główna Osobowa | 1Gł, 2Gł | 1,930 | 2,461 | Integration of WZP-WZD station locks into EBILock devices | 36 | 6 | 216 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 7; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 29 | traffic interruption | 2023-12-25 | 2024-01-29 | 1.093
507 | 1 | 23 | WARSZAWA GŁÓWNA OSOBOWA - WARSZAWA ZACHODNIA T2/1G, 12/2G | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Główna Osobowa | 2G | 1,930 | 2,641 | Upgrade of the station layout, construction of subway, roofing of platforms | 14 | 24 | 336 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | single-track two-way traffic on the active track | 2023-12-10 | 2023-12-24 | 1.093
508 | 1 | 46 | WARSZAWA ZACHODNIA - WARSZAWA CZYSTE T201,2S | IRR1/11 | stacja Warszawa Zachodnia | 10 | 2,943 | 3,586 | Upgrade of the station layout, construction of subway, roofing of platforms | 21 | 24 | 504 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 21 | traffic on active track at the station | 2024-01-09 | 2024-01-29 | 1.093
509 | 1 | 46 | WARSZAWA ZACHODNIA - WARSZAWA CZYSTE T201,2S | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Czyste | 1001, 1002 | 3,753 | 4,035 | Upgrade of the station layout, construction of subway, roofing of platforms | 14 | 24 | 336 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption | 2023-12-10 | 2023-12-24 | 1.093
510 | 1 | 447 | WARSZAWA ZACHODNIA - GRODZISK MAZOWIECKI | IRR1/11 | stacja Warszawa Zachodnia | 20, 23 | 2,296 | 2,735 | Upgrade of the station layout, construction of subway, roofing of platforms | 15 | 24 | 360 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 7; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 8 | traffic on active track at the station | 2023-12-25 | 2024-01-08 | 1.093
511 | 1 | 447 | WARSZAWA ZACHODNIA - GRODZISK MAZOWIECKI | IRR1/11 | stacja Warszawa Zachodnia | 101 | 2,600 | 2,800 | Upgrade of the station layout, construction of subway, roofing of platforms | 14 | 24 | 336 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic on active track at the station | 2023-12-10 | 2023-12-24 | 1.093
512 | 1 | 447 | WARSZAWA ZACHODNIA - GRODZISK MAZOWIECKI | IRR1/11 | stacja Warszawa Zachodnia | 31, 31a | 2,760 | 3,263 | Upgrade of the station layout, construction of subway, roofing of platforms | 21 | 24 | 504 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 21 | traffic on active track at the station | 2024-01-09 | 2024-01-29 | 1.093
513 | 1 | 447 | WARSZAWA ZACHODNIA - GRODZISK MAZOWIECKI | IRR1/11 | stacja Warszawa Zachodnia | 23 | 2,812 | 3,330 | Upgrade of the station layout, construction of subway, roofing of platforms | 21 | 24 | 504 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 21 | traffic on active track at the station | 2024-01-09 | 2024-01-29 | 1.093
514 | 1 | 448 | WARSZAWA ZACHODNIA - WARSZAWA REMBERTÓW | IRR1/11 | Warszawa Rembertów | 3m, 4m | 11.45 | 11.955 | construction tunnel at ul. Marsa | 153 | 24 | 3672 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30 | traffic on active track at the station | 2024-05-01 | 2024-09-30 | 1.066
515 | 1 | 448 | WARSZAWA ZACHODNIA - WARSZAWA REMBERTÓW | IRR1/11 | szlak Warszawa Zachodnia - Warszawa Wschodnia/p.o. Warszawa Ochota | 3ŚR, 4ŚR | -2,396 | -1,100 | Upgrade of the station layout, construction of subway, roofing of platforms | 14 | 4 | 56 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption | 2023-12-10 | 2023-12-24 | 1.093
516 | 1 | 448 | WARSZAWA ZACHODNIA - WARSZAWA REMBERTÓW | IRR1/11 | Warszawa Rembertów | 3m, 4m | 11.45 | 11.955 | construction tunnel at ul. Marsa | 141 | 4 | 564 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30 | traffic on active track at the station | 2023-12-10 | 2024-04-30 | 1.066
517 | 1 | 452 | WARSZAWA WSCHODNIA OSOBOWA - WARSZAWA GROCHÓW T4G | IRR1/11 | szlak Warszawa Wschodnia - Warszawa Grochów | 4G | 4,690 | 7,499 | Upgrade of railway lines and railway stations, RTC works | 15 | 24 | 360 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 7; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 8 | traffic interruption – single-track line | 2023-12-25 | 2024-01-08 | 1.093
518 | 1 | 448 | WARSZAWA ZACHODNIA - WARSZAWA REMBERTÓW | IRR1/11 | Warszawa Podskarbińska - Warszawa Rembertów | 3m, 4m | 6.07 | 10.3 | construction of a viaduct at ul. Chełmżyńska | 369 | 4 | 1476 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption | 2023-08-01 | 2025-07-31 | 1.066
519 | 1 | 2 | WARSZAWA ZACHODNIA - TERESPOL | IRR1/11 | Warszawa Antoninów - Warszawa Rembertów | 1m, 2m | 7.85 | 9.855 | construction of a viaduct at ul. Chełmżyńska | 369 | 4 | 1476 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption | 2023-08-01 | 2025-07-31 | 1.066
520 | 1 | 546 | WARSZAWA WSCHODNIA TOWAROWA - WARSZAWA REMBERTÓW T6M | IRR1/11 | Warszawa Antoninów - Warszawa Rembertów | 6m | 8 | 9.875 | construction of a viaduct at ul. Chełmżyńska | 369 | 4 | 1476 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption – single-track line | 2023-08-01 | 2025-07-31 | 1.066
521 | 1 | 901 | WARSZAWA WSCHODNIA TOWAROWA - WARSZAWA REMBERTÓW T5M | IRR1/11 | Warszawa Antoninów - Warszawa Rembertów | 5m | 8 | 10.003 | construction of a viaduct at ul. Chełmżyńska | 369 | 4 | 1476 | traffic interruption | no limit | 21 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 14 | traffic interruption – single-track line | 2023-08-01 | 2025-07-31 | 1.066
522 | 1 | 902 | WARSZAWA WSCHODNIA - WARSZAWA WSCHODNIA TOWAROWA T2P | IRR1/11 | szlak Warszawa Wschodnia - Warszawa Podskarbińska | 2P | 4,951 | 5,988 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 15 | 24 | 360 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 7; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 8 | traffic interruption – single-track line | 2023-12-25 | 2024-01-08 | 1.093
523 | 1 | 920 | WARSZAWA ZACHODNIA R 578 - WARSZAWA ZACHODNIA R 217 | IRR1/11 | stacja Warszawa Zachodnia | 101, 102 | 3,946 | 4,411 | Upgrade of railway lines and railway stations, works on Railway Traffic Controlling system [srk] | 50 | 24 | 1200 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 29 | traffic on active track at the station | 2023-12-10 | 2024-01-29 | 1.093
524 | 1 | 920 | WARSZAWA ZACHODNIA R 578 - WARSZAWA ZACHODNIA R 217 | IRR1/11 | stacja Warszawa Zachodnia | 101, 102 | 3,946 | 4,411 | Integration of WZP-WZD station locks into EBILock devices | 50 | 6 | 300 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 29 | traffic on active track at the station | 2023-12-10 | 2024-01-29 | 1.093
525 | 1 | 24 | PIOTRKÓW TRYBUNALSKI - ZARZECZE | IZ Łódź | Bełchatów - Zarzecze | 1 | 26.768 | 26.768 | Renovation of the railway viaduct at km 26.768 | 61 | 24 | 1464 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31 | traffic interruption – single-track line | 2023-04-01 | 2023-05-31
526 | 2 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IZ Kielce | Kielce Białogon - Sitkówka Nowiny | 1 | 194,870 | 194,900 | Major renovation of the viaduct at km 1.294 of line 568 | 49 | 24 | 1176 | 30 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 18; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31 | single-track two-way traffic on the active track | 2024-08-01 | 2024-08-30
527 | 2 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IZ Kielce | Kielce Białogon - Sitkówka Nowiny | 2 | 194,870 | 194,900 | Major renovation of the viaduct at km 1.294 of line 568 | 30 | 24 | 720 | 30 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 19; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 11 | single-track two-way traffic on the active track | 2024-09-02 | 2024-09-12
528 | 2 | 25 | ŁÓDŹ KALISKA - DĘBICA | IZ Skarżysko-Kamienna | Bratków - Opoczno | 1 | 67.693 | 81.391 | Major track repair | 122 | 24 | 2928 | traffic interruption | 120 km/h | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31 | traffic interruption – single-track line | 2024-04-01 | 2024-07-31
529 | 2 | 61 | KIELCE - FOSOWSKIE | IZ Kielce | Kielce Herbskie | 2,4,6 | 1,360 | 6,000 | Replacement of switches at Kielce Herbskie station | 59 | 24 | 1416 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 28; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31 | traffic on active track at the station | 2024-06-03 | 2024-06-30
530 | 2 | 61 | KIELCE - FOSOWSKIE | IZ Kielce | Kielce Herbskie | 1.22 | 1.36 | 6 | Replacement of switches at Kielce Herbski station | 26 | 24 | 624 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 26 | traffic on active track at the station | 2024-05-06 | 2024-06-30
531 | 2 | 61 | KIELCE - FOSOWSKIE | IZ Kielce | Górki Szczukowskie - Rykoszyn | 1 | 8,350 | 14,530 | AHM substructure reinforcement | 92 | 24 | 2208 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31 | single-track two-way traffic on the active track | 2024-08-01 | 2024-10-31
532 | 2 | 61 | KIELCE - FOSOWSKIE | IZ Kielce | Rykoszyn | 1.3 | 17,700 | 18.783 | Maintenance and repair works at Rykoszyn station | 61 | 24 | 1464 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30 | single-track two-way traffic on the active track | 2024-08-01 | 2024-10-31
533 | 2 | 61 | KIELCE - FOSOWSKIE | IZ Kielce | Rykoszyn | 2 | 17.7 | 18.783 | Maintenance and repair works at Rykoszyn station | 31 | 24 | 744 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31 | single-track two-way traffic on the active track | 2024-07-01 | 2024-07-31
534 | 2 | 61 | KIELCE - FOSOWSKIE | IZ Kielce | Czarnca - Żelisławice | 1 | 53,800 | 58,330 | AHM substructure reinforcement | 61 | 24 | 1464 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31 | single-track two-way traffic on the active track | 2024-04-01 | 2024-05-31
535 | 2 | 61 | KIELCE - FOSOWSKIE | IZ Kielce | Włoszczowa - Żelisławice | 2 | 58,330 | 53,530 | AHM substructure reinforcement | 61 | 24 | 1464 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31 | single-track two-way traffic on the active track | 2024-06-01 | 2024-07-31
536 | 2 | 61 | KIELCE - FOSOWSKIE | IZ Kielce | Żelisławice - Czarnca | 2 | 58.33 | 53.53 | AHM substructure reinforcement | 61 | 24 | 1464 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31 | single-track two-way traffic on the active track | 2024-06-01 | 2024-07-31
537 | 2 | 64 | KOZŁÓW - KONIECPOL | IZ Kielce | Starzyny - Koniecpol podg Starzyny | 1 | 32.719 | 39.742 | Major repair of track no. 1, replacement of a switch no. 6 at Starzyny Podg. | 92 | 24 | 2208 | 60 km/h | 60 km/h | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31 | traffic interruption – single-track line | 2024-06-01 | 2024-08-31
538 | 2 | 66 | ZWIERZYNIEC TOWAROWY - STALOWA WOLA POŁUDNIE | IZ Lublin | Biłgoraj - Huta Krzeszowska | 1 | 23.26 | 30 | Mechanical cleaning of the track with surface replacement | 59 | 24 | 1416 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 29 | traffic interruption – single-track line | 2024-04-02 | 2024-05-29
539 | 2 | 70 | WŁOSZCZOWICE - CHMIELÓW | IZ Kielce | Raczyce - Grzybów | 1 | 28,400 33,800 | 30,400 35,600 | AHM substructure reinforcement | 61 | 24 | 1464 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 12; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 19 | traffic interruption – single-track line | 2024-10-20 | 2024-12-19
540 | 2 | 70 | WŁOSZCZOWICE - CHMIELÓW | IZ Kielce | Włoszczowice - Chmielnik | 1 | 0 | 48 | Maintenance and repair work | 30 | 24 | 720 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 12; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 18 | traffic interruption – single-track line | 2024-10-20 | 2024-11-18
541 | 2 | 70 | WŁOSZCZOWICE - CHMIELÓW | IZ Kielce | Chmielnik - Raczyce | 1 | 0 | 48 | Maintenance and repair work | 30 | 24 | 720 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 12; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 18 | traffic interruption – single-track line | 2024-10-20 | 2024-11-18
542 | 2 | 70 | WŁOSZCZOWICE - CHMIELÓW | IZ Kielce | Raczyce - Grzybów | 1 | 0 | 48 | Maintenance and repair work | 30 | 24 | 720 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 12; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 18 | traffic interruption – single-track line | 2024-10-20 | 2024-11-18
543 | 2 | 70 | WŁOSZCZOWICE - CHMIELÓW | IZ Kielce | Grzybów - Staszów | 1 | 0 | 48 | Maintenance and repair work | 30 | 24 | 720 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 12; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 18 | traffic interruption – single-track line | 2024-10-20 | 2024-11-18
544 | 2 | 70 | WŁOSZCZOWICE - CHMIELÓW | IZ Kielce | Staszów - Rytwiany | 1 | 50,000 | 82,900 | Maintenance and repair work | 14 | 24 | 336 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 14 | traffic interruption – single-track line | 2024-06-05 | 2024-06-18
545 | 2 | 70 | WŁOSZCZOWICE - CHMIELÓW | IZ Kielce | Rytwiany- Strzegomek | 1 | 50,000 | 82,900 | Maintenance and repair work | 14 | 24 | 336 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 14 | traffic interruption – single-track line | 2024-06-05 | 2024-06-18
546 | 2 | 70 | WŁOSZCZOWICE - CHMIELÓW | IZ Kielce | Strzegomek - Chmielów | 1 | 50,000 | 82,900 | Maintenance and repair work | 14 | 24 | 336 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 14 | traffic interruption – single-track line | 2024-06-05 | 2024-06-18
547 | 2 | 70 | WŁOSZCZOWICE - CHMIELÓW | IZ Kielce | Staszów - Rytwiany | 1 | 50,130 | 50,160 | Major repair of viaduct at km 50.145 | 14 | 24 | 336 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 14 | traffic interruption – single-track line | 2024-06-05 | 2024-06-18
548 | 2 | 70 | WŁOSZCZOWICE - CHMIELÓW | IZ Kielce | Strzegomek - Chmielów | 1 | 67,000 | 70,300 | AHM substructure reinforcement | 60 | 24 | 1440 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 2; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 27 | traffic interruption – single-track line | 2024-04-29 | 2024-06-27
549 | 2 | 73 | SITKÓWKA NOWINY - BUSKO ZDRÓJ | IZ Kielce | Sitkówka Nowiny - Nida | 1 | 1,090; 1,835; 3,185 5,450 | 1,140; 1,885; 3,265 5,490 | Major renovation of engineering structures | 80 | 24 | 1920 | 30 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 19; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31 | single-track two-way traffic on the active track | 2024-05-13 | 2024-07-31
550 | 2 | 73 | SITKÓWKA NOWINY - BUSKO ZDRÓJ | IZ Kielce | Nida - Włoszczowice | 1 | 8,300; 15,290 17,700 | 8,400; 15,340 17,750 | Major renovation of engineering structures | 86 | 24 | 2064 | 30 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 25; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31 | single-track two-way traffic on the active track | 2024-05-06 | 2024-07-31
551 | 2 | 73 | SITKÓWKA NOWINY - BUSKO ZDRÓJ | IZ Kielce | Nida - Sitkówka Nowiny | 2 | 1,090; 1,835; 3,185 5,450 | 1,140; 1,885; 3,265 5,490 | Major renovation of engineering structures | 79 | 24 | 1896 | 30 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 18 | single-track two-way traffic on the active track | 2024-08-01 | 2024-10-18
552 | 2 | 73 | SITKÓWKA NOWINY - BUSKO ZDRÓJ | IZ Kielce | Włoszczowice-Nida | 2 | 8,300; 15,290 17,700 | 8,400; 15,340 17,750 | Major renovation of engineering structures | 92 | 24 | 2208 | 30 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31 | single-track two-way traffic on the active track | 2024-08-01 | 2024-10-31
553 | 2 | 73 | SITKÓWKA NOWINY - BUSKO ZDRÓJ | IZ Kielce | Włoszczowice - Busko Zdrój | 1 | 19.542 | 44.449 | Maintenance and repair work | 92 | 12 | 1104 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31 | traffic interruption – single-track line | 2024-08-01 | 2024-10-31
554 | 2 | 73 | SITKÓWKA NOWINY - BUSKO ZDRÓJ | IZ Kielce | Włoszczowice | 4.6 | 19.015 | 20.921 | Renovation of tracks no. 4,5,6, 7 at Włoszczowice station together with replacement of switches | 61 | 24 | 1464 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30 | traffic on active track at the station | 2024-08-01 | 2024-09-30
555 | 2 | 73 | SITKÓWKA NOWINY - BUSKO ZDRÓJ | IZ Kielce | Włoszczowice | 5.7 | 19.015 | 20.921 | Renovation of tracks no. 4,5,6, 7 at Włoszczowice station together with replacement of switches | 61 | 24 | 1464 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30 | traffic on active track at the station | 2024-10-01 | 2024-11-30
556 | 2 | 75 | RYTWIANY - POŁANIEC | IZ Kielce | Rytwiany - Połaniec | 1 | 2,280 | 2,290 | Major repair of viaduct at km 2.286 | 14 | 24 | 336 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 14 | traffic interruption – single-track line | 2024-06-05 | 2024-06-18
557 | 2 | 568 | SITKÓWKA NOWINY - SZCZUKOWICE | IZ Kielce | Sitkówka Nowiny - Szczukowice | 1 | -0.44 | 6.82 | Major renovation of engineering structures | 114 | 24 | 2736 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 22; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31 | traffic interruption – single-track line | 2024-05-10 | 2024-08-31
558 | 2 | 568 | SITKÓWKA NOWINY - SZCZUKOWICE | IZ Kielce | Sitkówka - Szczukowice | 1 | 3.05 | 7.6 | Major repair of track no. 1 of line 568 Sitkówka – Szczukowice | 60 | 24 | 1440 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 30 | traffic interruption – single-track line | 2024-06-01 | 2024-07-30
559 | 2 | 571 | CZARNCA - KNAPÓWKA | IZ Kielce | Czarnca - Knapówka | 1 | 0.052 | 3.742 | AHM substructure reinforcement | 61 | 24 | 1464 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31 | traffic interruption – single-track line | 2024-06-01 | 2024-07-31
560 | 3 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IZ Kraków | Miechów-Tunel | 2 | 276.625 | 269.047 | Contact line upgrade | 7 | 24 | 168 |  | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 7 | single-track two-way traffic on the active track | 2024-09-15 | 2024-09-21
561 | 3 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IZ Kraków | Miechów | 2,4,6 | 277.177 | 278.1 | Contact line upgrade | 7 | 24 | 168 | 50 km/h-1000 m | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 7 | traffic on active track at the station | 2024-09-15 | 2024-09-21
562 | 3 | 8 | WARSZAWA ZACHODNIA - KRAKÓW GŁÓWNY | IZ Kraków | Słomniki | 2.4 | 289.82 | 290 | Contact line upgrade | 22 | 24 | 528 | 50 km/h-1000 m | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 22 | traffic on active track at the station | 2024-10-08 | 2024-10-29
563 | 3 | 91 | KRAKÓW GŁÓWNY - MEDYKA | IZ Kraków | st. Kłaj | 4 | 27.73 | 28.853 | Addition of a platform edge for platform no. 2 on track no. 4 at Kłaj station | 107 | 24 | 2568 | 50 km/h-1000 m | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 16; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30 | traffic on active track at the station | 2024-03-14 | 2024-06-30 | KPO
564 | 3 | 91 | KRAKÓW GŁÓWNY - MEDYKA | IZ Kraków | st.Wola Rzędzińska | 4 | 84.784 | 86.761 | Addition of platform edges on track no 4 at Wola Rzędzińska station | 62 | 24 | 1488 | 50 km/h-1000 m | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 7; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 24 | traffic on active track at the station | 2024-06-24 | 2024-08-24 | KPO
565 | 3 | 91 | KRAKÓW GŁÓWNY - MEDYKA | IZ Kraków | st.Wola Rzędzińska | 3 | 84.784 | 86.761 | Addition of platform edges on track no 3 at Wola Rzędzińska station | 98 | 24 | 2352 | 50 km/h-1000 m | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 7 | traffic on active track at the station | 2024-09-01 | 2024-12-07 | KPO
566 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Tarnów Filia - Kłokowa | 1 | 4 | 5.596 | major track repair | 81 | 24 | 1944 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-04-02 | 2024-06-21
567 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | mij. Kłokowa | 1.3 | 5.596 | 6.802 | major track repair | 81 | 24 | 1944 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-04-02 | 2024-06-21
568 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Kłokowa - Łowczówek Pleśna | 1 | 6.802 | 9.785 | major track repair | 81 | 24 | 1944 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-04-02 | 2024-06-21
569 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | st. Łowczówek Pleśna | 1.3 | 9.785 | 11.28 | major track repair | 81 | 24 | 1944 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-04-02 | 2024-06-21
570 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Łowczówek Pleśna - Łowczów | 1 | 11.28 | 15.483 | major track repair | 81 | 24 | 1944 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-04-02 | 2024-06-21
571 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | mij. Łowczów | 1.3 | 15.483 | 16.939 | major track repair | 81 | 24 | 1944 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-04-02 | 2024-06-21
572 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Łowczów - Tuchów | 1 | 16.939 | 20.25 | major track repair | 81 | 24 | 1944 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-04-02 | 2024-06-21
573 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | st. Tuchów | 1,3,5 | 20.25 | 21.703 | major track repair | 81 | 24 | 1944 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-04-02 | 2024-06-21
574 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Tuchów - Siedliska | 1 | 21.703 | 25.398 | major track repair | 81 | 24 | 1944 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-04-02 | 2024-06-21
575 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | mij. Siedliska | 1.3 | 25.398 | 26.667 | major track repair | 81 | 24 | 1944 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-04-02 | 2024-06-21
576 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Siedliska - Gromnik | 1 | 26.667 | 31.319 | major track repair | 81 | 24 | 1944 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-04-02 | 2024-06-21
577 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | st. Gromnik | 1,2,3 | 31.319 | 32.694 | major track repair | 81 | 24 | 1944 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-04-02 | 2024-06-21
578 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Gromnik - Bogoniowice Ciężkowice | 1 | 32.694 | 35.307 | major track repair | 81 | 24 | 1944 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-04-02 | 2024-06-21
579 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | st. Bogoniowice Ciężkowice | 1,2,3 | 35.307 | 36.856 | major track repair | 81 | 24 | 1944 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-04-02 | 2024-06-21
580 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Bogoniowice Ciężkowice - Zborowice | 1 | 36.856 | 39.572 | major track repair | 81 | 24 | 1944 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-04-02 | 2024-06-21
581 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | mij. Zborowice | 1.2 | 39.572 | 40.971 | major track repair | 81 | 24 | 1944 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-04-02 | 2024-06-21
582 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Zborowice - Bobowa | 1 | 40.971 | 46.488 | major track repair | 81 | 24 | 1944 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-04-02 | 2024-06-21
583 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | st. Bobowa | 1,2,3 | 46.488 | 48.284 | major track repair | 81 | 24 | 1944 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-04-02 | 2024-06-21
584 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Bobowa - Wilczyska | 1 | 48.284 | 53.086 | major track repair | 81 | 24 | 1944 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-04-02 | 2024-06-21
585 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | mij. Wilczyska | 1.3 | 53.086 | 54.426 | major track repair | 81 | 24 | 1944 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-04-02 | 2024-06-21
586 | 3 | 96 | TARNÓW - LELUCHÓW | IZ Nowy Sącz | Wilczyska - Stróże | 1 | 54.426 | 55.395 | major track repair | 81 | 24 | 1944 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-04-02 | 2024-06-21
587 | 3 | 105 | MUSZYNA - KRYNICA-ZDRÓJ | IZ Nowy Sącz | Muszyna - Powroźnik | 1 | 0.544 | 3.86 | reconstruction of Powroźnik station | 104 | 24 | 2496 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 22; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-03-10 | 2024-06-21
588 | 3 | 105 | MUSZYNA - KRYNICA-ZDRÓJ | IZ Nowy Sącz | st. Powroźnik | 1,2,3,4,6,8 | 3.86 | 6.012 | reconstruction of Powroźnik station | 104 | 24 | 2496 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 22; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-03-10 | 2024-06-21
589 | 3 | 105 | MUSZYNA - KRYNICA-ZDRÓJ | IZ Nowy Sącz | Powroźnik - Krynica-Zdrój | 1 | 6.012 | 9.656 | reconstruction of Powroźnik station | 104 | 24 | 2496 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 22; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 21 | traffic interruption – single-track line | 2024-03-10 | 2024-06-21
590 | 3 | 108 | STRÓŻE - KROŚCIENKO | IZ Nowy Sącz | Stróże - Wola Łużańska | 1 | 1.986 | 9.18 | major repair of track and engineering structures | 105 | 24 | 2520 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption – single-track line | 2024-09-01 | 2025-06-30
591 | 3 | 108 | STRÓŻE - KROŚCIENKO | IZ Nowy Sącz | st. Wola Łużańska | 1,3,5 | 9.18 | 10.651 | major repair of track and engineering structures | 105 | 24 | 2520 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption – single-track line | 2024-09-01 | 2025-06-30
592 | 3 | 108 | STRÓŻE - KROŚCIENKO | IZ Nowy Sącz | Wola Łużańska - Gorlice Zagórzany | 1 | 10.651 | 19.619 | major repair of track and engineering structures | 105 | 24 | 2520 | traffic interruption | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 14 | traffic interruption – single-track line | 2024-09-01 | 2025-06-30
593 | 4 | 714 | JAWORZNO SZCZAKOWA JSE - PIECZYSKA T3P | IZ SOSNOWIEC | JAWORZNO SZCZAKOWA - PIECZYSKA | 3P | 0 | 4.3 | End-to-end surface replacement including facilities | 183 | 24 | 4392 | 20 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30 | traffic interruption – single-track line | 2024-04-01 | 2024-09-30
594 | 6 | 281 | OLEŚNICA - CHOJNICE | IZ Wrocław | Grabowno Wielki - Bukowice | 1 | 18.075 | 24.27 | overhead contact line inspection | 6 | 5 | 30 | traffic interruption (at night) | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 6 | traffic interruption – single-track line | 01.02.2024 | 06.02.2024
595 | 6 | 281 | OLEŚNICA - CHOJNICE | IZ Wrocław | Bukowice - Krośnice | 1 | 25.229 | 32.3 | overhead contact line inspection | 7 | 5 | 35 | traffic interruption (at night) | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 7 | traffic interruption – single-track line | 07.02.2024 | 13.02.2024
596 | 6 | 281 | OLEŚNICA - CHOJNICE | IZ Wrocław | Krośnice - Milicz | 1 | 33.105 | 40.812 | overhead contact line inspection | 8 | 5 | 40 | traffic interruption (at night) | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 8 | traffic interruption – single-track line | 01.03.2024 | 08.03.2024
597 | 6 | 281 | OLEŚNICA - CHOJNICE | IZ Wrocław | Milicz - Zduny | 1 | 42.05 | 54.9 | overhead contact line inspection | 13 | 5 | 65 | traffic interruption (at night) | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 13 | traffic interruption – single-track line | 02.01.2024 | 14.01.2024
598 | 6 | 355 | OSTRÓW WIELKOPOLSKI - GRABOWNO WIELKIE | IZ Wrocław | Bukowina Sycowska - Twardogóra | 1 | 39.661 | 47.559 | overhead contact line inspection | 8 | 5 | 40 | traffic interruption (at night) | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 8 | traffic interruption – single-track line | 07.08.2024 | 14.08.2024
599 | 6 | 355 | OSTRÓW WIELKOPOLSKI - GRABOWNO WIELKIE | IZ Wrocław | Twardogóra Sycowska - Grabowno Wlk | 1 | 48.488 | 53.552 | overhead contact line inspection | 5 | 5 | 25 | traffic interruption (at night) | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 5 | traffic interruption – single-track line | 15.08.2024 | 19.08.2024
600 | 6 | 751 | WROCŁAW GĄDÓW - WROCŁAW ZACHODNI | IZ Wrocław | Wr. Gądów - Wr. Zachodni | 1 | 0.297 | 6.837 | overhead contact line inspection | 7 | 5 | 35 | traffic interruption (at night) | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 7 | traffic interruption – single-track line | 17.01.2024 | 23.01.2024
601 | 6 | 281 | OLEŚNICA - CHOJNICE | IZ Wrocław | Dobroszyce - Grabowno Wielkie | 1 | 9.7 | 16.682 | Subgrade reinforcement | 90 | 24 | 2160 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 6; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 23 | single-track two-way traffic on the active track | 2023-09-25 | 2023-12-23
602 | 6 | 132 | BYTOM - WROCŁAW GŁÓWNY | IZ Wrocław | Oława - Święta Katarzyna | 1 | 155.12 | 169.297 | Construction of Oława Zachodnia stop and subway | 123 | 24 | 2952 | 40 km/h-500m | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 22; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 10 | single-track two-way traffic on the active track | 2024-03-10 | 2024-07-10
603 | 6 | 132 | BYTOM - WROCŁAW GŁÓWNY | IZ Wrocław | Oława - Święta Katarzyna | 2 | 155.12 | 169.297 | Construction of Oława Zachodnia stop and subway | 122 | 24 | 2928 | 40 km/h-500m | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 21; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XI: 9 | single-track two-way traffic on the active track | 2024-07-11 | 2024-11-09
604 | 7 | 351 | POZNAŃ GŁÓWNY - SZCZECIN GŁÓWNY | IZ Poznań | Wronki - Miały | 2 | 52.64 | 53.04 | construction of new platform Wronki-Zamość [Reg. Temp. no. 163/22] | 15 | 24 | 360 | 30 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 15 | single-track two-way traffic on the active track | 2023-09-01 | 2023-12-15
605 | 7 | 351 | POZNAŃ GŁÓWNY - SZCZECIN GŁÓWNY | IZ Poznań | Wronki - Miały | 1 | 52.64 | 53.04 | closure to closed track 2 Reg. Temp. no. 163/22 | 15 | 4 | 60 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 15 | traffic interruption | 2023-09-01 | 2023-12-15
606 | 7 | 351 | POZNAŃ GŁÓWNY - SZCZECIN GŁÓWNY | IZ Poznań | Wronki - Miały | 1 | 52.64 | 53.04 | construction of new platform Wronki-Zamość [Reg. Temp. no. 163/22] | 137 | 24 | 3288 | 30 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 16; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30 | single-track two-way traffic on the active track | 2023-12-16 | 2024-04-30
607 | 7 | 351 | POZNAŃ GŁÓWNY - SZCZECIN GŁÓWNY | IZ Poznań | Wronki - Miały | 2 | 52.64 | 53.04 | closure to closed track 1 Reg. Temp. no. 163/22 | 137 | 4 | 548 | no limit | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 16; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 29; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30 | traffic interruption | 2023-12-16 | 2024-04-30
608 | 7 | 3 | WARSZAWA ZACHODNIA - KUNOWICE | IZ Poznań | Nowy Tomyśl-Zbąszyń | 1 | 362.518 | 373.1 | Mechanical cleaning, topping up of the ballast and associated works on track 1 from km 362.518 to km 373.100 on line 003 | 61 | 24 | 1464 | 60 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30 | single-track two-way traffic on the active track | 2024-08-01 | 2024-09-30
609 | 7 | 14 | ŁÓDŹ KALISKA - TUPLICE | IZ OSTRÓW WLKP. | Wschowa | 1,3,5,7,9,11 | 245.434 |  | Bridge renovation | 61 | 24 | 1464 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30 | traffic on active track at the station | 2024-08-01 | 2024-09-30
610 | 7 | 14 | ŁÓDŹ KALISKA - TUPLICE | IZ OSTRÓW WLKP. | Wschowa | 2,4,6 | 245.434 |  | Bridge renovation | 31 | 24 | 744 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31 | traffic on active track at the station | 2024-10-01 | 2024-10-31
611 | 7 | 14 | ŁÓDŹ KALISKA - TUPLICE | IZ OSTRÓW WLKP. | Błaszki | 3 | 78.7522 | 79.6907 | Repair of track 3 | 61 | 24 | 1464 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30 | traffic on active track at the station | 2024-03-01 | 2024-10-31
612 | 7 | 14 | ŁÓDŹ KALISKA - TUPLICE | IZ OSTRÓW WLKP. | Opatówek | 4 | 98.2592 | 99.1626 | Repair of track 4 | 61 | 24 | 1464 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30 | traffic on active track at the station | 2024-05-01 | 2024-10-31
613 | 7 | 14 | ŁÓDŹ KALISKA - TUPLICE | IZ OSTRÓW WLKP. | Pępowo | 4 | 188.128 | 188.801 | Repair of track 4 | 61 | 24 | 1464 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31 | traffic on active track at the station | 2024-06-01 | 2024-10-31
614 | 7 | 14 | ŁÓDŹ KALISKA - TUPLICE | IZ OSTRÓW WLKP. | Ostrów Wlkp. | 407 | 84.526 | 85.373 | Repair of track 407 | 62 | 24 | 1488 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VIII: 31 | traffic on active track at the station | 2024-07-01 | 2024-10-31
615 | 7 | 14 | ŁÓDŹ KALISKA - TUPLICE | IZ OSTRÓW WLKP. | Ostrów Wlkp. | 409 | 84.526 | 85.428 | Repair of track 409 | 61 | 24 | 1464 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IX: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 X: 31 | traffic on active track at the station | 2024-09-01 | 2024-10-31
616 | 7 | 14 | ŁÓDŹ KALISKA - TUPLICE | IZ OSTRÓW WLKP. | Poniec | 5 | 209.302 | 209.543 | Repair of track 5 | 61 | 24 | 1464 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30 | traffic on active track at the station | 2024-05-01 | 2024-10-31
617 | 7 | 272 | KLUCZBORK - POZNAŃ GŁÓWNY | IZ OSTRÓW WLKP. | Przygodzice | 4 | 76.701 | 77.6201 | Repair of track 4 | 61 | 24 | 1464 | 50 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30 | traffic on active track at the station | 2024-03-01 | 2024-10-31
618 | 7 | 281 | OLEŚNICA - CHOJNICE | IZ OSTRÓW WLKP. | Jarocin - Żerków | 1 | 94.6 | 105.877 | Reconstruction of platform no. 1 at the p.o. Radlin as part of the Government Programme for Upgrade of Platforms | 91 | 24 | 2184 | 30 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 29 | single-track two-way traffic on the active track | 2023-09-05 | 2024-02-29
619 | 7 | 281 | OLEŚNICA - CHOJNICE | IZ OSTRÓW WLKP. | Jarocin - Żerków | 2 | 94.6 | 105.877 | Reconstruction of platform no. 2 at the p.o. Radlin as part of the Government Programme for Upgrade of Platforms | 122 | 24 | 2928 | 30 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30 | single-track two-way traffic on the active track | 2024-03-01 | 2024-06-30
620 | 7 | 281 | OLEŚNICA - CHOJNICE | IZ OSTRÓW WLKP. | Krotoszyn | 1.5 | 63.863 | 64.116 | Reconstruction of platform no. 1 at Krotoszyn station as part of the Government Programme for Upgrade of Platforms | 91 | 24 | 2184 | 30 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 XII: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 I: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 II: 29 | traffic on active track at the station | 2023-09-05 | 2024-02-29
621 | 7 | 281 | OLEŚNICA - CHOJNICE | IZ OSTRÓW WLKP. | Krotoszyn | 2.6 | 63.863 | 64.116 | Reconstruction of platform no. 2 at Krotoszyn station as part of the Government Programme for Upgrade of Platforms | 122 | 24 | 2928 | 30 km/h | no limit | Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 III: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 IV: 30; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 V: 31; Number of planned closing days in the timetable 2023/2024 in individual months from December 2023 to December 2024 VI: 30 | traffic on active track at the station | 2024-03-01 | 2024-06-30
622 | 7 | 370 | ZIELONA GÓRA - ŻARY | IZ Zielona Góra | Zielona Góra Główna- Nowogród Osiedle | 1 | 1.538 | 29.854 | end-to-end surface replacement and reconstruction of engineering structures | 396 | 24 | 9504 | no limit | no limit | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | traffic interruption – single-track line | 2023-08-01 | 2024-12-31
623 | 7 | 370 | ZIELONA GÓRA - ŻARY | IZ Zielona Góra | Nowogród Osiedle -Bieniów | 1 | 29.854 | 40.63 | end-to-end surface replacement and reconstruction of engineering structures | 396 | 24 | 9504 | no limit | no limit | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | traffic interruption – single-track line | 2023-08-01 | 2024-12-31
624 | 7 | 370 | ZIELONA GÓRA - ŻARY | IZ Zielona Góra | Bieniów- Żary | 1 | 40.63 | 52.655 | end-to-end surface replacement and reconstruction of engineering structures | 396 | 24 | 9504 | no limit | no limit | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | traffic interruption – single-track line | 2023-08-01 | 2024-12-31
625 | 8 | 367 | ZBĄSZYNEK - GORZÓW WIELKOPOLSKI | IZ Zielona Góra | Gorzów Wlkp. Zieleniec - Gorzów Wlkp. | 1 | 70.18 | 73.107 | reconstruction of two bridges | 396 | 24 | 9504 | no limit | no limit | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | traffic interruption – single-track line | 2023-06-11 | 2025-10-31
In the absence of a determination of the length of the speed limit on the adjacent track, a section of 2000 m is assumed for the calculation of the upgrade allowance. Speed limits for works lasting more than 4 months are assumed as the basis for the RRJ development.